## General Info
General information
Milestones
| Milestone | Date | Comment
| M0 | 2006-02-23
| S0 | 2006-02-28
| M1 | 2006-03-21
| S15 | 2006-04-25
| S2 | 2006-06-20
| S25 | 2006-07-18
| S3-HW | 2006-08-17
| AS | 2006-08-17
| DS | 2006-09-22
| S4 | 2006-10-09
| M3 | 2006-10-09
PCB Layout:
| A1 | Schematic freeze | 2006-02-17
|  | Tape out | 2006-03-01
|  | Evaluation | 15-03-06 à 06-04-06
|  | Preliminary Quantity | TBD
| A1+ | Schematic & Layout freeze | 2006-04-04
|  | Tape out | 2006-04-06
|  | Evaluation | 25-04-06 à 14-05-06
|  | Preliminary Quantity | TBD
| B1 | Schematic & Layout freeze | 2006-05-14
|  | Tape out | 2006-05-16
|  | Evaluation | 07-06-06 à 23-06-06
|  | Preliminary Quantity | TBD
| B2 | Schematic freeze | 2006-06-23
|  | Tape out | 2006-06-27
|  | Evaluation | 21-07-06 à 09-08-06
|  | Preliminary Quantity | TBD

## Team
General information
Name | Function | Location | Fixed # | Mobile # | 20060208 | 20060215 | 20060222 | 20060301 | 20060308 | 20060315 | 20060322 | 20060329
Poul Erik Rask | PL HW | AAL | +45 7219 5313 | +45 3065 4848 | x |  | x
Flemming Bach Kristensen | PL BB | AAL | +45 7219 5580 | +45 3065 46 88 | x | x | x
Michael Brammer | PL RF | AAL | +45 7219 5461 | +45 3065 4561 | x
Arne Bisgaard Kristensen | PL EA | AAL | +45 7219 5414 | +45 3065 4510 | x | x | x
Randi Bak | PL LPD | AAL | +45 7219 5491 | +45 3065 4599 | x | x | x
Dorte Nielsen | PL LPD VAR | AAL | +45 7219 5375 | +45 3065 4598 | x | x | x
Jens Riedel | LCM1 | KLF | +49 284295 5063 | +49 160 96941519
Katharian Hilker | LCM3 | KLF | +49 284295 5396 | +49 178 7701098 | x | x | x
Christian Primdahl Nielsen (Optional) | PLT | AAL | +45 7219 5372 | +45 3065 4717 | x
Lars Bonde (Optional) | PL ME | AAL | +45 7219 5112 | +45 2045 6872 | x |  | x
x = present
Red = absent

## Travel-Vacation
Name | CW 06 | CW 07 | CW 08 | CW 09 | CW10 | CW11 | CW12 | CW13 | CW14 | CW15 | CW16 | CW17 | CW18 | CW19 | CW20 | CW21 | CW22 | CW23 | CW24 | CW25 | CW26 | CW27 | CW28 | CW29 | CW30
Poul Erik Rask | CW 07: Beijing; CW15: Vacation; CW16: Vacation
Flemming Bach Kristensen
Michael Brammer
Arne Bisgaard Kristensen
Randi Bak
Dorte Nielsen
Jens Riedel
Katharian Hilker
Christian Primdahl Nielsen (Optional) | CW 07: Beijing
Lars Bonde (Optional) | CW 07: Beijing

## BB
Minutes of HW Meeting
| Owner: | Flemming Bach Kristensen
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Status | Topic | Action Item/decision | Owner | Support
1 | closed | I/O connector | The Slim Lumberger is working decision. AD is currently consulted if they can support the Jerry with accessories in the product life time.Vibra is moved above the RF Chamber, and changed to a Hera. | Poul Erik
2 | closed | Keylock side switch | Is there space for the MR sensor in the lower right side? Suggestion from MD and dHW is to use either Hall / MR sensor.Will be included in the first layout | .Kim/Flemming
|  | LCD | Aries display is selected Can the display be rotated 180 degrees? JJA will ask Alps and Phillips, and arrange samples? It is possible to change the viewing directions, so that we can rotate the LCD.It has been decided that the display is rotated 180 degrees, and no changes must be made to the display. So far it’s ok to place the display connector over the cut out for the speaker. | Flemming
3 |  | Battery | Present working assumption is 820 mAh (820 mAh batteri A5B00075547043 / V30145-K1310-X326) We cannot use the Hera battery, it will not help in the design. We need to find the design of the Swan and Hydra battery. Swan battery is too long Design will be presented to VF today includes the 820mAh battery, only if they reject the design we might change the battery. | Flemming
4 |  | Vibra | We are considering a bigger vibra motor | Flemming
5 |  | RFT fixture | Fixture for BB | Flemming
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## RF
Minutes of HW Meeting
Owner:Michael Brammer
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Status | Topic | Action Item/decision | Owner | Support
1 | closed | RF Chipset | Recommendations from RF are to use B6E due to performance and risk in the project. Find cost difference between B6E & IFX (SD1) solutions including external components. Answer will come today. It has been decided that we implement the B6E, it is implemented in the layout as well. | Michael
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## EA
Minutes of HW Meeting
Owner: Arne Bisgaard Kristensen
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Status | Topic | Action Item/decision | Owner | Support
1 | Info | Antenna | Antenna EA suggest a Cadilac antenna with app.90 mm length and feeding point near the center of the antenna. To be placed inside or outside of the plastic Depending on the RF solution. | Arne/Christian
2 |  | Antenna | The schedule for the antenna will be very critical, further investigations are needed. Timeline from B1 samples to AS is limited. | Arne
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## LPD
Minutes of HW Meeting
Owner: Katharina Hilker, Jens Riedel
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Status | Topic | Action Item/decision | Owner | Support
1 |  | On/Off switch | CPM is taking care of eventual patent right. We suggest to use a switch of the same type as the side keys (but single version) A few solutions (Found in SAP) has been provided to Mechanical department, for the on/off switch. Still on-going Ongoing. | Christian/Kim
2 | closed | 2xSidekey | Side-switch will be placed near the antenna. The pcb outline for the switches is to be copied from Philipe/Minos pcb. Today we have 81mm for the antenna, changing the RF solution would give more space
3 |  | Stack up | Is ready, but the outline is missing. First outline is expected Thursday CW06. Not yet received, but is expected at 10:15 the 15th of February 2006
4 | closed | SAR | SAR ring is not implemented currently in Jerry. We need conducting paint in the front part, with 2 contact points. | Arne / Christian
5 | closed | Vibra | Vibra must be placed as close as possible in the corner of the PCB
6 |  | Plastic screw towers | Working assumption is like Penlope pcb Screw towers are not used as fixing point, except for 1 hole in the top of the PCB, we need to check if this has to be moved due to the rotation of the display. Test points can be moved, but must be moved more than 3mm. Still open | Christian
7 |  | Testpoint Drawing | As soon as testpoints are fixed next Monday – Randi will send.a testpoint drawing. | Randi
8 | info | First release of BOM in SAP | A5B00100211853 L36880-N3350-Q JERRY/FIRSTCALC.LIST BEFORE M0
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## LCM
Minutes of HW Meeting
Owner: Randi Bak, Dorte Nielsen
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Status | Topic | Action Item/decision | Owner | Support
1 |  | Testtechnology workshop | Katharina will send mail with requirements from Aalborg | Katharina
2 |  | Production technology work | ½ to 1 day – maybe together with the FMEA | Katharina
3 | info | Materials for A1 prototype run | BOM check shows all components are available | Katharina
4 | info | A1 prototype series | Can be done in 2 days - Monday the 27February we will decide if it will be 9 -10 or 13 - 14 of March | Katharina/Poul Erik
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## Samples-Fixtures-General HW
Minutes of HW Meeting
Owner: Poul Erik Rask
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Status | Topic | Action Item/decision | Owner | Support
1 |  | Fixtures | Depending on fixture reuse from Service. Find a drawing of Penelope fixture.For the first prototype series we can use Penelope fixture | Randi/Katharina
2 |  | MDF | Will it be available for A1+ samples | Poul Erik
3 |  | Sample plan | Will be sent out this week | Poul Erik
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"