## Slide 1: Jerry Project Status
Dr. W. Klebsch / L. Bonde
2006-02-10

## Slide 2: Project Organization

## Slide 3: JERRY Design
…as agreed with Vodafone
… with Aries Display

## Slide 4: JERRY Design – current stackup (SGlite)

## Slide 5: Milestones
M0: 03/02-06
S0: 28/02-06
M1: 14/03-06 A1/B1 + DL
S15: 18/04-06
S2: 17/05-06
S25: 22/06-06
S3: 14/08-06
AS: 14/08-06
S3-HW: 17/08-06
PS: 01/09-06
DS: 15/09-06
M3/S4: 09/10-06

## Slide 6: Jerry Milestones
M0: 23/02-06
S0: 28/02-06
M1: 21/03-06
S15: 25/04-06
S2: 04/07-06
S25: 01/08-06
S3: 31/08-06
PS: 14/09-06
DS: 28/09-06
M3/S4: 26/10-06

## Slide 7: Software Effort Estimation

## Slide 8: Software Effort Estimation

## Slide 9: Project organization - Device Layer

## Slide 10: AAL DL Support
Native
UI
(SISL)
Java
Applications
Java
Framework
Application Engines and Services
(SISL/BEI)
Peripheral Services
(SISL/BEI)
Raw UI
(SISL)
SISL
BEI
AAL

## Slide 11: DL Workareas/packages
Steckbreif Styleguide UE Featurelist dHW delta

## Slide 12: Risks

## Slide 13: Integration Management support

## Slide 14: Integration Management - approach
Facts:
  Stabil Aries SW
  Very short term development time
Consequence:
  Stabilisation and protection of the SW MUST be managed and controlled through out the whole development cycle
    Strict planning of integration points
    Filtering sw maturity deliverires (Qualitity gates, tests)
    Non-immediate workflow
  Incremental integration sequence (layer dependencies)
  Release Management:
    Iterative process with main release every second week, bugfix follow the week after
  ClearQuest bug tracing from the start
  All development on one DB
  Seek to avoid distributed development
  SCRUM approach (i.e. target for next release etc.)

## Slide 15: Integration Management
Status
  IDB in BEJ with Aries SVN 25
  CDB in AAL in sync 09.02.2006
  Workflow TBD in workshop (wk 07)
    Definition of a SW packages from SISL
    Sneak preview from PSE/STSL/SISL
    Release Management
    Tracking team
  OTC (Official Tool Chain) TBC
    Production tooling (Lauterbach, winswup, bfc, etc.)

## Slide 16: Agenda
Monday 13.02.06
  10:00 – 10:30 Introduction / background (Koh Kheng Wah)
  10:30 – 11:00 Current project setup
    Organisation – Set-up BEJ and AAL – PL-T
    Communication scenarios, mailing lists PL-T
  11:00 – 12:00 Project status
    Status HW/MD/ID – Aalborg – HW-PPL
    Status SW – Beijing – SW-PPL
  12:00 – 13:30 Lunch
  13:30 – 17:00 Define process (tailoring) – Thomas Bartel
    Milestones for HW/SW/ST
    Synchronization points
    Define key activities (must have) for each milestones and nice to have’s (based on MEP 7.02)

## Slide 17: Agenda
Tuesday 14.02.06
  9:00 – 17:00 Work
    Split in 3 main groups: HW, SW and ST
    SW: define work packages, feasibility study, CM scenario, contractors, contracts
    HW: review stack-up concept, mechanical design, layout, part list, suppliers
    ST: HW performance test, TA, Cradle/fixture, Test spec, R&D support

## Slide 18: Agenda
Wednesday 15.02.06
  9:00 – 12:00 Continue with work started on Tuesday
  12:00 – 13:30 Lunch
  13:30 – 17:00 Project planning per department (PL-T)
    Create planning per department and define dependencies
    Input planning in PV

## Slide 19: Agenda
Thursday 16.02.06
  9:00 – 9:30 Prototype shops (LCM1 & 3)
    Define which prototype runs take place where
  9:30-12:00 Create handover planning (PPL)
    Detailed steps
  12:00 – 13:30 Lunch
  13:30 – 16:00 Optimize planning (PL-T)
    Based on input from work-days and dependencies
    Create committed milestone planning
  16:00-17:30 Conclusion (PL-T)
    Identify open action items and plan activities
    How far are we from S0/M1?