## Slide 1: Status Project JERRY
Simply Jerry UE Workshop Vodafone – BenQ Mobile VF-Group, Düsseldorf Tower 2105
BenQ Mobile / WK, 22.02.2006

## Slide 2: CONTENTS
Jerry – High Level Features (ID, Software)
Jerry – Project team setup
Jerry – Project Status (ID, HW, SW)
Agile SW development approach
Jerry – Project Schedule
TCD compliance – Smart Simply R3
Open Issue List
Text Input Review List - Feedback
Next Steps
T. Bartl
W. Klebsch
C. Lutsch
ALL

## Slide 3: Jerry – Market Positioning
Jerry is targeting the Vodafone Simply program.
  VF Simply Rel. 1 : Sagem VS1 and VS
  VF Simply Rel. 2: Sagem VS3
  VF Simply Rel. 3: BenQ Jerry (VS4)

## Slide 4: JERRY – Appealing Design
Design Status 20 Feb 2006

## Slide 5: JERRY – “Easy-to-Use” by dedicated hardkeys
 | “Idle Screen / Event Space” “Contacts Space” “Menu Space”
Volume hi/lo
Power on/off
Lock / Unlock
Ringer Profile Setting

## Slide 6: JERRY – “Easy-to-Use” user interface

## Slide 7
BenQ Siemens Jerry –Org Chart per site & function
CPM Kheng Wah
PL-T Arjen Broeze
PL-T Lars Bonde
PL-T Sara Song
Planning
PL CM/IM/DL
NPI
PL QM
PL MD
ST MO
PE
PL- HW
PL SW Yang YQ
SW Architecture
SW QM
3rd Party: SISL India
TPM Zhang Shuai
System Test
Beijing: Software / UE
Aalborg: HW / Mechanics
Beijing / Shanghai:
Business Operations
UE
LCM 1
Accessory Devices
Variant Management
Customer Care
Application Services
Strategy Procurement
QM
BO PL

## Slide 8
BenQ Siemens Jerry –Org Chart per site & function

## Slide 9: Project organization - Device Layer

## Slide 10: AAL DL Support
Native
UI
(SISL)
Java
Applications
Java
Framework
Application Engines and Services
(SISL/BEI)
Peripheral Services
(SISL/BEI)
Raw UI
(SISL)
SISL
BEI
AAL

## Slide 11: Integration Management support

## Slide 12: Jerry – Project Status
Kick-off workshop of the complete Jerry Project Team from Feb 13th to 17th in Beijing:
  the project team is established with clear responsibilities
  the feasibility of all requested features is analyzed
  a detailed project plan is established
  all software workpackages are assigned
  the Agile software development approach is agreed (to be communicated with VF)

## Slide 13: Jerry – Project Status [Hardware & Mechanics]
Stack-up and PCB floorplan in line with new Jerry-ID recently being signed-off by VF.
  ... with minor adaptations on ID to improve ergonomics
First working PCB’s scheduled for Mid 3/06
Fine tuning of mechanical design is running. Design freeze is scheduled for 28 February. Release of 100% data for hardtools on 25 April.

## Slide 14: Jerry – Project Status [Hardware & Mechanics]
Open issues:
  position for lanyard attachment
  keypad back lights – blue vs white
  soft-touch finish on battery cover => potential color mismatch with middle frame
  VF jewel-sticker on soft-touch finish
  Chrome plating of groove in function keypad area

## Slide 15: Jerry – Project Status [Software]
Successfully changed from EGRadio / Apoxi to SGlite / Native platfom in Jan ’06
  ... resolving resources conflicts with Goldfinch (VF listed)
  ... and securing time-to-market for Jerry

## Slide 16: Jerry – Project Status [Software]
Agile software development approach:
  Each software feature is separated into handy work packages of at most 4 weeks duration.
  All features / work packages are collected in a list of prioritized ”backlog” items. This list is owned by the product manager.
  The whole software is developed in several successive steps (”sprints”), in each of which a defined and agreed set of backlog items from the top of the list is handled. This approach is ”test driven” (TDD) and will provide a testable intermediate phone software at the end of each sprint.
  The intermediate software result is checked and released by the customer.

## Slide 17: Jerry – Project Status [Software]
All features are clustered and analyzed:

## Slide 18: Jerry – Project Status [Software]
All features are separated into workpackages of max 4 wks length

## Slide 19: Jerry Key Milestones
M0: 23-02-2006
S0: 28-02-2006
M1: 21-03-2006
S15: 25-04-2006
S2/S25: 18-07-2006
S3: 17-08-2006
PS: 02-10-2006
DS: 09-10-2006
= Design Freeze
B1(+) samples to VF: 03 July
Start acceptance tests: 10 July
Global SW approval: 29 Sept
Shipment to Opcos by: 13 Oct
Customer Milestones
Product Milestones

## Slide 20: Jerry Vodafone Approval plan (SGL)
VF final
acceptance
start shipment
GCF / TA samples
pre-test
acceptance tests
Final
test
8 weeks
Start Test Phase A
B2 Samples
Start Test Phase B
Start Test Phase C
Start Pre Test
B2 Samples
SW Drop 2
SW Drop 1
SW Drop 3
37
36
38
39
25
27
26
28
29
30
35
34
31
32
33
B1 Samples
03.07.06
SW Drop Pre
S25
S3
40
2.10.06
25.09.06
31.07.06
28.8.06
Bugfix +retest

## Slide 21: Jerry Key Milestones
M0: 23-02-2006
S0: 28-02-2006
M1: 21-03-2006
S15: 25-04-2006
S2/S25: 18-07-2006
S3: 17-08-2006
PS: 02-10-2006
DS: 09-10-2006
Agreed Product Backlog 03 Mar
B1(+) samples to VF: 03 July
Start acceptance tests: 10 July
Global SW approval: 29 Sept
Software Milestones (Agile)
Product Milestones
Sprint 1 + Demo by 31 Mar
VF Feedback by 07 Apr
Sprint 2 + Demo by 04 May
VF Feedback by 11 May
Sprint 3 + Demo by 01 Jun
VF Feedback by 08 Jun
Sprint 4 + Demo by 10 Jul
S25-SW 10 Jul
S3-SW 28 July

## Slide 22: Jerry Project Plan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
S0
M0
S15
S2
S3
PS
DS
M3/S4
M1
A1
A1+
B1
B2
Ramp-Up
Pilot Run
Design Freeze
Design Work
Hardtool
Plastic Parts B1
Plastic Parts B2
Sprint 1
Sprint 2
Sprint 3
Sprint 4
pc simu setup
Start-up / power on dialogs
Idle screen
Phone spaces, colour schemes, icons, fonts
Voice call screen basic
Menu look and feel basic
Contact list and menu options
Remove or disable or hide features
Startup Ass.
Startup/ power on dialogues
Idle Screen
Contact list & menu options
Screen Trans. (Sliding Effect)
Volume Side, Ringer Side & and lock key
Sync. incl. remote sync.
Settings
View Contact Log
Remove,disable or hide features
Startup Ass.
Idle Screen
Voice call screens full funct.
Voice messaging
MsgAE
Menu look & Feel – full compliance
Contact List & Menu Options
Screen Transitions (Sliding Effect)
View contact log
Remove, disable or hide features
VF Simply Alarm Clock
Idle Screen
Interruption by events
Sleep mode with timer settings
Text messages (SMS)
hover functionality in Contact list
VF Simply Alarm
MsgAE
Hardware
Test by VF
Test by VF
Test by VF
Pre-Test by VF
Pre-Test by VF
Global SW Approval
Mechanics
Software