## Slide 1
BenQ Siemens Jerry –Org Chart per site & function
BA Jie Gao
CPM Kheng Wah
PL-T Arjen Broeze
PL HW Lars Bonde
PL-T Xin Juan Song
Planning
PL CM/IM/DL
NPI
PL QM
PL MD
ST MO
PE
PL- HW
PL SW Yang Yong Qiang
SW Architecture
SW QM
3rd Party: SISL India
TPM Zhang Shuai
System Test
Site: Beijing / Software / UE
Site: Aarlborg HW/ Mechanics
Site: Beijing/Shanghai/
Business Operations
UE
LCM 1
Accessory Devices
Variant Management
Customer Care
Application Services
Strategy Procurement
QM
BO PL

## Slide 2: Jerry – Project Team
Status 21 Feb 2006
BOM D. Nielsen
LCM3 K. Hilker
PSO B.L. Thomsen
PL SW Yang Y.Q.
PL QM T. Bartel P. Sondergaard
PL MD C. P. Nielsen
ST Li Y. Wei X.K.
PE M. Svendsen
HW P. E. Rask
PL CM/IM/DL A. Hansen
GRM R A. Springer
AD A. Maierhofer
I2P P. E. Rask
LCM1 J. Riedel
SQA Hu X.G.
SW Architecture S. Burkert
L1 /HW rel. SW
Protocol
Stack
Requirement Huang Q.
CM-P Ma Y.T.
RF M. Brammer
DHW Baseband F.B. Kristensen
LPD R. Bak
EA A.B. Kristensen
CPM
Koh K.W.
PL-T
L. Bonde
PL-T Song X.Y. A. Broeze
UE
Lin Y.B.
TPM Zhang S.
AAL
BEJ
KLF / MCH
Key Customer PM
T. Bartel
UE
C. Lutsch

## Slide 3: Jerry Project Plan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
S0
M0
S15
S2
S3
PS
DS
M3/S4
M1
A1
A1+
B1
B2
Ramp-Up
Pilot Run
Design Freeze
Design Work
Hardtool
Plastic Parts B1
Plastic Parts B2
Sprint 1
Sprint 2
Sprint 3
Sprint 4
pc simu setup
Start-up / power on dialogs
Idle screen
Phone spaces, colour schemes, icons, fonts
Voice call screen basic
Menu look and feel basic
Contact list and menu options
Remove or disable or hide features
Startup Ass.
Startup/ power on dialogues
Idle Screen
Contact list & menu options
Screen Trans. (Sliding Effect)
Volume Side, Ringer Side & and lock key
Sync. incl. remote sync.
Settings
View Contact Log
Remove,disable or hide features
Startup Ass.
Idle Screen
Voice call screens full funct.
Voice messaging
MsgAE
Menu look & Feel – full compliance
Contact List & Menu Options
Screen Transitions (Sliding Effect)
View contact log
Remove, disable or hide features
VF Simply Alarm Clock
Idle Screen
Interruption by events
Sleep mode with timer settings
Text messages (SMS)
hover functionality in Contact list
VF Simply Alarm
MsgAE
Hardware
Test by VF
Test by VF
Test by VF
Pre-Test by VF
Pre-Test by VF
Global SW Approval
Mechanics
Software

## Slide 4: Jerry Vodafone Approval plan (SGL)
VF final
acceptance
start shipment
GCF / TA samples
pre-test
acceptance tests
Final
test
8 weeks
Start Test Phase A
B2 Samples
Start Test Phase B
Start Test Phase C
Start Pre Test
B2 Samples
SW Drop 2
SW Drop 1
SW Drop 3
37
36
38
39
25
27
26
28
29
30
35
34
31
32
33
B1 Samples
03.07.06
SW Drop Pre
S25
S3
40
2.10.06
25.09.06
31.07.06
28.8.06
Bugfix +retest