## Slide 1: Product House Europe EF81 – Production Plan / Operator Approval / EXIT-Stability OPC-Europe Report
Mario Topel
BenQ Mobile
14. February 2006

## Slide 2: Production Plan Production start to be achieved in cw07

## Slide 3: Component Delivery Plan Production volumes after DS not secured
  Giving example above – already end of Feb we run in component shortage for upcoming production in March/April

## Slide 4
%
Operator Approval Plan EF81 Tremendous number of parallel approvals planned
  1st 18 variants have to be approved till cw15
  To achieve this approval plan an excellent collaboration between ST/SW/PM has to be implemented

## Slide 5: Operator Approval Plan EF81 Tremendous number of parallel approvals planned
  2nd 18 variants have to be approved till cw16
  To achieve this approval plan an excellent collaboration between ST/SW/PM has to be implemented

## Slide 6: EXIT Stability EF81 significantly better compared to S75 Number of open defects still too high  ~950 Results from SMS on EXIT Team / SW-Project Team
%
  Current nCCPi is 198.000 – thereof 120 defects /w RPN>1000

## Slide 7
%
  Current nCCPi is 198.000 – thereof 120 defects /w RPN>1000
EF81 – Main Problem Areas Beside expected Operator defects – main issues are still weaknesses from SXG75
  R1-R3 – Ranking: AS/S3/DS-relevant (~375 defects):
  R1-R3 prioritized defects are essential:
    e-mails (same as in Wolf5)
    MMS/ SMS (same as in Wolf5)
    Browser (same as in Wolf5)
    DRM (same as in Wolf5)
    Accessory support (various car kits, Audio Quality) (same as in Wolf 5)
    MPM, file transfer (same as in Wolf5)
    Streaming (functionality available, seems to be setting problems)
    Clam shell topics (Kestrel specific)
    Memory leaks (Kestrel specific)
  R4 basically nice to have

## Slide 8: Next Steps Operational Excellence is required to secure launch in March
%
  Declare S3-HW in cw07
  Start production in cw07
  Start VF-approval phase A in cw08
  Stop immediately finger pointing in all functions
  Putting “own” function on save side doesn’t help the company at all
  Replace project manager if they cannot perform the last mile
  As of Wednesday Feb 15th a TTM-Team will be established under lead of TPM which will secure AI-tracking on daily base
  We can launch EF81 in March if we all focus