## Slide 1: Jerry Status Update
Status - Commercial discussions
Ceiling price of 90€ agreed (incl desktop stand and headset) for first 3 months after launch and 84€ for 2nd 3 months after launch.
Vodafone will commit to a minimum volume of 150k in the period from launch to end Dec 06
This volume commitment will remain in place as long as the product is in channels by 15th October
VF have indicated that they are willing to invest 4.5€ million Euros in to the development of Jerry to bring down the net net price to VF opcos (NRE fund). The NRE scenario is as follows:
  4.5€ million would directly subsidise the first 300,000 units by 15€ per unit, thus reducing 1st quarter price to 75€ and the 2nd to 69€.
  The 4.5€ million would be paid in 3 instalments and at significant milestones during the project. VF and BenQ have in principle agreed the following milestones:
    At availability of B1+ samples
    At test of Acceptance testing
    At point of global product SW approval
VF would like to enforce penalties upon late delivery of Jerry by way of non payment of NRE (without any affect on price) and reduction in volume commitment. An agreement here has not been made.
VF have an option to engage BenQ in a design refresh of Jerry in 1st half of 2007.
Agreement will be finalised by way of contract and the outcome will depend largely on Vodafone's level of confidence on TTM.

## Slide 2: Jerry Status Update
Project Status
Initial Jerry launch date was communicated for 1st September 2005.
Delays have occurred to Jerry as a knock on from delays to EGold Apoxi
Product platform has now been swapped to Sgold lite to secure Christmas business.
Current date for shipments from Shanghai is 28th September. A delivery date to opcos has not yet been given.
Vodafone confidence is extremely low that stock will be in channel in time for Christmas business.
Project Risk
The success of Jerry largely depends on Price and Time to Market.
The current concerns around TTM may jeopardise efforts to reduce the price (via NRE) and achieve sales of 150k in CY 06 at the higher price point.
Pulling out of any project would have dire consequences for the relationship with VF.
Short Terms Actions
Take steps to install VF with confidence for a mass market launch before 15th Oct 06
Sign development agreement and secure NRE and volume commitment
Secure delivery timeline.