## Sheet1
Jerry effort estimation
Component / Task | meaning | First Effort Estimation (2006-01-16) | Effort estimation Beijing (2006-01-23) | Effort estimation PHE (2006-01-23) | Comments | Period from/to
C_apbas | AppBasein Native UI (Setup, DRM UI, User Profiles, FAK, Service UI, Application Manager, Vibra & Light) | 32 | 32 | 32 | UI flow, look&feel | start Feb. or March
C_apcnct | Connectivity = ConnectHM + AppConnect | 4 | 4 | 1 | removing features | 1 month before S25
C_apidc | Idle/Call Handling in Native UI (Idle Handling, Call Handling, SIS UI, GSM Setup) | 50 | 150 | 50 | might be higher | start Feb. or March
C_apmm | Multimedia UI in Native UI (Media Folder, Data Exch System, Personalization & PPH, Camera, Sound Recorder, Audio&Sound, Media Player) | 4 | 4 | 4 | removing features | 1 month before S25
C_apMMS | Multimedia Messaging in Client UI (R65) | 16 | 16 | 16 |  | start Feb. or March
C_apmsg | Messaging Application in Native UI (EMS, MMS, EMail, I-MMS. i-Mail, Life!Cast, WAP Push, WAP ITAP, Context Manager, Global Device Inbox=GDI) | 16 | 16 | 16 |  | start Feb. or March
C_appim | Instant Messaging in IMPS | 25 | 25 | 25 |  | start Feb. or March
C_appImail |  | 0 | 0 | 0 |  | start Feb. or March
C_appIMPS |  | 0 | 0 | 0 |  | start Feb. or March
C_AppMenu |  | 2 | 2 | 2 | removing FlexMenu | start Feb. or March
C_ApPoC |  | 0 | 0 | 0 |  | start Feb. or March
C_apreui |  | 6 | 6 | 6 | 2 Man * 3 Month | start Feb. or March
C_Avatar |  | 0 | 0 | 0 |  | start Feb. or March
C_browser |  | 4 | 4 | 4 | remove browser | 1 month before S25
C_coapi |  | 4 | 4 | 4 |  | start Feb. or March
C_cojava | Core Java in Java Framework | 4 | 4 | 4 | remove Java | start Feb. or March
C_couios |  | 8 | 8 | 8 |  | asap
C_DoJa |  | 0 | 0 | 0 |  | start Feb. or March
C_JavaApps |  | 0 | 0 | 0 |  | start Feb. or March
C_JavaAppsExtern |  | 0 | 0 | 0 |  | start Feb. or March
C_mobsim |  | 4 | 4 | 2 | add keys, adapt display size, feature set | asap (setup PCMMI)
C_mopi |  | 2 | 2 | 2 | support for developers
C_security |  | 1 | 1 | 1 | remove DRM feature
C_servims |  | 0 | 0 | 0
C_servPoC |  | 0 | 0 | 0
C_SipRtp |  | 0 | 0 | 0
Object Server |  | 2 | 2 | 2
Device Layer |  | 25 | 25 | 25 |  | PL complete time, 4-5 Dev until End April, 1 Dev complete time
Core Integration Team + IM |  | 36 | 36 | 36 | 20 (DL only) + 4*4 MMI | IM complete time, CIT from April
Customization |  | 2 | 2 | 2 | only one customer, no variants
DSP |  | 0 | 0 | 0 | no changes expected
PC-Tools |  | 2 | 2 | 2 | MPM not clarified
Protocol Stack |  | 4 | 4 | 4 | 1 TAM, support from IFX, 5-6 weeks for new features and bug fixing. | Complete time
CM |  | 10 | 10 | 10 | 1 person + 2 months consultant | Complete time
Smoke Test |  | 8 | 8 | 8 | 1 SM leader + interns | Complete time
BM |  | 20 | 20 | 20 | 2-3 BMs | Complete time
MMI Spec |  |  |  |  | Do we need internal MMI spec?
RM |  | 12 | 12 | 12 | 1 RM + 1 MMI clarifications | Complete time
ST
Component Test |  |  |  |  | assumption: only unit and system test
PL |  | 24 | 24 | 24 | 4 PLs (1 DL (see above), 2 MMI, 1 PL-SW) | Complete time
Architects |  | 16 | 16 | 16 | 1 DL (see above), 2 MMI | Complete time
Effort sum |  | 343 | 443 | 338