## Sheet1
Activity ID | Activity Name | Responsible Site | Start | Finish
Jerry SW FEA PL Jerry SW (VF simply) Feature Planning |  |  | 2006-02-20 09:00 | 2006-07-31 09:00
Jerry SW FEA PL.CMS SW Milestone |  |  | 2006-04-03 09:00 | 2006-07-31 09:00
12 | Sprint 1 SW Demo |  | 2006-04-03 09:00
13 | Sprint 2 SW Demo |  | 2006-05-04 09:00
14 | Sprint 3 SW Demo |  | 2006-06-01 09:00
15 | Sprint 4 SW Demo |  | 2006-07-03 09:00
16 | S25 SW |  | 2006-07-07 09:00
17 | S3 SW |  | 2006-07-28 15:00
18 | VF test phaseA start |  | 2006-07-31 09:00
Jerry SW FEA PL.PRECOND Preconditions |  |  | 2006-02-20 09:00 | 2006-03-24 15:00
2 | Identify all text and icon resources for sprint 1 and sprint 2 | SISL | 2006-02-20 09:00 | 2006-03-03 15:00
3 | Identify all text and icon resources for other sprints | SISL | 2006-03-06 09:00 | 2006-03-17 15:00
4 | Integration of Sprint 1 and 2 texts/icon resources into database | SISL | 2006-02-27 09:00 | 2006-03-10 15:00
5 | Integration of remaining texts/icon resources into database | SISL | 2006-03-13 09:00 | 2006-03-24 15:00
6 | define Font in UIOS | Beijing | 2006-02-20 09:00 | 2006-02-24 15:00
7 | color scheme switch in UIOS | Beijing | 2006-02-20 09:00 | 2006-03-03 15:00
8 | external interfaces from other components, e.g. IDC | SISL | 2006-02-20 09:00 | 2006-03-10 15:00
9 | DB setup |  | 2006-02-20 09:00 | 2006-02-21 15:00
Jerry SW FEA PL.FEA-PL Jerry SW Feature Planning |  |  | 2006-02-22 09:00 | 2006-07-28 15:00
Jerry SW FEA PL.FEA-PL.1 Feature Sprint 1 |  |  | 2006-02-22 09:00 | 2006-03-31 15:00
Jerry SW FEA PL.FEA-PL.1.1 pc simu setup |  |  | 2006-02-22 09:00 | 2006-03-21 15:00
22 | 3 hard keys simulation including blinking effect for Home key | SISL | 2006-02-22 09:00 | 2006-03-21 15:00
23 | side keys simulation | SISL | 2006-02-22 09:00 | 2006-03-07 15:00
| Changes in C_MobSIM for removing/disabling/hiding features | SISL | 2006-02-28 09:00
Jerry SW FEA PL.FEA-PL.1.2 Start-up/power on dialogs |  |  | 2006-02-22 09:00 | 2006-03-21 15:00
25 | PIN input including error handling | SISL | 2006-02-22 09:00 | 2006-03-21 15:00
Jerry SW FEA PL.FEA-PL.1.3 Idle screen |  | SISL | 2006-02-22 09:00 | 2006-03-21 15:00
27 | Idle screen basic layout |  | 2006-02-22 09:00 | 2006-03-21 15:00
28 | Home/Contact/Menu hard key invocation | SISL | 2006-02-22 09:00 | 2006-03-21 15:00
Jerry SW FEA PL.FEA-PL.1.5 Phone spaces, color schemes, Icons, Fonts |  |  | 2006-03-06 09:00 | 2006-03-17 15:00
30 | color scheme switching interface, define additional virtual colors | Beijing | 2006-03-06 09:00 | 2006-03-17 15:00
31 | text resource define color scheme | Beijing | 2006-03-06 09:00 | 2006-03-13 10:00
32 | phone space color scheme switching(IDC) | SISL | 2006-03-06 09:00 | 2006-03-13 10:00
Jerry SW FEA PL.FEA-PL.1.6 Voice call screen basic |  |  | 2006-02-22 09:00 | 2006-03-21 15:00
34 | call origination, termination, call setup | SISL | 2006-02-22 09:00 | 2006-03-21 15:00
35 | Headline and soft key look and feel | SISL | 2006-02-22 09:00 | 2006-03-21 15:00
Jerry SW FEA PL.FEA-PL.1.8 Menu look and feel basic |  |  | 2006-02-22 09:00 | 2006-03-21 15:00
37 | look and feel w/o transition | Beijing | 2006-02-22 09:00 | 2006-03-21 15:00
38 | scroll bar | SISL | 2006-03-06 09:00 | 2006-03-17 15:00
Jerry SW FEA PL.FEA-PL.1.9 Contact list and menu options (Without functionality inside) after pressing Contact hard key |  |  | 2006-03-06 09:00 | 2006-03-24 15:00
40 | list address book | SISL | 2006-03-06 09:00 | 2006-03-17 15:00
41 | display menu options with some functions, e.g. copy, delete, add | SISL | 2006-03-06 09:00 | 2006-03-24 15:00
Jerry SW FEA PL.FEA-PL.1.10 Remove or disable or hide features |  |  | 2006-02-22 09:00 | 2006-03-31 15:00
43 | Java (remove) | Beijing | 2006-02-22 09:00 | 2006-02-28 15:00
44 | Development test and Sprint 1 ST | Beijing | 2006-03-29 09:00 | 2006-03-31 15:00
Jerry SW FEA PL.FEA-PL.2 Feature Sprint 2 |  |  | 2006-02-22 09:00 | 2006-04-28 15:00
46 | Tips including sub-menus | SISL | 2006-03-13 09:00 | 2006-04-07 15:00
Jerry SW FEA PL.FEA-PL.2.2 Startup Assistant |  |  | 2006-03-13 09:00 | 2006-03-17 15:00
48 | Enter own number | SISL | 2006-03-13 09:00 | 2006-03-17 15:00
Jerry SW FEA PL.FEA-PL.2.3 Start-up/power on dialogs |  |  | 2006-03-13 09:00 | 2006-03-13 09:00
50 | date and time setup (covered by Sprint 2 - Settings) | SISL | 2006-03-13 09:00
Jerry SW FEA PL.FEA-PL.2.4 Idle screen |  |  | 2006-03-29 09:00 | 2006-04-25 15:00
52 | Idle UI adaption on network selection | SISL | 2006-04-03 09:00 | 2006-04-14 15:00
53 | show call setting: call barring incoming/outcoming if abroad (new ), effect in Idle | SISL | 2006-03-29 09:00 | 2006-04-25 15:00
Jerry SW FEA PL.FEA-PL.2.5 Contact list and menu options (Without functionality inside) after pressing Contact hard key |  |  | 2006-03-27 09:00 | 2006-04-21 15:00
55 | contact editor | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
56 | merge entry in sim to contact list | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
57 | complicated functions: add reminder, sim backup w/o view log | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
58 | call record look and feel | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
Jerry SW FEA PL.FEA-PL.2.6 Screen transitions (Sliding effect) |  |  | 2006-03-22 09:00 | 2006-04-18 15:00
60 | sliding effect | Beijing | 2006-03-22 09:00 | 2006-04-18 15:00
Jerry SW FEA PL.FEA-PL.2.7 Volume side key, Ringer side key and lock key invocation |  |  | 2006-03-08 09:00 | 2006-04-05 11:00
62 | ringer side key in idle | SISL | 2006-03-08 09:00 | 2006-03-21 15:00
63 | volume side key in call | SISL | 2006-03-22 09:00 | 2006-03-29 10:00
64 | lock key | SISL | 2006-03-29 10:00 | 2006-04-05 11:00
Jerry SW FEA PL.FEA-PL.2.8 Synchronization including remote sync and sync with SIM |  |  | 2006-02-22 09:00 | 2006-03-28 15:00
66 | SyncML UI adaption | SISL | 2006-02-22 09:00 | 2006-03-21 15:00
67 | SyncML workflow adaption | SISL | 2006-02-22 09:00 | 2006-03-28 15:00
Jerry SW FEA PL.FEA-PL.2.9 Settings |  |  | 2006-03-22 09:00 | 2006-04-21 15:00
69 | ring tong, keypad tone, time/date | SISL | 2006-04-03 09:00 | 2006-04-21 15:00
70 | display my number, language, change PIN | SISL | 2006-04-03 09:00 | 2006-04-21 15:00
71 | Unified Inbox (Layout) | SISL | 2006-03-22 09:00 | 2006-04-04 15:00
72 | Templates/Drafts | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
Jerry SW FEA PL.FEA-PL.2.12 View contact log |  |  | 2006-03-27 09:00 | 2006-04-21 15:00
74 | new msg info table support in PIM AE | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
75 | sorting mechanism | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
76 | UI implementation in PIM | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
77 | export inteface (insert contact, select contact) to external appl. i.e. messaging, IDC | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
78 | call record adaption | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
Jerry SW FEA PL.FEA-PL.2.13 Remove or disable or hide features |  |  | 2006-03-27 09:00 | 2006-04-28 15:00
80 | Irda, BT (remove) | SISL | 2006-04-03 09:00 | 2006-04-14 15:00
81 | Camera (remove) | SISL | 2006-04-03 09:00 | 2006-04-14 15:00
82 | Browser (hide) | SISL | 2006-03-27 09:00 | 2006-04-21 15:00
83 | showing UI notification about accessory from connectivity (disable) | SISL | 2006-04-03 09:00 | 2006-04-14 15:00
84 | customization | Beijing | 2006-04-10 09:00 | 2006-04-21 15:00
85 | Development test and Sprint 2 ST | Beijing | 2006-04-25 09:00 | 2006-04-28 15:00
Jerry SW FEA PL.FEA-PL.3 Feature Sprint 3 |  |  | 2006-03-20 09:00 | 2006-05-31 15:00
87 | Key lock screen after switching the key lock hard key. | SISL | 2006-04-19 09:00 | 2006-05-19 15:00
88 | Inbox UI (all message list) | SISL | 2006-03-27 09:00 | 2006-04-28 15:00
89 | Settings complete | SISL | 2006-04-24 09:00 | 2006-05-17 15:00
Jerry SW FEA PL.FEA-PL.3.4 Startup Assistant |  |  | 2006-03-29 09:00 | 2006-05-19 15:00
91 | SyncML invocation | SISL | 2006-03-29 09:00 | 2006-04-04 15:00
Jerry SW FEA PL.FEA-PL.3.4.2 Idle screen |  |  | 2006-05-08 09:00 | 2006-05-19 15:00
93 | new event dialog (part of Unified Inbox) | SISL | 2006-05-08 09:00 | 2006-05-19 15:00
Jerry SW FEA PL.FEA-PL.3.5 Voice call screens full function |  |  | 2006-04-24 09:00 | 2006-05-24 15:00
95 | all call list | SISL | 2006-05-08 09:00 | 2006-05-19 15:00
96 | handling different network release codes | SISL | 2006-04-24 09:00 | 2006-05-24 15:00
97 | call reminder | SISL | 2006-04-24 09:00 | 2006-05-24 15:00
98 | in-call menu adaption | SISL | 2006-05-08 09:00 | 2006-05-19 15:00
Jerry SW FEA PL.FEA-PL.3.6 Voice messaging |  |  | 2006-03-20 09:00 | 2006-05-24 15:00
100 | view and editor | SISL | 2006-03-20 09:00 | 2006-05-24 15:00
101 | send and receive | SISL | 2006-05-08 09:00 | 2006-05-19 15:00
Jerry SW FEA PL.FEA-PL.3.7 MsgAE |  |  | 2006-04-10 09:00 | 2006-05-24 15:00
103 | get and update msg table from inbox UI/sent msg UI | SISL | 2006-04-10 09:00 | 2006-05-10 15:00
104 | delete msg and delete all | SISL | 2006-04-17 09:00 | 2006-05-17 15:00
105 | SMS/MMS client updation | SISL | 2006-05-04 09:00 | 2006-05-17 15:00
106 | Picture messaging | SISL | 2006-04-24 09:00 | 2006-05-24 15:00
107 | Message Setting | SISL | 2006-04-24 09:00 | 2006-05-17 15:00
Jerry SW FEA PL.FEA-PL.3.10 Menu look and feel - full compliance |  |  | 2006-03-22 09:00 | 2006-05-12 15:00
109 | UIOS full compliance (incl. progress bar) | Beijing | 2006-03-22 09:00 | 2006-04-11 15:00
110 | VF menu full compliance (incl. progress bar) | SISL | 2006-04-12 09:00 | 2006-05-12 15:00
Jerry SW FEA PL.FEA-PL.3.11 Contact list and menu options (Without functionality inside) after pressing Contact hard key |  |  | 2006-04-24 09:00 | 2006-05-17 15:00
112 | launch external application, e.g. Voice Messaging, SMS, call | SISL | 2006-04-24 09:00 | 2006-05-10 15:00
113 | PIM settings | SISL | 2006-05-04 09:00 | 2006-05-17 15:00
Jerry SW FEA PL.FEA-PL.3.12 Screen transitions (Sliding effect) |  |  | 2006-04-19 09:00 | 2006-05-19 15:00
115 | menu selection transition | Beijing | 2006-04-19 09:00 | 2006-05-19 15:00
116 | popup transition | Beijing | 2006-04-19 09:00 | 2006-05-19 15:00
Jerry SW FEA PL.FEA-PL.3.13 View contact log |  |  | 2006-04-24 09:00 | 2006-05-10 15:00
118 | adaption in messaging | SISL | 2006-04-24 09:00 | 2006-05-10 15:00
Jerry SW FEA PL.FEA-PL.3.14 Remove or disable or hide features |  |  | 2006-04-24 09:00 | 2006-05-24 15:00
120 | MM removing | SISL | 2006-05-08 09:00 | 2006-05-19 15:00
121 | DRM (disable) | Beijing | 2006-04-24 09:00 | 2006-05-24 15:00
Jerry SW FEA PL.FEA-PL.3.15 VF Simply Alarm Clock |  |  | 2006-04-24 09:00 | 2006-05-31 15:00
123 | list all alarm events | SISL | 2006-04-24 09:00 | 2006-05-24 15:00
124 | customization | Beijing | 2006-05-12 09:00 | 2006-05-25 15:00
125 | Development test and Sprint 3 ST | Beijing | 2006-05-26 09:00 | 2006-05-31 15:00
Jerry SW FEA PL.FEA-PL.4 Feature Sprint 4 |  |  | 2006-03-20 09:00 | 2006-07-28 15:00
127 | Idle split screen | SISL | 2006-06-01 09:00 | 2006-06-28 15:00
Jerry SW FEA PL.FEA-PL.4.2 Idle screen |  |  | 2006-03-20 09:00 | 2006-06-09 15:00
129 | Welcome tour | SISL | 2006-06-05 09:00 | 2006-06-09 15:00
130 | Charging display adaption | SISL | 2006-06-05 09:00 | 2006-06-09 15:00
Jerry SW FEA PL.FEA-PL.4.2.3 Interruption by Events |  |  | 2006-03-20 09:00 | 2006-05-30 15:00
132 | Separation of Call functionality from the Idle | SISL | 2006-03-20 09:00 | 2006-04-28 15:00
133 | Call CSM Message Handling | SISL | 2006-04-10 09:00 | 2006-05-24 15:00
134 | Dial Dialog Updation Handling | SISL | 2006-04-28 09:00 | 2006-05-30 15:00
Jerry SW FEA PL.FEA-PL.4.3 Sleep mode with timer settings |  |  | 2006-05-22 09:00 | 2006-06-23 15:00
136 | back to last screen | SISL | 2006-05-22 09:00 | 2006-06-16 15:00
137 | screen saver handling in idle | SISL | 2006-06-12 09:00 | 2006-06-23 15:00
Jerry SW FEA PL.FEA-PL.4.4 Text Message (SMS) |  |  | 2006-05-08 09:00 | 2006-06-14 15:00
139 | view and editor | SISL | 2006-05-08 09:00 | 2006-06-09 15:00
140 | send and receive | SISL | 2006-06-01 09:00 | 2006-06-14 15:00
Jerry SW FEA PL.FEA-PL.4.5 hover functionality in Contact list |  |  | 2006-05-22 09:00 | 2006-06-16 15:00
142 | Implementation by UIOS | SISL | 2006-05-22 09:00 | 2006-06-02 15:00
143 | PIM Adaption | SISL | 2006-06-05 09:00 | 2006-06-16 15:00
144 | messaging adaption | SISL | 2006-06-05 09:00 | 2006-06-16 15:00
Jerry SW FEA PL.FEA-PL.4.6 VF Simply Alarm Clock |  |  | 2006-05-04 09:00 | 2006-06-28 15:00
146 | time/date editor | SISL | 2006-05-29 09:00 | 2006-06-09 15:00
147 | alarm text | SISL | 2006-05-29 09:00 | 2006-06-02 15:00
148 | alarm tone/volume/vibration | SISL | 2006-05-29 09:00 | 2006-06-16 15:00
149 | menu options in alarm clock, i.e. delete, add | SISL | 2006-06-01 09:00 | 2006-06-14 15:00
150 | Unified Inbox Functionality | SISL | 2006-05-04 09:00 | 2006-06-28 15:00
151 | Unified sent message | SISL | 2006-05-29 09:00 | 2006-06-23 15:00
152 | Delete (All) wizard | SISL | 2006-05-29 09:00 | 2006-06-23 15:00
Jerry SW FEA PL.FEA-PL.4.10 MsgAE |  |  | 2006-04-24 09:00 | 2006-07-28 15:00
154 | Sync between message table in PIM and message DB in AppMsg | SISL | 2006-04-24 09:00 | 2006-05-17 15:00
155 | customization | Beijing | 2006-06-05 09:00 | 2006-06-23 15:00
156 | Development test and Sprint 4 ST | Beijing | 2006-06-26 09:00 | 2006-06-30 15:00
157 | S25 SW bugfix | Beijing/SISL | 2006-07-03 09:00 | 2006-07-28 15:00
Jerry SW FEA PL.ST_TST System Test |  |  | 2006-06-26 09:00 | 2006-07-21 15:00
159 | 1st full run | Beijing | 2006-06-26 09:00 | 2006-07-21 15:00