## Cover
For internal use only
COM MD PD |  |  | Jerry
Jerry.04.25-001
SW Risk Management Plan (SRMP)

Status | released |  |  |  |  | Versioncheck
Version | 1.0_002 |  |  |  |  | 1.0_002
Date | 2006-03-08 |  |  |  |  | 2
4
1
Responsible | Yang Yong Qiang |  | COM MD PD SW |  | PL SW | 0
002
Author(s) | Yang Yong Qiang |  | COM MD PD SW |  | PL SW | TRUE
TRUE
TRUE
Release | Yang Yong Qiang |  | COM MD PD SW |  | PL SW | TRUE
Template: SRMP.xls
Status:Released |  | Version: 1.2_003 |  | Date: 2004-09-23
Copyright (C) Siemens AG 2004
The information contained herein is confidential and the property of Siemens AG and is supplied without liability for errors or omissions. No part may be reproduced or used except as authorised by contract or other written permission. The copyright and the foregoing restriction on reproduction and use extend to all media in which the information may be embodied. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.
Published by | COM MD PD
Siemens AG
Note on F6: GENERAL USAGE GUIDELINES Specify the document attributes (organizational unit, document scope, identifier, title, status, version, etc.) only on the cover sheet. The footer lines on all sheets use references to the text entered here and are actualized automatically by macro when the document is being saved. The format and layout of the cover sheet including header and footer lines must not be changed. If the document is uniquely identified by the "Scope" (e.g. the project or component name) and the "Title" (e.g. the name of an artefact required by the development process), the separate attribute "Identifier" may be omitted. The attributes "Status" and "Version" are mandatory for documents that are regularly changed or formally approved. The "Release" signature is only required for documents that are officially released.

## History of Change
Template History of Change
This table shows the History of Change for the SRMP template, not the instantiated SRMP. It may be deleted when creating an SRMP.
Version | Date | Editor | Status | Description
1.0_011
1.1_001 | 2004-04-08 | Canditt | in review | This table added
Performance improved by deleting footer fields and removing macro Workbook_BeforeSave
Guideline shortened, moved to comments
New columns risk status instead of category
Classification / quantification / reset links buttons removed
1.1_002 | 2004-04-19 | Canditt | in review | header and footer lines adapted for all remaining worksheets
1.1_003 | 2004-04-20 | Canditt | released | incorporation of review remarks from J.Haag
1.1_004 | 2004-06-07 | Conolly | released for piloting | Entered a new Column "Raised by", in order to do this I also changed the macros. Performance Improvement
1.1_005 | 2004-06-15 | Conolly | released for piloting | Updated <<DocVersion>> from x.y/zzz to new standard versioning format x.y_zzz
1.2_001 | 2004-08-18 | Conolly/ Canditt | released | All Macros deleted, reporting worksheet removed, added columns for Platform and Product Projects and addressed all open Process Requests
1.2_002 | 2004-09-16 | Conolly | released | Added Risk report
1.2_003 | 2004-09-23 | Conolly | released | Modified Risk Report so that occurred and cancelled risks would not be counted in the risk exposure or appear in the graphs.
History of Change
Version | Date | Editor | Status | Description
1.0_001 | 2006-01-23 | AALhhs | Released | Initial version.
1.0_002 | 2006-03-08 | Yang Yong Qiang | released | updated for M0, and template version update
Note on A5: Louis Peter: Format “x.y_zzz”. The version string consists of the planned major “x” and minor “y” version, and the editorial revision or step “zzz” which starts from 001 with each new planned version "x.y". Thus the first version string is “1.0_001”.
Note on A22: Louis Peter: Format “x.y_zzz”. The version string consists of the planned major “x” and minor “y” version, and the editorial revision or step “zzz” which starts from 001 with each new planned version "x.y". Thus the first version string is “1.0_001”.

## Guideline
Guideline
The purpose of this template is to provide maximum control over project risks with a minimum of effort using one single risk management plan in the risk management process.
For a detailed description refer to the SW Risk Management Process.
The work with this template comprises the following steps:
Instantiation of template
Adjust parameters in worksheet Risk Classes
Risk identification
Document identified risks in worksheet Risk Plan, area Risk Identification.
Risk assessment
Document risk probability and impact in worksheet Risk Plan, area Risk assessment
Risk handling
Document risk handling activities in worksheet Risk Plan, area Risk handling

## Risk Classes
0
0
Project data |  | Planned schedule |  | Planned cost |  |  | 0
0
|  | 160 | days | 150000000 | Euro
Risk classes |  | Schedule delay |  | Cost increase
Disastrous | ≥ | 5 | days | 20000 | Euro | Missing links
Critical | ≥ | 1 | days | 6000 | Euro
Undesired | ≥ | 0 | days | 2000 | Euro
Tolerable | ≥ | 0 | days | 0 | Euro
Please specify the thresholds for the highest risk class with respect to schedule delay and cost increase for your project, as appropriate. The thresholds for the other risk classes are calculated accordingly. The planned project data is optional and may be documented simply for comparison. The thresholds of the highest risk class are used to caculate the normalized risk exposure: [Risk Exposure] = [Risk Probability] x [Risk Impact], where [Risk Impact] = [Normalised Schedule Impact] + [Normalised Cost Impact]. * The values in brackets are dimensionless numbers, and the units are defined by the thresholds of the highest risk class. * Note that each risk can have an impact either on the schedule, or the cost, or on both.

## Config (hidden)
Disastrous | 1 | 2 | 0.875 | 5 | 20000 | 10 | 40000
Critical | 0.3 | 0.65 | 0.625 | 1 | 6000 | 3.25 | 13000
Undesired | 0.1 | 0.2 | 0.375 | 0 | 2000 | 1 | 4000
Tolerable | 0 | 0.05 | 0.125 | 0 | 0 | 0.25 | 1000
Red | 1
Yellow | 0.3
Green | 0

## Risk Plan
[24 empty] | Disastrous | Active | 10%
|  | Risk identification |  |  | Risk identification |  |  |  |  | Risk assessment | [6 empty] | Risk assessment | Risk handling |  |  |  |  | Risk handling | Critical | Occurred | 40%
[10 empty] | Top 10 Risks: Select all rows> Data> Sort> Choose Column | [13 empty] | Undesired | Cancelled | 60%
[12 empty] | Yellow cells perform the calculation; do not edit!! |  |  | Total Exposure | 1.31 | [7 empty] | Tolerable | Problem | 90%
[15 empty] | (Active, Transferred or Problem only) | [9 empty] | Transferred
No. | Risk description | Implication on project | Raised by | Risk Status | Identification date | Platform | <<Product Name>> | <<Product Name>> | <<Product Name>> | Last change date | Probability | Schedule impact [class] | Schedule impact [day] | Cost impact [class] | Cost impact [Euro] | Exposure | Risk class | Risk handling activity | Trigger | Responsible | Planned date | Planned cost | Handling Activity Status
| Too few wingboards | Bottleneck situation when debuging. | Hans Henrik Skovgaard | Problem | 2006-01-23 |  |  |  |  | 2006-03-08 | 90% | Critical | 9.75 | Tolerable | 2000 | 0.63 | Undesired | Collect/order and modify Aries boards | no enough winboards for SISL/Beijing | Allan Hansen |  |  | Active
| Availabiliy of B1 software. | Delay HW veryfication | Hans Henrik Skovgaard | Active | 2006-01-23 |  |  |  |  | 2006-03-08 | 40% | Undesired | 3 | Critical | 26000 | 0.34 | Undesired
| CM environment. | Delay sw deliveries. | Hans Henrik Skovgaard | Cancelled | 2006-01-23 |  |  |  |  | 2006-03-08 | 10% | Undesired | 3 | Tolerable | 2000 | 0.025 | Undesired | close cooperation for BM in AAL/Beijing/SISL |  | Allan Hansen |  |  | Completed
| Sw development divided on more than 2 cites. A difficult task to manage | Delay DS. | Hans Henrik Skovgaard | Cancelled | 2006-01-23 |  |  |  |  | 2006-03-08 | 40% | Undesired | 3 | Tolerable | 2000 | 0.1 | Undesired | close cooperation |  | Yang Yong Qiang |  |  | Completed
| New UI on native platform. | Delay DS. | Hans Henrik Skovgaard | Cancelled | 2006-01-23 |  |  |  |  | 2006-03-08 | 40% | Critical | 9.75 | Tolerable | 2000 | 0.28 | Undesired | Deep investigations by System Arch and component Arch, on time technical support |  | Chen Mian, Stefan Burkert |  |  | Active
| Lack of resources with necessary competences in BEJ.(AppMMS, AppMSG) | Delay DS. | Hans Henrik Skovgaard | Cancelled | 2006-01-23 |  |  |  |  | 2006-03-08 | 40% | Undesired | 3 | Undesired | 8000 | 0.16 | Critical | Get support from Europe |  | Yang Yong Qiang |  |  | Active
| Open requirements on VF flow | Delay DS. | Yang Yong Qiang | Occurred | 2006-03-08 |  |  |  |  | 2006-03-08 | 90% | Critical | 9.75 | Undesired | 8000 | 0.765 |  | RM should have close coorperation with VF contact person: Thomas Bartl/Clemens Lusch |  | Shen Yu Kai |  |  | Active
| Lack of CA/MMI CIT members on site in Beijing | Delay sw deliveries. | Yang Yong Qiang | Active | 2006-03-08 |  |  |  |  | 2006-03-08 | 40% | Critical | 9.75 | Undesired | 8000 | 0.34 |  | Ask SISL to provide experienced CIT members, or Beijing assigns experienced CA/MMI dev to join CIT |  | Yang Yong Qiang, Allan Hansen |  |  | Planned
| VF font format could not be supported by Native platform | Delay sw Sprint 1 | Yang Yong Qiang | Occurred | 2006-03-08 |  |  |  |  | 2006-03-08 | 90% | Critical | 9.75 | Undesired | 8000 | 0.765 |  | Push VF to provide .RC format, or VF accepts Aries fonts |  | Yang Yong Qiang, Thomas Bartl |  |  | Active
[13 empty] | 0 |  | 0 | 0
[13 empty] | 0 |  | 0 | 0
[13 empty] | 0 |  | 0 | 0
[13 empty] | 13 |  | 0 | 0
[13 empty] | 0 |  | 0 | 0
[13 empty] | 0 |  | 0 | 0
16 | [12 empty] | 0 |  | 0 | 0
17 | [12 empty] | 0 |  | 0 | 0
18 | [12 empty] | 0 |  | 0 | 0
19 | [12 empty] | 0 |  | 0 | 0
20 | [12 empty] | 0 |  | 0 | 0
21 | [12 empty] | 0 |  | 0 | 0
22 | [12 empty] | 0 |  | 0 | 0
23 | [12 empty] | 0 |  | 0 | 0
24 | [12 empty] | 0 |  | 0 | 0
25 | [12 empty] | 0 |  | 0 | 0
26 | [12 empty] | 0 |  | 0 | 0
27 | [12 empty] | 0 |  | 0 | 0
28 | [12 empty] | 0 |  | 0 | 0
29 | [12 empty] | 0 |  | 0 | 0
30 | [12 empty] | 0 |  | 0 | 0
31 | [12 empty] | 0 |  | 0 | 0
32 | [12 empty] | 0 |  | 0 | 0
33 | [12 empty] | 0 |  | 0 | 0
34 | [12 empty] | 0 |  | 0 | 0
35 | [12 empty] | 0 |  | 0 | 0
36 | [12 empty] | 0 |  | 0 | 0
37 | [12 empty] | 0 |  | 0 | 0
38 | [12 empty] | 0 |  | 0 | 0
39 | [12 empty] | 0 |  | 0 | 0
40 | [12 empty] | 0 |  | 0 | 0
41 | [12 empty] | 0 |  | 0 | 0
42 | [12 empty] | 0 |  | 0 | 0
43 | [12 empty] | 0 |  | 0 | 0
44 | [12 empty] | 0 |  | 0 | 0
45 | [12 empty] | 0 |  | 0 | 0
46 | [12 empty] | 0 |  | 0 | 0
47 | [12 empty] | 0 |  | 0 | 0
48 | [12 empty] | 0 |  | 0 | 0
49 | [12 empty] | 0 |  | 0 | 0
50 | [12 empty] | 0 |  | 0 | 0
51 | [12 empty] | 0 |  | 0 | 0
52 | [12 empty] | 0 |  | 0 | 0
53 | [12 empty] | 0 |  | 0 | 0
54 | [12 empty] | 0 |  | 0 | 0
55 | [12 empty] | 0 |  | 0 | 0
56 | [12 empty] | 0 |  | 0 | 0
57 | [12 empty] | 0 |  | 0 | 0
58 | [12 empty] | 0 |  | 0 | 0
59 | [12 empty] | 0 |  | 0 | 0
60 | [12 empty] | 0 |  | 0 | 0
61 | [12 empty] | 0 |  | 0 | 0
62 | [12 empty] | 0 |  | 0 | 0
63 | [12 empty] | 0 |  | 0 | 0
64 | [12 empty] | 0 |  | 0 | 0
65 | [12 empty] | 0 |  | 0 | 0
66 | [12 empty] | 0 |  | 0 | 0
67 | [12 empty] | 0 |  | 0 | 0
68 | [12 empty] | 0 |  | 0 | 0
69 | [12 empty] | 0 |  | 0 | 0
70 | [12 empty] | 0 |  | 0 | 0
71 | [12 empty] | 0 |  | 0 | 0
72 | [12 empty] | 0 |  | 0 | 0
73 | [12 empty] | 0 |  | 0 | 0
74 | [12 empty] | 0 |  | 0 | 0
75 | [12 empty] | 0 |  | 0 | 0
76 | [12 empty] | 0 |  | 0 | 0
77 | [12 empty] | 0 |  | 0 | 0
78 | [12 empty] | 0 |  | 0 | 0
79 | [12 empty] | 0 |  | 0 | 0
80 | [12 empty] | 0 |  | 0 | 0
81 | [12 empty] | 0 |  | 0 | 0
82 | [12 empty] | 0 |  | 0 | 0
83 | [12 empty] | 0 |  | 0 | 0
84 | [12 empty] | 0 |  | 0 | 0
85 | [12 empty] | 0 |  | 0 | 0
86 | [12 empty] | 0 |  | 0 | 0
87 | [12 empty] | 0 |  | 0 | 0
88 | [12 empty] | 0 |  | 0 | 0
89 | [12 empty] | 0 |  | 0 | 0
90 | [12 empty] | 0 |  | 0 | 0
91 | [12 empty] | 0 |  | 0 | 0
92 | [12 empty] | 0 |  | 0 | 0
93 | [12 empty] | 0 |  | 0 | 0
94 | [12 empty] | 0 |  | 0 | 0
95 | [12 empty] | 0 |  | 0 | 0
96 | [12 empty] | 0 |  | 0 | 0
97 | [12 empty] | 0 |  | 0 | 0
98 | [12 empty] | 0 |  | 0 | 0
99 | [12 empty] | 0 |  | 0 | 0
100 | [12 empty] | 0 |  | 0 | 0
101 | [12 empty] | 0 |  | 0 | 0
102 | [12 empty] | 0 |  | 0 | 0
103 | [12 empty] | 0 |  | 0 | 0
104 | [12 empty] | 0 |  | 0 | 0
105 | [12 empty] | 0 |  | 0 | 0
106 | [12 empty] | 0 |  | 0 | 0
107 | [12 empty] | 0 |  | 0 | 0
108 | [12 empty] | 0 |  | 0 | 0
109 | [12 empty] | 0 |  | 0 | 0
110 | [12 empty] | 0 |  | 0 | 0
111 | [12 empty] | 0 |  | 0 | 0
112 | [12 empty] | 0 |  | 0 | 0
113 | [12 empty] | 0 |  | 0 | 0
114 | [12 empty] | 0 |  | 0 | 0
115 | [12 empty] | 0 |  | 0 | 0
116 | [12 empty] | 0 |  | 0 | 0
117 | [12 empty] | 0 |  | 0 | 0
118 | [12 empty] | 0 |  | 0 | 0
119 | [12 empty] | 0 |  | 0 | 0
120 | [12 empty] | 0 |  | 0 | 0
121 | [12 empty] | 0 |  | 0 | 0
122 | [12 empty] | 0 |  | 0 | 0
123 | [12 empty] | 0 |  | 0 | 0
124 | [12 empty] | 0 |  | 0 | 0
125 | [12 empty] | 0 |  | 0 | 0
126 | [12 empty] | 0 |  | 0 | 0
127 | [12 empty] | 0 |  | 0 | 0
128 | [12 empty] | 0 |  | 0 | 0
129 | [12 empty] | 0 |  | 0 | 0
130 | [12 empty] | 0 |  | 0 | 0
131 | [12 empty] | 0 |  | 0 | 0
132 | [12 empty] | 0 |  | 0 | 0
133 | [12 empty] | 0 |  | 0 | 0
134 | [12 empty] | 0 |  | 0 | 0
135 | [12 empty] | 0 |  | 0 | 0
136 | [12 empty] | 0 |  | 0 | 0
137 | [12 empty] | 0 |  | 0 | 0
138 | [12 empty] | 0 |  | 0 | 0
139 | [12 empty] | 0 |  | 0 | 0
140 | [12 empty] | 0 |  | 0 | 0
141 | [12 empty] | 0 |  | 0 | 0
142 | [12 empty] | 0 |  | 0 | 0
143 | [12 empty] | 0 |  | 0 | 0
144 | [12 empty] | 0 |  | 0 | 0
145 | [12 empty] | 0 |  | 0 | 0
146 | [12 empty] | 0 |  | 0 | 0
147 | [12 empty] | 0 |  | 0 | 0
148 | [12 empty] | 0 |  | 0 | 0
149 | [12 empty] | 0 |  | 0 | 0
150 | [12 empty] | 0 |  | 0 | 0
151 | [12 empty] | 0 |  | 0 | 0
152 | [12 empty] | 0 |  | 0 | 0
153 | [12 empty] | 0 |  | 0 | 0
154 | [12 empty] | 0 |  | 0 | 0
155 | [12 empty] | 0 |  | 0 | 0
156 | [12 empty] | 0 |  | 0 | 0
157 | [12 empty] | 0 |  | 0 | 0
158 | [12 empty] | 0 |  | 0 | 0
159 | [12 empty] | 0 |  | 0 | 0
160 | [12 empty] | 0 |  | 0 | 0
161 | [12 empty] | 0 |  | 0 | 0
162 | [12 empty] | 0 |  | 0 | 0
163 | [12 empty] | 0 |  | 0 | 0
164 | [12 empty] | 0 |  | 0 | 0
165 | [12 empty] | 0 |  | 0 | 0
166 | [12 empty] | 0 |  | 0 | 0
167 | [12 empty] | 0 |  | 0 | 0
168 | [12 empty] | 0 |  | 0 | 0
169 | [12 empty] | 0 |  | 0 | 0
170 | [12 empty] | 0 |  | 0 | 0
171 | [12 empty] | 0 |  | 0 | 0
172 | [12 empty] | 0 |  | 0 | 0
173 | [12 empty] | 0 |  | 0 | 0
174 | [12 empty] | 0 |  | 0 | 0
175 | [12 empty] | 0 |  | 0 | 0
176 | [12 empty] | 0 |  | 0 | 0
177 | [12 empty] | 0 |  | 0 | 0
178 | [12 empty] | 0 |  | 0 | 0
179 | [12 empty] | 0 |  | 0 | 0
180 | [12 empty] | 0 |  | 0 | 0
181 | [12 empty] | 0 |  | 0 | 0
182 | [12 empty] | 0 |  | 0 | 0
183 | [12 empty] | 0 |  | 0 | 0
184 | [12 empty] | 0 |  | 0 | 0
185 | [12 empty] | 0 |  | 0 | 0
186 | [12 empty] | 0 |  | 0 | 0
187 | [12 empty] | 0 |  | 0 | 0
188 | [12 empty] | 0 |  | 0 | 0
189 | [12 empty] | 0 |  | 0 | 0
190 | [12 empty] | 0 |  | 0 | 0
191 | [12 empty] | 0 |  | 0 | 0
192 | [12 empty] | 0 |  | 0 | 0
193 | [12 empty] | 0 |  | 0 | 0
194 | [12 empty] | 0 |  | 0 | 0
195 | [12 empty] | 0 |  | 0 | 0
196 | [12 empty] | 0 |  | 0 | 0
197 | [12 empty] | 0 |  | 0 | 0
198 | [12 empty] | 0 |  | 0 | 0
199 | [12 empty] | 0 |  | 0 | 0
200 | [12 empty] | 0 |  | 0 | 0
Note on B6: Risk Description: [mandatory] Describe the risk and its origin. Also describe the "drivers", i.e. the facts that influence the probability of the risk event.
Note on C6: Implication on Project: [mandatory] Briefly describe the consequences for the project if the risk occurs. Also describe the "drivers", i.e. the facts that influence the probability and the magnitude of the impact.
Note on D6: Raised by: [mandatory] Please enter the name of the person that highlighted the risk.
Note on E6: Status: [mandatory] Active: identified risk, needs continuous attention Occurred: risk has already occurred Cancelled: risk cannot or is unlikely to occur any more Problem: risk is a problem (probability > 90 %); handled elsewhere (in report problem lists) Transferred: Tranferred to another party; handled by another risk management plan. Reference new responsible/ location in the "risk handling activity column". Note: To sort without Cancelled entries, click on filter arrow> Custom >Status >Not equal to > Cancelled
Note on F6: Identification date: [mandatory] Specify the indentification date of the risk.
Note on G6: Platform & <<Product Name>>: [Mandatory] Enter an "X" if risk has an impact on this project
Note on K6: Last Change Date: [mandatory] Specify the last change date of the risk record. Note that risks should be re-assessed regularly throughout the project life cycle.
Note on L6: Probability: [mandatory] The probability is a rough estimate, therefore only rough classes are possible inputs. A risk with a probability of 90% is a problem. The PL decides whether to handle this risk in this plan or to transfer it to a problem list.
Note on M6: Schedule impact: [optional] Classify the schedule impact of the risk according to the thresholds defined in the worksheet "Risk Classes". Note that cost impact or schedule impact must be specified.
Note on N6: Schedule impact [day]: [optional] The estimated schedule delay in working days if the risk occurs. If countermeasures are defined, then the residual risk should be assessed.
Note on O6: Cost impact [class]: [optional] Classify the cost impact of the risk according to the thresholds defined in the worksheet "Risk Classes". Note that cost impact or schedule impact must be specified.
Note on P6: Cost impact [Euro]: [optional] The estimated project cost increase in Euro if the risk occurs. If countermeasures are defined, then the residual risk should be assessed. No scientific accuracy is needed ! Note that cost impact or schedule impact must be specified.
Note on Q6: Exposure: [calculated] The dimensionless risk exposure is defined as: [Exposure] = [Probability] x [Impact] where the normalized impact number is determined from the schedule and cost impacts by comparing against the thresholds specified in the Data sheet.
Note on R6: Risk Class: [calculated] The risk class is derived from the risk exposure as follows: Exposure ≥ 1,0 : Disastrous Exposure ≥ 0,3 : Critical Exposure ≥ 0,1 : Undesired Exposure < 0,1 : Tolerable
Note on S6: Risk handling activity: [mandatory] Describe (proactive) countermeasures (incl. ref to work package in project plan) and/or (reactive) contingency plans. If risk has project external impact, add ref to informed persons. If risk is not handled, provide a reason.
Note on T6: Trigger: [optional] Enter any threshold value or other criterium which, when exceeded, triggers the contingency plans to be put into action.
Note on U6: Responsible: [mandatory] Name the responsible for the planned countermeasure.
Note on V6: Planned date: [optional] Set the end date for the planned countermeasure to be completed. If the countermeasure has been included in the project work break down structure, the planned date may be omitted here.
Note on W6: Planned cost: [optional] Enter the estimated cost of the planned countermeasure. If the countermeasure has been included in the project work break down structure, the planned cost may be omitted here.
Note on X6: Status: [mandatory] Set the status of the countermeasure. Open : Not decided yet. None : Risk accepted, no handling activity taken. Planned : Activities have been planned. Active : Activities are being performed. Completed : Activities have been completed.

## Risk Report
Risk Report
| Project : <<DocScope>> |  |  |  |  | Date: | <<DocDate>>
Risk Assessment
|  | Risk Class Count |  | Risk Status Count
(Active, Transferred or Problem only)
|  | Disastrous | 0 | Active | 2 | Total Exposure | 1.31
|  | Critical | 0 | Transferred | 0
|  | Undesired | 2 | Problem | 1
|  | Tolerable | 0
|  | Total | 2 | Total | 3
|  |  |  | Occurred | 2
|  |  |  | Cancelled | 4
Risk Status
Risk Class Count (Active, Transferred or Problem only)