## M1
Jerry M1 Milestone. Items critical or blocking for milestone declaration
Blocking |  | Blocking issue for declaring the specific milestone
Critical |  | Problem to be solved later- solution and timeframe must however be known and agreed
Milestone can be/is approved
Line | M1 | Blocking or critical issue | Status | Comment | Risk assesment | Actions | Who | When
BB - F. B. Kristensen |  | No big risk and blocks for M1 except the timeline
RF - M. Brammer |  | No big risk and blocks for M1 except the timeline
| blocking | S0 blocking point: board outline and stackup concept finalized |  | Expected to be finished on Mar. 16
EA - A. B. Krisensen |  | No big risk, no blocking points for M1 |  | Expect to declare on Mar. 20
MD - C. P. Nielsen
| Blocking | Design FMEAs | scheduled | Will be done on 21-22/3
| Critical | TTDs | not started | Draft versions need to be done before M1
| Blocking | MAP plan | not started
SW - Y. Y. Qiang | Critical | Lack of CIT members for CA/MMI. | not started | Planning: - 2 SISL CIT member to be onsite from mid May to end Sept., maybe earlier, depending on number of bugs - 2 enployees onsite from beginning of June. |  | SW director/line manager should provide proper resources. | Juergen Bonfert, Yang Yong Qiang | by end of March.
| Critical | No modified wingboard in SISL so far, which might endanger SW Sprint 1 | active |  |  |  | Allan Hensan, Yang Yong Qiang | by 21.03.06
| Blocking | Some requirements still open and to be clarified with VF. | active | Some features required by VF must be compromised due to high effort, e.g. Text Editor. |  | Get VF to compromise or plan additional effort | Arjen Broeze, Shen Yu Kai | by 21.03.06
| Blocking | There is no direct connection between RIDB Beijing and CDB SISL, and no auto sync therefore, which impacts integration cycle. | active | Need agreement bwtween ITS BenQ and Siemens SBS. |  | Get a timeline to get this fixed or additional resources for doing manual sync | Arjen Broeze | by 21.03.06
SW-QM - B. M. Mortensen
| critical | ASP corporate instruction has to be agreed on by SW team | Will be reviewed by SW team
QM - T. Bartel | Blocking | All PPLs have declared M1 milestones with attached reasonable MEP checklists showing restrictions, planned corrective actions, timeline for implementation | not started |  |  |  |  | 2006-03-24
| Blocking | M1 document (performance description) | not started |  |  | All PPLs have to implement their requirements into M1 document |  | 2006-03-20
| Blocking | Design FMEAs performed and reviewed from QM | not started |  |  |  | MD/QM | 2006-03-24
| Blocking | Risk analysis for product safety filled out from relevant PPL and signed by PLT,PM & QM | not started |  |  | PPLs to fill out risk and safety analysis document and PLT/PM/QM sign | PLT/PM/QM | Due by March 22
| Blocking | M1 Q-Gate has been perfomed | not started |  |  |  |  | week 12
| Blocking | RMEA available for PS/DS | not started |  |  | Still needs to be done. | PLT/PM | 2006-03-24
| Blocking | Quality Planning is available | not started |  |  | Create Quality plan | T.Bartel | week 11
| Blocking | PSQA plans available from RF, EA, dHW, MD, SW | not started |  |  | Create PSQA plans | PPLs for RF, EA, dHW, MD | week 12
| Blocking | ASP concept is complete and agreed by ASP team |  |  |  | ASP concept was already received by Claus Nielsen and looks ok | dHW, ASP team, QM | week 12
AD - T. Lange
ST MO - F. Kokholm
ST SW - Yang Li
| Blocking | Finalized featurelist needed |  | Will be available before March 17
| critical | Finalized number of SW variants for VF |  | Currently looks like max 25, customization will be very limited |  |  | Sean,Monika | 2006-03-25
ST TA - Wei Xue Kai
Documents like peformance description needed
Primavera detailed planning
CC - H. Boll
VM - K. Falkenberger
| Critical | Hardware variant is not fixed (logo on battery cover) |  |  |  |  | Monika,VF
| Critical | Software variants not fixed |  |  |  |  | Monika,VF
GPM - Frans Billich
PE - M. Svendsen
BA - Jie gao
PL-T - Broeze, Song, Bonde
CPM - K. W. Koh
| Blocking | Contract with VF is not finalized |  |  |  |  | Koh Kheng Wah, Gary Vincent | ?
Planning - B. L. Thomsen
LCM1 - Jens Riedel
| critical | dispo variant should be in place |  |  |  | Should be available latest middle/end of april | Poul Erik | 2006.03.28
| blocking | does VF accept delivery out of SSMC? |  |  |  | Koh Kheng Wah will check | Koh Kheng Wah | 2006.03.20
LCM3 - K. Hilker | Critical | Commited result out of production and test workshop is available | ongoing | assembly - DONE board-level-test DONE phone-level-test - planned for CW11 | commited result for device-level-test expected by end of CW11 |  |  | 2006-03-20
| Critical | Detailed Primavera project plan up to M3/S4 is available, showing dedicated resources by name and/or on department level for external consultants | ongoing | not all resources in BMS are available in Primavera
| Critical | Packaging concept is fixed and ensures a manual and automatic packaging, a hint is placed in the performance list (PM) | ongoing | decision about package box needed
| Blocking | The assembly concept ensures a manual and automatic assembling of the Components; a hint is placed in the performance list (PM) | open | we agreed in the assembly WS that all trays have to fulfill the requirements described in GTTD61119 |  | hint has to be placed in the performance list | Lars Bonde | M1
| Blocking | 70% 3D Data in supplier safe available | open | at least 50% data must be available in supplier safe |  |  | Christian P. Nielsen | M1
| Blocking | Prototype volumes and dates are agreed | ongoing | mainly volume is missing |  | TPM has to provide prototype volumes | Poul Erik Rask | 2006-03-17
| Critical | Budget plan is agreed | ongoing | has to be done after volumes are fixed |  | TPM has to provide prototype volumes | Poul Erik Rask | 2006-03-17
| Blocking | Prototype shop sites and volume split is defined | ongoing | prototype shop is BMK until A1+ and BMS effective from B1 - volumes still missing |  | TPM has to provide prototype volumes | Poul Erik Rask | 2006-03-17
| Critical | Milestone planning is in accordance with prototype runs, PTR, FRT, ramp up plan and ramp up volume | ongoing | ramp up plan will be updated for M1 and PTR and FRT need to be checked, duration of prototype runs to be checked after volumes are fixed |  | TPM has to provide prototype volumes | Poul Erik Rask | 2006-03-17
| Critical | Make-or-Buy decision for VF logo on battery cover needed | open |  | because of the shape a misalignment of the logo on the battery cover is critical | TPM have to find out the expected variance of the battery cover. Needs to be finalized until S15 | Lars Bonde | 2006-03-17
| Critical | Decision if tape on earpiece is really needed |  |  |  | Tolerance calculation has to be done | Christian P. Nielsen | M1
|  | Evaluate feasibility to use a standard SW for production in Jerry | open | a stable version of the mobile SW will be used in production - phones are re-booted in CI with new SW versions SMT/board-test/device-test will use stable SW and are not influenced by SW changes |  | check expected SW for re-booting and decide if a standard SW for production makes sense | Allan Hansen, Katharina Hilker, Lars Bonde | M1
|  | Quality targets for production have to be added to performance description | open
SD QM - Thomas Limbach
TPM - Shuai Zhang