## Open issues
ID | ID or page |  | Comment | Status | Result | Ais
MRS_16 | 3 | SyncML remote synchronization | Reimplementation of SyncML remote synchronization necessary. No sync of SIM phonebook possible yet in SGL, would this be acceptable? AI for Clemens & Thomas by Feb 24:Clarify it is a two way "Sychonization" or just one way back up the contacts in SIM card. --What happens if the remote server has 1000 entries and the SIM card can only store 200 entries? If the entry is deleted in SIM or phone, shall the SycML be started otherwise the entries which is deleted shall be copied again to phone/SIM on next startup | open | Clemens will clarify. - Thomas: 2 way sync. - The server and SIM card have the same number of entries. - The deletion senario will be confirmed with VF. VF answer: Deletion activity has majority (just like additions and editing). | AI(CL): (March 10) clarify the deletion senario.
MRS_19 | 20 | Messages Settings | Secondary input language negotiable? Would require upgrade to T9 v7.x, integration layer effort, UI effort 6 man months effort. Thomas&Clemens will confirm with VF. Should negotiatable.. - Thomas(Feb. 27): discuss with Clemens and send the confirmation to SW | open | Thomas will clarify. | AI(Thomas): clarify which version of T9 shall be supported.
MRS_136 | TCD-USRX-BAS-008103 | All phonebook entries (i.e. names, email addresses, ..) shall be available as candidate words in the candidate list in Single-tap entry. | partially supported in SGL | open | communicate T9 version. It is in the editor feedback list.
MRS_137 | TCD-USRX-LIV-008406 | The Help system shall make use of multimedia animations to explain in a richer way (e.g. "Show Me"). | clarify with VF how it looks like. -VF: High prio: deliver detailed implementation plan for help, especially usage of animation. Timing: Sprint2 (struktur according to spec, incl. Reference text) -Clemens: we can put text in help system firstly. Animation will be followed by VF. | open | -Yes, accordimng to SISL we can commkunicate to VF in early April the exact details of the Animations we need, VF can order the and deliver them to us
MRS_144 | message | how to handle if user receives message with the normal MMS: picture&sound&text. |  | open | handle as SGL. The looklike refer to the UI Spec. -SYK: how to handle the sound when forwarding a normal MMS? Need clarify with Clemens VF: OK | AI(CL): March 10
MRS_154 | PIN2 | Do we support PIN2? | Prefer to hide this function since it's not described in UI flow. | open | Thomas will clarify with VF | AI(Thomas)
MRS_177 | volume screen | Clarify volume screen behaviour |  | open | Shen Yukai will clarify if there is some bitmap existing -no, ask clemens to check with VF. VF: Will be provided | AI(CL):March 10
MRS_180 | line 1, line 2 | Line 1, Line 2 supported ? |  | open | Thomas or Clemens will clarify | AI(Thomas)
MRS_184 | font | Can we use the same font for Arabic like in Aries, or is it necessary to use a font delivered by VF? | We have a special ordering of characters (not Unicode compliant) for some of the characters, so a Unicode compliant font would cause a lot of effort in software to change the bidirectional rendering engine. | open | clarify with Clemens VF: VF will not provide a "VF" Arabic font. Use BenQ arabic font (if needed) | Will be checked with VF AI(CL): March 10
MRS_185 | CB service | 1. CB needs to be turned on by user. Assumption : For Jerry, CB will be turned ON automatically based on SIM or Mapfile settings. No user action required. 2. CB has a concept of Topics/Channels/IDs. User has to manually select the Topics that he/she is interested in. Assumption : For Jerry, CB Topic/Channels will be selected(activated) automatically based on Mapfile settings. No user action required. 3. User has to manually select the CB language. Assumption : For Jerry, CB Language will be selected(activated) automatically based on Phone-Language settings. No user action required. 4. Display on Idle, when a message is received. Assumption : Jerry should display CB on Idle, similar to the other R65 phones. Layout needs to be decided. |  | open | will VF provide these values to us by Mobicon? - Thomas will confirm. | AI(Thomas)
MRS_186 | Font | 1) what is the "lable text"? 2) some of the "graphics provided by VF"are not included in icon package. | when to provide these graphics? | open | VF: VF will verify Styleguide | 1)AI(CL)(March 10) 2)AI(Thomas)
MRS_188 | SIM/Phone icons | 1. The flow spec says that there should be some indicator/icon to tell user where the contact is stored (SIM or Phone or both). This is to be shown only in detail view. The contact name & icons have to be shown on the same row. 2. The contact-list as well as the contact-details screens in the Style Guide do not show any such icons. In some cases we may have to use the both the icons. | Check with Clemens for our solution: 1) the icons shall be shown at the position as UI Spec says. update the styleguide. 2) in case the name is too long to be shown, shorten it. | open | VF Answer: No, we only want one icon (if contact is on both SIM/PHONE NO icon is shown// If contact is either on SIM or on PHONE respective ICON to be shown) | AI(CL):March 10, check with VF
MRS_193 | emergency call | How the UI would be if the screen saver/Lock Screen is active and the number 911 is pressed | Handle the emergency number input in the lock screen only, as in Aries, Confirmation with Clemens is still pending | open | VFAnswer: Yes, emergency call to be supported! BenQ to use their Spec | AI(CL): March 10
MRS_194 | USSD | Is USSD supported? | Yes, Layout is still pending with CBS issue | open | VF Answer; VF will verify internally if this is really required for JERRY | AI(CL): March 10
MRS_198 | icons | The VF icon package contains some GIF animations. These cannot be used directly as resources. We need a sequence of BMPs (instead of GIF) for defining the animation IDs. |  | open |  | AI for Thomas: need to let VF provide the discrete icons
MRS_199 | Voicemail | check with Clemens if the Voicemail notification in SGL is accepted by VF. |  | open |  | Thomas AI