## Change History
History of Change
Version | Date | Editor | Status | Description
1.0_001 | 2006-02-13 | Stefan Burkert | in work | First draft
1.0_002 | 2006-02-14 | Huang Qian | in work | Update the Critical Requirements sheet during the workshop.
1.0_003 | 2006-02-14 | Lovleen Chadha | in work | Merged issues from other RM list.
1.0_004 | 2006-02-14 | Shen Yu Kai | in work | added open issues from the result of WS for Appbase, AppPIM, UIOS
1.0_005 | 2006-02-15 | Clemens Lutsch | in work | add comments on unclear requirements in req. clarification meeting.
1.0_006 | 2006-02-15 | Shen Yu Kai | in work | merge comments of IDC open issue.
1.0_007 | 2006-02-16 | Shen Yu Kai | in work | merge the comments of message open issues and open issues from SMART simply TCD sheet.
1.0_008 | 2006-02-17 | Shen Yu Kai | in work | further clarify with Clemens
1.0_009 | 2006-02-17 | Huang Qian | in work | Teleconference with Thomas, update items according to the input with Thomas.
1.0_010 | 2006-02-22 | Shen Yu Kai | in work | as per discussion with Kashyap.Gagan on Idle issues, there are several open issues been clarified, merge them to unclear requirement.
1.0_011 | 2006-02-24 | Shen Yu Kai | in work | reviewed by product architect, updated the open issues. Reopen some clarified issues. Updated with Clemens.
1.0_012 | 2006-02-27 | Shen Yu Kai | in work | clarify some issues with Thomas.
1.0_013 | 2006-03-01 | Shen Yu Kai | in work | export from DOORs.
1.0_013 | 2006-03-03 | Shen Yu Kai | in work | update after clarification with Clemens.
1.0_014 | 2006-03-08 | Shen Yu Kai | in work | update the open questions, export to be clarified.

## Clarification Table
ID | ID or page |  | Status | Comment | Result | Ais
MRS_1 | TCD-EXEN-SIM-001084 | The terminal shall handle the sending process of messages (MMS, e-mail, Instant messages, SMS, USSD) in the background without negatively effecting the applications used after the sending of the messages has been initiated by the customer. | closed | Propose to drop, high effort and risk. | Dropped, confirmed by VF
MRS_2 | TCD-MESG-GEN-001473 | If a message can not be sent, (e.g. due to an out of coverage problem) than the messaging client shall offer the possibility to retry to the customer. The retry time must be configurable for the customer. | closed | A lot of scenarios need to be considered. | Clemens will clarify. -VF: yes, user can decide to retry or to cancel (msg in drafts) | AI for Clemens by Feb 24: Check with VF, whether existing SGL solution is acceptable (the "Retry" softkey after sending failed is sufficient or not.)
MRS_3 | TCD-MESG-GEN-001653 | The actual receiving of a MMS shall take place in the background, i.e. customers shall be able to perform other tasks (e.g. browsing folders) with the device in parallel. | closed | Propose to drop, high effort and risk. | Dropped, confirmed by VF
MRS_4 | TCD-MESG-GEN-002030 | The terminal shall enable users to select image in a message to display as original size with horizontal/vertical scrolling bar. | closed | Propose to drop. Not support in current MMS editor. | Dropped, general messaging requirements not applied for VF Simply. Clemens will verify with VF. | AI for Clemens by Feb 24: Verify with VF. - dropped
MRS_5 | TCD-S_PB-C&S-002428 | Standard vCard version that should be supported by the device is vCard2.1. vCard3.0 shall be only import supported. Conform following about character encoding and Transfer-encoding. in the case of conversion to vCard format: - When receiving (importing) vCard, the terminal shall support the following CHARSET Parameters: UTF-8, US-ASCII, ISO-8859-1, Shift_JIS. In addition, when CHARSET property is not present in the vCard, The vCard shall be assumed to be encoded using ISO-8859-1. For Japan, it shall be regarded as Shift_JIS. - When sending (exporting) vCard, When the character string other than 'IA5-ascii' is set to Property Value, CHARSET Parameter which shows character encoding must be specified. At this time, CHARSET Parameter should specify UTF-8. For Japan, CHARSET Parameter should specify Shift_JIS. - When Property Value becomes two or more lines, ENCODING Parameter which shows Transfer-encoding must be specified. At this time, ENCODING Parameter should specify QUOTED-PRINTABLE. The example of Format which specifies ENCODING Parameter is shown following: <example>:[Property name];ENCODING=QUOTED-PRINTABLE:[Property Value] | closed | Propose to drop vCard v3.0 requirement. To be checked which character sets are supported for vCards in SGL platform. No use case in VF Simply. Can we drop it? Thomas(Feb 17): Should be dropped. vCard2.1 is ok. | vCard 2.1 is Ok | Thomas will confirm with VF. - clarify which format will be used in SyncML by SYK - yes, SyncML use vCard format.
MRS_6 | TCD-S_PB-C&S-002431 | The device must support distoribtion list within the address book for managing contacts. | closed | Distribution list only supported in SG2 platform. Propose to drop this requirement. | Dropped, confirmed by VF
MRS_7 | TCD-USRX-BAS-008053 | In case an event (e.g. an incoming call, battery low) interrupts the current use case the user shall be taken back to the last screen with the same state as before the interruption. Related Principle: Give the user control Example Use Cases to check: - Calls - I receive a video call from someone not stored in my Contacts - Calls - I receive a video call from someone stored in my Contacts - Calls - I receive a voice call from someone stored in my Contacts - Calls - I receive a voice call from someone not stored in my Contacts | closed | Not supported in SGL and SG2 platforms, very high effort and risk. Architectural design limitation.Around 10 Man months effort for redesign the architecture. Option in case this cannot be dropped: Implement this for few special cases, e.g. message editors. | Clemens will clarify. | AI for Clemens by Feb 15: Define the screens/applications which need to be resumed. -Not possible for all situations, Messaging & Contacts supported. Screensaver does not return to idle -VF: High prio: Make sure that key lock behaves just like screensaver (not back to idle: preserves states). BenQ: clarify that events (e.g. reminders) don't affect current task (closing resumes task).
MRS_8 | TCD-USRX-BAS-008101 | The candidate word list (while in single-tap entry) shall be organised dynamically based on the user's frequency of use for each word. Related Principle: Encourage usage Example Use Cases to check: - Messaging/MMS - I add text to an MMS - Messaging/Postcard - I add text to a postcard | closed | Propose to drop. 2 man months efforts. Nice to drop. | Clemens will clarify. | AI for Clemens by Feb 24: Check with VF - we have to do it
MRS_9 | TCD-USRX-BAS-008107 | The symbol list shall contain in addition to the special characters the major emoticons ( i.e. :) , :( , :¦ , :D, ;). Related Principle: Encourage usage Example Use Cases to check: - Messaging/MMS - I add text to an MMS - Messaging/Postcard - I add text to a postcard | closed | No support for multiple characters in symbol table. Propose to drop. | Clemens will clarify. | AI for Clemens by Feb 24: Check with VF
MRS_10 | TCD-USRX-SIM-008460 | Moving from one terminal area to another (e.g. from contacts to the log) shall be emphasised by animated screen transitions. | closed | Transitions seem to be challenging work, especially partial-screen transitions. | It's a must feature. Follow the style guide.
MRS_11 | 29 | Menu item horizontal text scrolling | closed | Is there a situation in which a long text scrolls horizontally with an icon in front? Can we keep our scrolling style (end of text and beginning of text are not visible at the same time)? Missing knowledge about this part of SW, it's in low layer SW, high risk for changing it. | Clemens will clarify. | AI for Clemens by Feb 24: Clarify this with VF. our marquee is ok.
MRS_12 | 31 | Text Editor | closed | Main text editor differences to SGL platform: - T9 word proposals in list - Different keys for T9 on/off and small/cap. letters - Different multi-tap key mappings |  | AI for Clemens: Show text editor in C55 to VF for assessment. - As Aries has been shown for VF, they have feedback on it. hope for the text editor's concept.
MRS_13 |  | Messaging | closed | In SGL75 there are separate inboxes for SMS and MMS, also for Sent folder. Possible solutions for Sent folder: - Merge the two folders (4 MM) - Discuss with Vodafone? | Clemens will clarify. | AI for Clemens by Feb 24: Check whether VF can accept separate sent box for MMS and SMS. -Unified Inbox and sebt box can be implemented in Jerry
MRS_14 |  | MMS | closed | Will MMS 1.1 be sufficient (1.2 requested)? Effort for update MMS client to version v1.2 is about 20 man months. | Thomas will contact VF. | Thomas will contact VF and update TPD. - we can support 1.2 in SGL
MRS_15 | 2 | Startup | closed | Vodafone: Can we exchange the order of copy SIM to AB and date/time setting? | Follow the VF specification.
MRS_16 | 3 | SyncML remote synchronization | closed | Reimplementation of SyncML remote synchronization necessary. No sync of SIM phonebook possible yet in SGL, would this be acceptable? AI for Clemens & Thomas by Feb 24:Clarify it is a two way "Sychonization" or just one way back up the contacts in SIM card. --What happens if the remote server has 1000 entries and the SIM card can only store 200 entries? If the entry is deleted in SIM or phone, shall the SycML be started otherwise the entries which is deleted shall be copied again to phone/SIM on next startup | Clemens will clarify. - Thomas: 2 way sync. - The server and SIM card have the same number of entries. - The deletion senario will be confirmed with VF. VF answer: Deletion activity has majority (just like additions and editing). | AI(CL): (March 10) clarify the deletion senario.
MRS_17 | 9 | Messaging | closed | Discuss MMS editor layout with Vodafone - can we basically keep SGL layout with stripped-down features? Missing knowledge, high risk for changing. | Refer to SGL solution.
MRS_18 | 15 | Change PIN | closed | New dialog "Change PIN": Can we keep our platform solution with several dialogs for changing codes rather than a combined one?). Missing knowledge, old codes, high risk for changes. | Follow the VF specification.
MRS_19 | 20 | Messages Settings | open | Secondary input language negotiable? Would require upgrade to T9 v7.x, integration layer effort, UI effort 6 man months effort. Thomas&Clemens will confirm with VF. Should negotiatable.. - Thomas(Feb. 27): discuss with Clemens and send the confirmation to SW | Thomas will clarify. | AI(Thomas): clarify which version of T9 shall be supported.
MRS_20 | 21 | Call Forwarding | closed | Different divert control flow - should be negotiated with Vodafone to keep SGL solution due to risks | Follow the VF specification.
MRS_21 |  | USB 1.1 | closed | Clarify whether SGL platform support USB. | Thomas will clarify. -not feasible, no show stopper for VF. We close it. | AI for Clemens: Inform Thomas to check with VF Yang Yong Qiang (Feb 24): Talk with Smartcom and ally with Allan. Clarify the feasibility supporting Smartcom SW.
MRS_22 | TCD-MESG_SIM-990002 | At power on, the device shall check EF_MSISDN on the SIM for the presence of an MSISDN. If the field is blank then the device shall prompt the user to "Enter own number"; details of the UI interaction shall be in accordance with the User Experience TCD. | closed | To be clarified: When to display the own number, use cases for entering own number. | spec needed for number entry, display on home (check VF Spec)
MRS_23 | TCD-MESG-BUS-003721 | The terminal shall support a unified MMS / SMS composer. | closed | Not required according to TPD document and UI spec. CONFLICT | confirm with VF, this req. is not available.
MRS_24 | TCD-MESG-GEN-001473 | If a message can not be sent, (e.g. due to an out of coverage problem) than the messaging client shall offer the possibility to retry to the customer. The retry time must be configurable for the customer. | closed | Missing specification. | Discussed in Critical req. Section, refer to MRS_2
MRS_25 | TCD-MESG-GEN-001479 | The device shall be able to store the most used words not present originally in the device and propose them to the customer. | closed | Unclear requirement. | Discussed in Critical req. Section. Dropped! Not part of new TCD.
MRS_26 | TCD-MESG-GEN-001576 | The terminal shall enable users to store at least 1000 messages in the Inbox. | closed | 1000 messages in one list? Unusable, if it is in one list. If folder structure is necessary, not feasible in given timeline. | no additional folders, not a simply scenario. Dropped! Not part of new TCD.
MRS_27 | TCD-MESG-GEN-001635 | The terminal shall display the subject and sender information of a received messages in any Messaging folders. | closed | Feasible, but has to be checked. 2 or 3 Preview lines in menu? | refer to VF Spec solution
MRS_28 | TCD-MESG-GEN-003477 | The terminal shall be possible to pre-configure per OpCo if SMS is sent via CS or PS channel. - The values of this setting are CS/PS. - The default value of this setting shall be customizable per OpCo. - The visibility of this setting shall also be customizable per OpCo. This setting shall be applied with SMS. | closed | How to customize? Via Mobicon? No user setting possible? | Via Mobicon. Normal way in SGL products.
MRS_29 | TCD-MESG-GEN-005590 | The terminal may enable uses to move received messages from one folder to another folder. | closed | Requirement unclear: Moving from Sent to Inbox etc. or to any folder? Can the user create folders? | not needed, refer to VF Spec
MRS_30 | Message 03 | Usage of templates and MMS. | closed | exact rules for usage / templates & drafts MMS or SMS? | Clemens check with VF - unsent message will be saved in template
MRS_31 | TCD-MESG-SMS-001492 | The terminal shall enable users to call the sender of a message in all folders by pressing the green call key. If sender address is e-mail address, the default MSISDN shall automatically be retrieved if the sender is available in the phone book. | closed | Looks like the contact information does not include email addresses. To be checked with VF. | no email needed
MRS_32 | TCD-S_PB-SEC-002433 | The terminal shall have a function to lock access to the phonebook with a password. A setting to activate/deactivate this function must be available The password shall be required to change the setting. ? The default is OFF (No restriction). ? When this function is ON, a message shall be displayed on the screen that indicates the user access to the phonebook is restricted. | closed | Do we need to protect the SIM phonebook? Assumption: Not possible, SIM can be put into another phone to read it. Only possible solution: Use FDN only. | not a simply req. Thomas to confirm
MRS_33 | TCD-S_PB-SEC-002434 | All application including Smart Clients accessing personal data such as the phonebook must ensure the integrity of data and meet all security and data protection requirements | closed | To be clarified. | low brainer, data integrity is alway important ;)
MRS_34 | TCD-S_PB-SEC-002435 | The operation of any Phonebook and any other application that may have access to the Phonebook must ensure that all personal data is protected both in the local phone storage and during any data transfer either over the air or via any local connection. | closed | To be clarified. | low brainer, data integrity is alway important ;)
MRS_35 | TCD-S_PB-USE-002342 | Due to limited calling line presentation capability the following rules will be applied: 1) In case of incoming call the audio ringtone and the eventual assigned picture will be displayed. 2) In case a video ringtone is assigned only the video ringtone is played. | closed | Incoming call and ringtone presentation (To VF: Calling picture necessary? Implemented.) | no assigned pictures
MRS_36 | TCD-USRX-BAS-008055 | The terminal shall display the following status information wherever and whenever appropriate: 1. Signal strength and network type (3G, 2.5G, GSM, HSDPA) 2. Battery level and charging 3. Roaming 4. Messaging status (eg, if new messages are available) 5. Current profile (eg, silent) 6. Active connections (eg, sync connections, browser connection, Bluetooth) Related Principle: Make the user aware Example Use Cases to check: - Calls - I make a voice call to someone by entering a number - Connectivity - I switch to Bluetooth headset while in a call - Device Management - I re-charge my phone - Download - I Download and store a song to the music folder and start listening to it directly (FTMD) - Links and Service Access - I browse the Vodafone live!Portal - Messaging/Email - I receive a notification for new Email(s) on the home screen - Profiles - I activate another profile - Misc - I use my phone in a foreign country | closed | A little fuzzy. Assumption: Only displayed in idle screen and keylock screen. | Stick to VF Spec & Styleguide
MRS_37 | TCD-USRX-BAS-008058 | If an operation fails, retry and cancel options shall be offered to the user when there are chances that retrying will lead to task completion (e.g. when logging into a service). Related Principle: Prevent errors and allow for recovery Example Use Cases to check: - Calls - I try to make a video call but I am out of 3G coverage - Connectivity - I switch to Bluetooth headset while in a call - Contacts - I backup my contacts to the Network - Download - I download a ring tone to the ring tone folder and listen to it directly - Links and Service Access - I connect to the Vodafone live! start page from the home screen - live! cast - I want to see the full content / article related to a live!cast message - Messaging/Email - I download an attachment separately from an email | closed | Availability of Retry / Cancel Option after Operation Failure (has to be considered for all applications). Partly implemented, widespread requirement: To RM team: Specify exactly. | Discussed in Critical req. Section
MRS_38 | TCD-USRX-BAS-008069 | Where appropriate, lists shall be ordered chronologically with the most recent item at the top (e.g. in the call log, inbox or in a picture folder). Related Principle: Ensure learnability Example Use Cases to check: - live! cast - I read the live! cast news ticker on my home screen - live! cast - I flip through the ten latest news - Messaging/General - I browse to the next message from the message I view - Messaging/General - I search for a message - My Files - I browse my content | closed | Sorting in a List (Widespread requirement, affecteds serveral componentrs, not only IDC, but also others, like, appmsg, apmm, browser. Partly implemented already.). To RM team: Specify exactly where. | * Inbox * call log -> refer to VF Spec
MRS_39 | TCD-USRX-BAS-008096 | Indication of the Number of Available Characters in Text Entry Fields | closed | Do we have to display the number of remaining characters in every text editor or only in messaging? | according to VF Spec, messaging scenario only
MRS_40 | TCD-USRX-BAS-008134 | When viewing a list of contacts the user shall be able to see at least the contact name and default number without having to open a detailed view. Related Principle: Facilitate communication Example Use Cases to check: - Contacts - I view a contact - Contacts - I browse my contact list - | closed | Conflict with requirement TCD-USRX-SIM-008484 | there is only one number, therefore this is the default number ;))) check VF spec for more info
MRS_41 | TCD-USRX-BAS-008137 | The user shall have quick access to the most recently used contacts in all relevant services. Related Principle: Encourage usage; Facilitate communication Example Use Cases to check: - Messaging/Email - I send an email from the contact list - Messaging/MMS - I send an MMS from the contact list - Messaging/MMS - I send a SMS from the contact list | closed | Is this about "Top 3 Contacts"? | to be checked with VF - it is the most frequently used.
MRS_42 | TCD-USRX-BAS-008143 | When viewing a message it shall be possible to navigate to the next or previous message (in the same folder) without having to go back to the list view. Related Principle: Allow for efficient interaction for frequent use cases Example Use Cases to check: - Messaging/Email - I read an email I downloaded - Messaging/General - I view a message from the inbox | closed | For SMS, it is possible to go to the next message only. For MMS not available. UI flow (softkeys?) to be clarified. | to be checked with VF - VF: req. dropped.
MRS_43 | TCD-USRX-SIM-008463 | Privacy settings shall be offered so that the user can : - hide or lock their Log History - hide their own number on the Home screen . - hide their own number when in a call. Related Principle: Give the user control Example Use Cases to check: - Not Applicable | closed | Is log history the same as unified inbox? | to be checked with VF - Log histoy no longer mentioned in spec: VF: Log history dropped, SPEC overrules req.
MRS_44 | TCD-USRX-SIM-008488 | The user shall be able to see in the contact list when they have last contacted a person (e.g. upon selection 'contacted 1 week ago' is displayed) Related Principle: Facilitate communication Example Use Cases to check: - Contacts - I view a contact - Contacts - I search for a contact - Contacts - I browse my contact list | closed | Does this mean all kinds of communication (MO&MT call, sent and received messages)? Can we get this information from the log? Or does it have to be stored in the contact? Reason: Information changes if messages or call logs are deleted from log. | outgoing communication, counts the actual difference of date of communication and actual device date
MRS_45 | TCD-USRX-SIM-008490 | In case the SIM card is full, a 'Delete Wizard' shall suggest less frequently used contacts for deletion. From this list of contacts the user shall be able to select and delete contacts one by one. Related Principle: Give the user control Example Use Cases to check: - Contacts - I create a contact from a missed/received/dialled call - Contacts - I save contact from the call log - Contacts - I create a contact by entering someone`s number from the home screen | closed | Is this list sorted according to frequency of use? How many contacts should be displayed in the delete wizard? | Yes, frequency. Propose: show 5 least frequent used contacts.
MRS_46 | TCD-UTIL-VRC-003088 | The voice recorder shall support the capturing audio codecs specified in the Content Types TCD. | closed | Missing "Content Types TCD". Expectation: only AMR-NB | AMR-NB
MRS_47 | TCD-V&VT-VOC-004934 | While the setting of Call Barring is activated, UE shall display the message that user can understand 'during call barring,' when the call(AMR, UDI, SMS) origination is rejected. | closed | Unclear | Discussed in Critical req. Section - no more questions about it. SW is investigating for the call barring when in abroad.
MRS_48 | 20 | Menu icons | closed | Do we need different icon bitmaps for highlighted and non-highlighted menu items? Or is just the color different? To be checked also for idle/locked screen icons. | Check VF Styleguide
MRS_49 | 23 | Screen transitions | closed | Does a key press finish the transition? Or does the user have to wait? Or is the key press buffered, being consumed after the transition finished? | no, refer to Sagem implementation
MRS_50 | 25 | List item opening transition | closed | Screen 5b: What use cases? | Styleguide p26
MRS_51 | 29 | Menu item horizontal text scrolling | closed | Is there a situation in which a long text scrolls horizontally with an icon in front? Can we keep our scrolling style (end of text and beginning of text are not visible at the same time)? | Discussed in Critical req. Section
MRS_52 |  | GPRS | closed | Do we need GPRS settings in the UI? | no
MRS_53 |  | On-hook key | closed | End key functionality (back to idle, or back one level?). Assumption: Due to "Home" hardkey, back one level. | back one level, home key = back to idle
MRS_54 |  | MMS | closed | What MMS capabilities (also Video…)? User agent profile content to be clarified. | no video, profile MNO OTAP
MRS_55 |  | Contacts Synchronization | closed | Synchronization with PC - Will MPM be used? | Discussed in Critical req. Section - no PC Synchronization.no MPM. No smartcom
MRS_56 |  | Dialog Timeout | closed | Do we need a dialog timout (for returning to Idle screen)? Should it be different for key lock state? | no timeouts described in VF (no back to idle timeout)
MRS_57 |  | Sleep Mode | closed | Do we need to go to sleep mode from every status? Do we need to return there? | yes (resume task issue)
MRS_58 |  | Contacts | closed | Which fields are contained in a contact entry? How many characters/digits are supported for each field? | refer to VF Spec (name, number)
MRS_59 |  | Contacts | closed | Protected SIM phonebook entries to be synchronized? Assumption: No. | no
MRS_60 |  | Contacts | closed | If new SIM contains more entries than can be added to contacts, what should happen? | Discussed in Critical req. Section
MRS_61 | 2 | Startup | closed | Vodafone: Can we exchange the order of copy SIM to AB and date/time setting? | Discussed in Critical req. Section
MRS_62 | 2 | Startup | closed | To be specified in which use cases the copy-to-contacts prompt is displayed (first time with new SIM or other use cases?). | new sim
MRS_63 | 3 | SyncML remote synchronization | closed | Reimplement SyncML remote synchronization (no sync of SIM phonebook possible yet in SGL), UI flow to be reimplemented | Discussed in Critical req. Section
MRS_64 | 4 | Welcome Tour | closed | What's in the Welcome Tour? | additional info from VF needed - take Sagem as reference
MRS_65 | 9 | Messaging | closed | Do we need a template folder (MMS templates?). What is the definition of "Template"? Is it just the same as a draft message or only text? | no special templates folder asode from drafts/messages. Usage of mms "teplates" to be clarified with VF
MRS_66 | 9 | Messaging | closed | Picture Message: Is it possible to store pictures in filesystem? | not needed
MRS_67 | 9 | Messaging | closed | Message options: "Insert Template": Can we insert a template of any other than the current message type? | to be checked with VF -- No "Insert template" when forwarding MMS.
MRS_68 | 9 | Messaging | closed | Dialog "Send x messages?" refers to concatenated SMS? | to be checked with VF - yes.
MRS_69 | 10 | Message Templates | closed | What is the sorting criterion for templates? | chronologically
MRS_70 | 13 | Delete wizard | closed | From where is the delete wizard started? Automatically when running out of memory? Need use cases for contacts, messages, calls. | Contact delet wizard (nothing else required) Case a) if the user has entered the "last possible new entry" wizard starts Case b) SIM is full, user wants to enter a new contact
MRS_71 | 15 | Change PIN | closed | New dialog "Change PIN": Can we keep our platform solution with several dialogs for changing codes rather than a combined one?) | refer to VF Spec, discussed in critical req. Section
MRS_72 | 16 | Settings | closed | What's the functionality of "Power Saving"? | to be checked with VF -acccording to our Meeting with VF, the Power Save setting (ON/OFF) is used to “enable” all power saving settings (reduced backlight time, sooner hit of Screensaver, low power screen…) If the setting is OFF all this stuff will not be enabled or use the standard setting (eg. Backlight 15 secs instead 10 secs with Power Save ON)
MRS_73 | 16 | Settings | closed | What's "Area Info"? | Cell id. Do we support Cell broadcast or some other flash SMS? -VF: yes. Support USSD, CB, flash SMS.
MRS_74 | 16 | Settings | closed | Vodafone Services: SAT or dedicated menus? | Ask VF on details of Vodafone Services -SAT
MRS_75 | 18 | Contacts Settings | closed | What is the definition of "Top 3 Contacts"? How is the priority determined? | check issue above
MRS_76 | 22 | Hover functionality | closed | Unclear functionality - Is this about preview lines within the list or like a popup window?
MRS_77 | 18 | Settings | closed | What is "Reminder Tone"? Are these settings per contact or global? | global remindertone
MRS_78 | 2 | Contacts | closed | No "Smart Phonebook" in SGL platform -> Huge implementation effort for unified contact list. Negotiable with VF? -> RM | Discussed in Critical req. Section
MRS_79 | 8 | Main Menu | closed | How to get to this menu? With Log hardkey? | menu hard key
MRS_80 | 15 | Settings | closed | Why prompt to enter own number? Not necessary for Hide ID functionality.
MRS_81 | TCD-CONT-FLH-003377 | When a file is saved, the following rules must be applied: 1) Apply unique names to the file names in the same folder 2) Do not use the following half-width characters (except '.' in an extension) -005C \\ -002F / -003A : -003B ; -002A * -003F ? -0022 ' -003C < -003E > -007C ¦ -002E . 3) When saving a file to the terminal, delete all the above-mentioned do-not-use characters. If file name becomes empty, apply suitable characters/naming. 4) When saving a file from a browser, the extension should be the file format according to Content-Type correspondance table (TCD_CONT_REF_000897_Content_Type_Extensions.xls) attached regardless of the extension (e.g. '.cgi', '.php', etc) of the URI specified at the time of a request. 5) When a file format is unknown, apply the extension contained in Request URI. 6) When an extension is contained in Request URI, attach the extension to a file name and save it. 7) When an extension is not contained in Request URI, save a file name without the extension. | closed | What use cases? | we don't save files
MRS_82 | TCD-DISP-MAI-001047 | The device shall support the following display modes for the main display: - Mode 1: Idle screen with background light, - Mode 2: Idle screen without background light, - Mode 3: Sleep mode for saving battery time. Changing between the different display modes shall be handled on the following conditions: - Mode 1 into Mode 2: if there is for a specified duration ('backlight lighting time', default 20 sec.) no user interaction at all or if the user lock the keypad, - Mode 2 into Mode 3: if there is for a specified duration ('display time - backlight lighting time', default: 30 sec) no user interaction at all, - Mode 3 into Mode 1: if the user press any key - Mode 2 into Mode 1: if the user press any key The sleep mode (Mode 3) shall still display the current time and date without using the background light. This behaviour is valid for Candy bar devices and for Clamshell devices in an open state. The user shall be able to set the 'backlight lighting time': - by second (default: 20 sec. / min: 0 sec. / max: 60 sec.) - always ON/OFF. The user shall be able to set 'display time': - by second, - always ON. Note: An optimal implementation of power save modes would not deactivate backlight in the following application context: - Playing a video. - Streaming a video. - Viewing an MMS Presentation - Other cases (TBC). | closed | Main Display Power Save Modes (Light timeout has to be made configurable. To VF: What does Sleep Mode mean exactly?) | power save mode issue addressed above
MRS_83 | TCD-EXEN-OPN-001079 | An application within the untrusted domain shall always provide a one-shot prompt to gain user permission before accessing multimedia recording features. An application within the trusted domain shall always provide a session prompt to gain user permission before starting a session which will access multimedia recording features. The user may change this to a blanket prompt. An application within the operator and high trust domain is not required to provide a prompt to gain user permission before accessing multimedia recording features. Multimedia recording features Cameras, Microphones etc | closed | DRM related? If not, which use cases? | not simply issue, to be dropped
MRS_84 | TCD-MESG-BUS-003722 | The terminal shall place both incoming SMS and MMS in a common Inbox. | closed | X75 support. Show missed calls in this inbox? | we have one inbox for SMS, MMS
MRS_85 | TCD-MESG-GEN-001486 | The actual sending of a message shall take place in the background. Customers shall be able to perform other tasks with the device in parallel to the sending process. During the sending process a blinking icon on the idle screen shall indicate that a message is in the process of being sent. | closed | Not supported in SGL, very hard to do. Should be cancelled (or reopen platform discussion?). Effort estimation for SGL75 CR available? | VF confirmed, bgrd sending can be dropped
MRS_86 | TCD-USRX-BAS-008056 | The low-power screen state shall display the current time. Related Principle: Make the user aware Example Use Cases to check: - Not Applicable | closed | VF requirement to be clarified. | that is the screensaver, refer to styleguide
MRS_87 | TCD-USRX-BAS-008115 | All sounds shall be played through the external speakers (if available). Exceptions: In call sounds, call connection sounds, and all sounds played in a PPT call shall be played through the internal speaker (earpiece) unless the terminal is switched to external speaker mode (hands free mode). Related Principle: Encourage usage Example Use Cases to check: - Calls - I make a voice call to someone from Contacts - Messaging/General - I view an MMS containing a sound - My Files - I listen to a song or ring tone - Push to Talk - I start a PTT session from the phone contact list - Push to Talk - I take part in a PTT session | closed | Two speakers? | Sound will have to be player "loud", not in "earphone" sytle ;)
MRS_88 | TCD-USRX-SIM-008454 | The terminal shall have the following areas: - Home screen and Settings - Contacts space - Log space - in Call (no hard key access required) Related Principle: Ensure learnability Example Use Cases to check: - Not Applicable | closed | Main Terminal Areas (Unclear requirements. If split view according to Live!Cast (LV) shall be implemented, effort is huge. -> LV must be migrated from X75 -> Functionality must be extended. -> Parts of Orange Homescreen must be migrated from X75 and adapted according to VF) Probably more than 10 MM | To be closed ?
MRS_89 | TCD-USRX-SIM-008458 | The terminal shall preserve the current state and continue active processes (e.g. downloading) when locking or closing the terminal. Unlocking or opening the terminal shall resume the previous state. Exceptions: The terminal shall end the current application when: - in browsing sessions - in calls without headset connection The terminal shall pause the current application while: - playing back video including streaming (eg, Mobile TV) - playing games Related Principle: Prevent errors and allow for recovery Example Use Cases to check: - Connectivity - I switch to Bluetooth headset while in a call - Links and Service Access - I browse the Vodafone live! Portal - My Files - I view a picture or video - My Files - I listen to a song or ring tone - Non Native Applications - I browse the internet - Non Native Applications - I play a game with other local player(s) - Non Native Applications - I play a game with other distant player(s) | closed | Preservation of State when Locking or Closing the Terminal (Requires nearly full-featured Multitasking which has been introduced partly in X75.). Indication of keylock necessary wherever you are? Information dialog how to release keylock? Emergency call dialog necessary? | Discussed in Critical req. Section. MRS_7
MRS_90 | TCD-USRX-SIM-008460 | Moving from one terminal area to another (e.g. from contacts to the log) shall be emphasised by animated screen transitions. Related Principle: Express the Vodafone brand Example Use Cases to check: - Calls - I make a voice call to someone from Contacts - Calls - I make a voice call to the sender of a message - Calls - I make a voice call to call back someone who has called me before | closed | Check if VF has concrete concept. Feasibility study to be done. | Styleguide
MRS_91 | TCD-USRX-SIM-008465 | The layout and design of the home screen shall be compliant with the style guide for Vodafone Simply. Related Principle: Display and communicate information Example Use Cases to check: - Not Applicable | closed | Home Screen Layout (Requires the implementation of a new VF Homescreen (according to Orange Homescreen in X75)). Need styleguide from VF. Very high effort. | Apply VF Styleguide
MRS_93 | TCD-S_PB-C&S-002431 | The device must support distribution list within the address book for managing contacts. | closed | Distribution list only supported in SG2 platform. Propose to drop this requirement. | Dropped, confirmed by VF
MRS_94 | TCD-S_PB-C&S-002428 | Standard vCard version that should be supported by the device is vCard2.1. vCard3.0 shall be only import supported. Conform following about character encoding and Transfer-encoding. in the case of conversion to vCard format: - When receiving (importing) vCard, the terminal shall support the following CHARSET Parameters: UTF-8, US-ASCII, ISO-8859-1, Shift_JIS. In addition, when CHARSET property is not present in the vCard, The vCard shall be assumed to be encoded using ISO-8859-1. For Japan, it shall be regarded as Shift_JIS. - When sending (exporting) vCard, When the character string other than 'IA5-ascii' is set to Property Value, CHARSET Parameter which shows character encoding must be specified. At this time, CHARSET Parameter should specify UTF-8. For Japan, CHARSET Parameter should specify Shift_JIS. - When Property Value becomes two or more lines, ENCODING Parameter which shows Transfer-encoding must be specified. At this time, ENCODING Parameter should specify QUOTED-PRINTABLE. The example of Format which specifies ENCODING Parameter is shown following: <example>:[Property name];ENCODING=QUOTED-PRINTABLE:[Property Value] | closed | Propose to drop vCard v3.0 requirement. To be checked which character sets are supported for vCards in SGL platform. | Discussed in Critical req. Section
MRS_95 | TCD-USRX-BAS-008101 | The candidate word list (while in single-tap entry) shall be organised dynamically based on the user's frequency of use for each word. Related Principle: Encourage usage Example Use Cases to check: - Messaging/MMS - I add text to an MMS - Messaging/Postcard - I add text to a postcard | closed | Propose to drop. | To be closed ? - Feasible, with medium effort.
MRS_96 | TCD-USRX-BAS-008107 | The symbol list shall contain in addition to the special characters the major emoticons ( i.e. :) , :( , :¦ , :D, ;). Related Principle: Encourage usage Example Use Cases to check: - Messaging/MMS - I add text to an MMS - Messaging/Postcard - I add text to a postcard | closed | Propose to drop. | discussed in Critical req. Section (verbal: VF does not req. Emoticons for Simply)
MRS_97 | TCD-MESG-GEN-002030 | The terminal shall enable users to select image in a message to display as original size with horizontal/vertical scrolling bar. | closed | MMS requirement, propose to drop | discussed in Critical req. Section (verbal: VF does not req. this interaction for Simply)
MRS_98 | 15 | Clarify Ringtone setting' MMI spec, specially on RSK "Edit" | closed |  | Clemens check with VF - take it out
MRS_99 |  | Do we need phone code handling? | closed | Currently in SGL, there is procedure to handle phonecode together with PIN. | no VF req.
MRS_100 | 15 | In "display own number", what is "number known" | closed | the flow of display my number need to be clarified.
MRS_101 | 5 | if the contacts in "copy contacts to phone/SIM" mean all the entries in phone/SIM | closed |  | all entries
MRS_102 |  | the limitation of the number of Contact and Reminder's linkages | closed | if there is the limitation of numbers for reminder | we provide limitations
MRS_103 | 6 | clarify reminder's recurrence rule | closed |  | we provide "rules"
MRS_104 | 5 | Duplicate check, and only show the same contact once | closed | in SGL, if there is duplicated entry in contact book, the contact will be shown duplicatedly.to implement this req., the effort is high. duplicate handling like VF Spec - it is really tough work to handle the duplicate check. further more, the TCD has not mentioned this requirement. propose to drop. need to be clarify with Clemens. | - check again with Architect. solution is : Check when create a new contact entry. If it is a duplicate one, prompt user not to save it. Check when copy SIM/phone to phone/SIM. If there is duplicate entry, only list once.
MRS_105 | TCD-USRX-BAS-008091 | The user shall be able to quickly cycle between all available text entry modes with a single click or key press. Language selection and Single-tab on/off shall be separate from changing the text entry modes. | closed |  | apply our solution and the VF Spec, VF will provide feedback of SGL text entry assessment
MRS_106 | TCD-USRX-BAS-008096 | In multi-line text fields and if the maximal number of characters is limited it shall be clear to the user how many characters can yet be entered (i.e. the text field restricted to 1024 characters, the user has already entered 24 characters: '1000' may be displayed). | closed | Is it necessary to show the numbers wherever there is editor? | only messaging
MRS_107 | TCD-USRX-BAS-008105 | The symbols of the language independent keypad assignment of special characters specified in the ETSI Standard (ETSI ES 202 130) shall be used for the symbol list. The order of the characters shall follow the specified order. | closed | Can we use the symbol list in currently SGL? | discuss with VF -refer to Aries feedback . The symbol guideline has not been provided yet. 0224
MRS_108 |  | Remove the line in headline | closed | can we keep the line at the bottom of headline? Removing it will lead high effort. | stick to VF Styleguide
MRS_109 | 33 | When the user input too much digital as phone number, the font is changed from 24pt to 12pt | closed | the amout limitation of input number? If there are more than 2 lines, how about the digital size? | either 24 (one line) or 12
MRS_110 | 9 | roaming icon and at home icon | closed | there is no roaming and at home icon currently in SGL. Shall we remove them? | nice try ;))) add needed icons
MRS_111 | 24 | if there are new events come during the lock status, do we need show those events list in lock screen? | closed |  | No, the SLI of the Home Button will be used (blinking)
MRS_112 | 21 | call barring: ‘incoming/outcoming if abroad’ | closed |  | Already on the AI - under investigation for SW.
MRS_113 | 16 | power saving setting: only set on/off, how about other settings, for example time, if we no need set the details, please define some default value about power saving setting. | closed |  | No other settings
MRS_114 | 12 | Drop a call: what status can be treated as drop, and what description will be shown to the user? | closed |  | technical issue, we proposa an error message (check SGL implementation)
MRS_115 | 12 | we need clarify the redial workflow: do we need show an icon when redial set? | closed |  | refer to styleguide. no icon specified
MRS_116 |  | How to cancel a redial setting? | closed |  | No detailed req., cancel only when reminder "fires"
MRS_118 | 21 | define what kind icon with what kind text | closed |  | Please just use the reference icon list, the styleguide and the Spec
MRS_119 | TCD-USRX-BAS-008138 | what are SIP, URI? | closed |  | Not needed
MRS_122 | TCD-USRX-PRI-008045 | The user shall be able to customize selected aspects of the terminal. By this they can tailor the terminal to their individual needs, habits and preferences. Example 1: The user can customize the home screen shortcuts Example 2: The user can select new wallpaper from the Vodafone live! portal | closed | is it valid for Simply phone? | the user can set ringtones, profiles....based on the UI Spec settings.
MRS_123 | TCD-USRX-BAS-008126 | Clear feedback and status indication shall be provided and all options listed below shall be easily accessible to the user: - Switch loudspeaker on/off - Mute on/off - Hold call - Add new call - Access Contacts - End call | closed | It is about Options For An Ongoing Voice Call. User can not access contacts according to the UI Spec | refer to UI Spec.
MRS_124 | TCD-USRX-BAS-008129 | The user shall be able to access detailed information about the calls in the call log (e.g. date and time, duration, number of attempts, caller information etc.) | closed | there are not so many info. in UI Spec about a certain call log. | refer to UI Spec hover page
MRS_125 | TCD-USRX-SIM-008481 | If the user ends an active call while having another call on hold, the held call shall not be retrieved automatically. The terminal shall continue to display the call on hold and the held call should only be activated when the user chooses to do so. | closed | it is different with SGL. Partially supported. Can we use the same solution as SGL? | there is only one call on hold. No active call in such case. - VF: More than one call possible? >>> Answer: Yes: Setting Call waiting TRUE // Incoming call > hold active call > accept incoming call etc.
MRS_126 | TCD-USRX-LIV-008319 | The user shall be able to initiate a SyncML back up for their contacts from the contact application (i.e. it shall not be necessary to go to settings or connectivity). | closed | according to the UI spec, there are no options for user to copy contacts to network. | refer to UI Spec. the open issue for VF. SyncML here refer to syncronize the contact in SIM and phonebook.
MRS_127 | TCD-USRX-SIM-008489 | The user shall be able to see all calls (incoming, outgoing and missed), messages and reminders related to a single contact in one view. | closed | should "Reminder" be shown in contact log? In UI Spec page 6 there is no reminder in contact log. | Clemens will clarify with VF. -VF: SPEC Correct: reminders in contact detail view (like SPEC), but not in LOG view
MRS_128 | TCD-USRX-BAS-008046 | On master reset all the customisation settings shall be restored to the "out of the box settings". The master reset shall be protected by PIN or user password. | closed | in UI Spec, there isn't any password protection. | refer to UI Spec
MRS_129 | TCD-USRX-LIV-008405 | The help system shall invite the user to apply the learning via "Do it" links. (e.g. When "changing the ring tone" is explained, a "Do it" link goes directly to the settings where the user can change the ring tone directly). | closed | help tips UI shall be provided. | the UI is according to the styleguide. -SYK: will VF provide the animation that is in styleguide? -Clemens: we can put text in help system firstly. Animation will be followed by VF.
MRS_130 | TCD-USRX-BAS-008082 | The terminal shall support the localisation per market for the following aspects: - Local Languages: Local languages shall be supported per market (eg, Belgian French") - Language Adaptation: Local languages and grammar rules shall be supported for display and input language. The translation shall consider cultural specific meanings - Vodafone live! Service Names: The terminal shall be able to support the Vodafone live! service names adapted to local markets - Time and Date Format: Formats for date and time shall be adaptable according to local markets - Numeric Formats: Formats for numeric systems shall be adaptable according to local markets - Currency Formats: Currency formats shall be adaptable according to local markets - Alignment: Alignment of text and other information shall consider cultural characteristics (e.g. Headlines and text to be top left aligned for western markets) - Home Screen Short Cuts: Short cuts from the home screen shall be subject to localisation based on service availability - Main Menu Structure: Main Menu structure shall be subject to localisation based on service availability - Application Key Assignments: Application hard key assignments shall be subject to localisation based on service availability - Embedded Links: Title, Positions and URLs for Embedded Links can vary through markets | closed | How many language should Jerry support? European languages plus Arabic, no asian languages. | Huang Qian (Feb 21): Check with Chai Chun Qian Whether the existing Language Group covers all languages required by VF. Whether there is any redundant languages in existing LGs. - existing Language Group covers all languages required by VF.
MRS_131 | TCD-USRX-LIV-008327 | During the message composition the user shall be aware of the number of concatenated SMS, as well as the type of messages he is sending. | closed | from styleguide, there is no number of concentrate SMS in SMS edior | Clemens will clarify with VF. - VF:Display in text editor [1/160] =first: number of SMS =second: chars available in SMS (count down)
MRS_132 | TCD-USRX-LIV-008333 | It shall be possible to select a message template for the message composition (e.g. a quick text or an MMS template). | closed | it is about "insert template".template need to be clarified. | yes. Template is in open issues.
MRS_133 | TCD-USRX-BAS-008150 | The Voice Message is played back through the earpiece by default. The user shall have the option to play the message via loudspeaker. | closed | no such options in UI Spec regarding Voice message | no such option. The default way to play back VOM is earpiece.
MRS_134 | TCD-USRX-LIV-008357 | Alarms and reminders shall be executed, even if the terminal is switched off. After handling the reminder the user shall be offered to leave the terminal on. | closed | in SGL, after handling the reminder the user can not be offered to leave the terminal on. | VF req. More detailed planning from VF is going on.
MRS_135 | TCD-USRX-BAS-008116 | The terminal shall play DTMF sounds whenever the user enters a phone number or sends DTMF (in call). The terminal shall not play DTMF sounds in any other context. | closed | partially supported. Only can send DTMF in call. | for Jerry, we only need keytone. Not required to play DTMF sound everywhere. -VF:In Jerry only "during call" needed
MRS_136 | TCD-USRX-BAS-008103 | All phonebook entries (i.e. names, email addresses, ..) shall be available as candidate words in the candidate list in Single-tap entry. | open | partially supported in SGL | communicate T9 version. It is in the editor feedback list.
MRS_137 | TCD-USRX-LIV-008406 | The Help system shall make use of multimedia animations to explain in a richer way (e.g. "Show Me"). | open | clarify with VF how it looks like. -VF: High prio: deliver detailed implementation plan for help, especially usage of animation. Timing: Sprint2 (struktur according to spec, incl. Reference text) -Clemens: we can put text in help system firstly. Animation will be followed by VF. | -Yes, accordimng to SISL we can commkunicate to VF in early April the exact details of the Animations we need, VF can order the and deliver them to us
MRS_138 | TCD-USRX-BAS-008070 | A means for multiple selection shall be offered where a command can be applied to more than one object in parallel (e.g. 'delete messages' or 'copy contacts to SIM', 'delete all call log entries') | closed | no multiple selection in UI Spec | do not need it
MRS_139 | new | In the messaging editor the user shall be given guidance to explain - which text entry mode is currently active - how to change the text entry mode - how to insert a symbol - how to insert a space | closed | it is about Automatic Help Texts In The Messaging Editor. Has no indication in UI Spec | refer to the text editor delta requirement list.
MRS_140 | TCD-USRX-BAS-008101 | The user shall be able to edit and delete words in the candidate word list | closed | not supported | not compliant.
MRS_141 | new | The font for text entry situations (e.g. number composition, contact name entry, etc.) shall be enlarged in order to improve legibility . | closed | has not such requirements in styleguide | dedicated for phone number inputting
MRS_142 | new | On initial start up a welcome message shall be displayed. An option to start a guided tour which explains the basic features of the terminal shall be offered along with the message. | closed | it is regarding the new phone? Need to be clarified. | according to Spec. refer to new SIM -Please provide more info regarding contents of the welcome tour -VF: Just like Sagem (using new Jerry specific texts)
MRS_143 | message | where is unsent message stored? Draft/template? | closed |  | in draft.
MRS_144 | message | how to handle if user receives message with the normal MMS: picture&sound&text. | closed |  | handle as SGL. The looklike refer to the UI Spec. -SYK: how to handle the sound when forwarding a normal MMS? Need clarify with Clemens VF: OK | AI(CL): March 10
MRS_145 | message in template | if the draft/template folder supports to store picture or voice message, how to distiguish it from each other, are the icons different? | closed | need to be clarified with VF about the stuff in template. | The differentiation for vom and other messages is by icon. the icon is the same as in sent folder
MRS_146 | message | delete all message: delete order(one by one according to time, or SMS and then MMS)? | closed |  | no specifical req.
MRS_147 | 13 | SK: delete and done. What the UI when delete is pressed? | closed |  | refer to page 10: 03.06
MRS_148 | message | from SW point of view, we need the amount limitation for the sent and draft message folder. | closed |  | we can decide it
MRS_149 | 4 | what the "hide" lead to? The idle screen? | closed |  | go to blank split idle screen with some tbd SK
MRS_150 | startup | What would be the look alike when there is no sim | closed |  | refer to Sagem phone
MRS_151 | call | should we close the application before originating a call from address/phone book , so the application running be stay when the call is ended. | closed |  | come back to addressbook
MRS_152 | screensaver | should screen saver bring the screen back to Idle | closed |  | no
MRS_153 | countrycode | Country code selection menu supported, if yes how the UI look alike? | closed |  | no country code
MRS_154 | PIN2 | Do we support PIN2? | open | Prefer to hide this function since it's not described in UI flow. | Thomas will clarify with VF | AI(Thomas)
MRS_155 | startup | do we need power on confirmation checking? | closed |  | no need
MRS_156 | number input | how the number input would shown in terms of font size | closed |  | Same as simply/R3 until the specificatino is available
MRS_158 | baby sitter | Check if the baby sitter is available | closed |  | Not available
MRS_161 | screensaver | screensaver behaviour should be clarified.. | closed |  | a) No, there is no icon displayed in screen saver for all missed event, only the blinking should be shown on the home hardkey and the event list(info prompt)(sms,mms,reminder, alarm, voice mailbox,missed call,) in idle would be updated
MRS_162 | idle display status | Decide the direction of transition for different status in idle | closed |  | Only one way transition of the status(Profile) should be shown and for others(battery,signal) it should be automatically changed.
MRS_164 | IrDA | Is infrared available? | closed |  | No
MRS_165 | Color scheme | colour scheme shoud be of the context of the calling application or this is fixed for all the application | closed |  | Colour scheme should only be changed in the context of the calling application
MRS_166 | roaming | Investigate the roaming icon | closed |  | If the phone is not roaming and vodafone is the operator then show vodafone icon, otherwise show no icon. If the phone is in roaming and no vodafone operator is available then only show the roaming icon else show vodafon icon
MRS_167 | voicemail | what this (X) in the screen 4:0 | closed |  | X represenet the number of voicemail count
MRS_168 | accessory | what is the wired accessory supported like carkit,headset.. | closed |  | We support(according to steckbrief): Headset Basic HHS-500, Headset HHS-510, Headset Purestyle HHS-610 Car Kit Portable HKP-500, Car Kit Easy HKP-700, Car Kit Comfort Basic HKC-700 (tbc), Mobile Holder Antenna HMH-750 (tbc)
MRS_169 | dictaphone | Is dictaphone supported? | closed |  | Not available
MRS_170 | AT Command | Should the ATK support be provided? | closed |  | AT command would be same as aries.
MRS_171 | ring | Clarify ring tone & ringer setting | closed |  | 1. Ringtone is the right alternative word for profile as in siemens phone. 2. When there is any incoming/outgoing/active call, then ringtone key will be totally nonfunctional. 3. When user is in any menu level then ringtone key should be fully functional.
MRS_172 | dial dialog | should the dial dialog only display Battery and network signal… | closed |  | a) We shall follow the style guide, only battery, signal and ring status shoud be shown
MRS_173 | dial dialog | connecting… text would be required for sprint 1, receiving call screen is not shown in R3 spec, is there are new text then provide the same. | closed |  | Follow the text display , while we intiating or receiving call from R3 specification
MRS_174 | phone feature | Is this a colour phone? | closed |  | Yes, 64 K colour
MRS_175 | idle display status | Ask about the total number of status representation in Idle | closed |  | 1. Signal, 2. Ringtone, 3. Battery, 4. Own Number(Depending upon setting) 2. Accessory notication would overwrite Own Number display if available
MRS_176 | font size | Know the font size to be displayed for the different display in Idle | closed |  | See guidline for adjustments to screendesign for 132x176
MRS_177 | volume screen | Clarify volume screen behaviour | open | Shen Yukai will clarify if there is some bitmap existing -no, ask clemens to check with VF. | VF: Will be provided | AI(CL):March 10
MRS_178 | call swap | Call swap supported? | closed | - since we support to accept a second call if there is another call hold, so, is there call swap? - yes. (check with Clemens) - no conference call? (check with Clemens) - If user keeps a call on hold, can he intitiate another call? (check with Clemens) | One: switching between calls seems to be not required Two: No, the user can not initiate another call during call, it is possible to accept another incoming call.
MRS_179 | call conference | No conference? | closed |  | No
MRS_180 | line 1, line 2 | Line 1, Line 2 supported ? | open |  | Thomas or Clemens will clarify | AI(Thomas)
MRS_181 | home zone | What is home zone? | closed |  | Thomas or Clemens will clarify -the info will be provided by SIM. And support of STK command is already proved by SGL. We only need to check if the right icon is displayed.
MRS_182 | idle | Idle has no softkey? | closed |  | No
MRS_183 | SyncML | SyncML remote synchronization | closed | how to get whether the country with SyncML, flat pricing model? | - Clarify with Thomas. Mobicon stuff -Thomas will clarify. - Thomas: these info will be put by mobicon in SYNCML setting.
MRS_184 | font | Can we use the same font for Arabic like in Aries, or is it necessary to use a font delivered by VF? | closed | We have a special ordering of characters (not Unicode compliant) for some of the characters, so a Unicode compliant font would cause a lot of effort in software to change the bidirectional rendering engine. | clarify with Clemens VF: VF will not provide a "VF" Arabic font. Use BenQ arabic font (if needed) | Will be checked with VF AI(CL): March 10
MRS_185 | CB service | 1. CB needs to be turned on by user. Assumption : For Jerry, CB will be turned ON automatically based on SIM or Mapfile settings. No user action required. 2. CB has a concept of Topics/Channels/IDs. User has to manually select the Topics that he/she is interested in. Assumption : For Jerry, CB Topic/Channels will be selected(activated) automatically based on Mapfile settings. No user action required. 3. User has to manually select the CB language. Assumption : For Jerry, CB Language will be selected(activated) automatically based on Phone-Language settings. No user action required. 4. Display on Idle, when a message is received. Assumption : Jerry should display CB on Idle, similar to the other R65 phones. Layout needs to be decided. | open |  | will VF provide these values to us by Mobicon? - Thomas will confirm. | AI(Thomas)
MRS_186 | Font | 1) what is the "lable text"? 2) some of the "graphics provided by VF"are not included in icon package. | open | when to provide these graphics? | VF: VF will verify Styleguide | 1)AI(CL)(March 10) 2)AI(Thomas)
MRS_187 | delete wizard | In case deleteing Contacts, if less frequently used contacts are to be shown first, then do we have to maintain the counter for contacts on SIM also. If yes, then what will happen if this SIM is inserted in some other phone. Because there is no provision in SIM to have this counter information. | closed | Check with Clemens for our solution: we should maintain the counter after deleting some less frequently used contacts. but if the SIM is inserted in some other phone, the counter should be reset. | OK
MRS_188 | SIM/Phone icons | 1. The flow spec says that there should be some indicator/icon to tell user where the contact is stored (SIM or Phone or both). This is to be shown only in detail view. The contact name & icons have to be shown on the same row. 2. The contact-list as well as the contact-details screens in the Style Guide do not show any such icons. In some cases we may have to use the both the icons. | closed | Check with Clemens for our solution: 1) the icons shall be shown at the position as UI Spec says. update the styleguide. 2) in case the name is too long to be shown, shorten it. | VF Answer: No, we only want one icon (if contact is on both SIM/PHONE NO icon is shown// If contact is either on SIM or on PHONE respective ICON to be shown) | AI(CL):March 10, check with VF
MRS_189 | Battery Icon/Text | provide the table, which represent when to show which battery/signal icon/text | closed | check with Clemens with our solution | OK
MRS_190 | short/long press keys | Clarify the behavior of short/long press handling of the keys like Contact,Home,Menu, side keys, Navi Keys | closed | check with Clemens for our solution: Long press and short press of the keys(Home,Contact,Menu, sidekeys,Ringtone, Softkeys ) have the same behaviour, while Navikey, Volume key, back key have the different functionality Short Navikey press in Menu -> navigation by one menu item Long Navikey press in Menu -> Navigation will go until the release of key happens. Volume key + press -> Same as Navikey handling short press Back key -> one screen back Long press of back key -> Go to Home screen See also ( TCD-USRX-SIM-008470/ Feature Id: PF_Jerry_1877) On pressing of Home/Contact/Menu hardkey all the previous opened application will be closed and the respective application shall be started, only exception is the call handling. During call dialing, call connected and call recieving screen, these hardkeys(Home/Contact/Menu) will have no function | Long press of back key = No action
MRS_191 | charger | If phone is switch off , what should be the behavior when charger is connected?, how the screen should appear. | closed |  | Same as Aries
MRS_192 | alarm | Should the alarm be triggered when phone is switched off? If possible what is the UI | closed |  | Same as Aries but with additional requirement(TCD-USRX-LIV-008357/ PF_Jerry_1881)
MRS_193 | emergency call | How the UI would be if the screen saver/Lock Screen is active and the number 911 is pressed | closed | Handle the emergency number input in the lock screen only, as in Aries, Confirmation with Clemens is still pending | VFAnswer: Yes, emergency call to be supported! BenQ to use their Spec | AI(CL): March 10
MRS_194 | USSD | Is USSD supported? | open | Yes, Layout is still pending with CBS issue | VF Answer; VF will verify internally if this is really required for JERRY | AI(CL): March 10
MRS_195 |  | How Sim full indication to be shown? | closed |  | Follow the Aries solution with UI customization as specified in simply styleguide
MRS_196 |  | Is address book access supported while in a call? | closed | Confirm with Clemens: During a call access to the hardkeys ( Home.Contact,Menu) is not possible, Also the in call there is no option menu. This means user doesn't have access to phone/Address book while in a call. | No contacts access during call
MRS_197 |  | Will the menu entries be accessed by the number? If so discuss the use case of unified list in Idle | closed |  | In all the menu item, the each item can be accessed by number, while in split screen menu in idle , this can be avoided
MRS_198 | icons | The VF icon package contains some GIF animations. These cannot be used directly as resources. We need a sequence of BMPs (instead of GIF) for defining the animation IDs. | open |  |  | AI for Thomas: need to let VF provide the discrete icons
MRS_199 | Voicemail | check with Clemens if the Voicemail notification in SGL is accepted by VF. | open |  |  | Thomas AI
MRS_202 | Voicemail | When viewing a voice mail notification the user shall be able to contact either the mailbox or the initiator of the call. | open | check if VF voice mail notification has the initiator's number.
MRS_203 | Time/date format | Shall Jerry need to have more than one time/date format regarding to different marketing? | open
MRS_204 | accessory | Since Jerry will support accessories, how about the UI settings? shall we add the menu to settings? which Sprint shall the accessory be done? | open