# Jerry Offshore development STATUS Report

Project Context: Jerry Offshore development Customer: BenQ Mobile, Beijing Start date: 22/02/2006 End date:

- Activities Status

| Feature | WP ID | Description | Sprint |  | Completion Status |  | Expected Finish Date | Resource |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Current Week: 31st Mar to 6th Apr |  |  |  |  |  |  |  |  |
| Preparation | 0_6 | Identify all text/icon resources and delivery to ResUI team for integration into project database for sprint 2 |  | 2 | 90%. Some additional updates to be done. | 07 Apr |  | Lovleen |
|  | 0_7 | Integration of graphics/fonts into project database for Sprint 2 |  | 2 | 100% |  | 06 Apr | Rajiv |
|  | 0_9 | Integration of texts into project database for Sprint 2 |  | 2 | 0 |  | 13 Apr | Rajiv |
| Start-up/power on dialogs | 1_2 | Date and Time settings (covered by 18_3) |  |  |  |  |  |  |
| Show Startup Assistant | 2_1 | (TCD-MESG_SIM-990002) At power on, the device shall check EF_MSISDN on the SIM for the presence of an MSISDN. If the field is blank then the device shall prompt the user to "Enter own number"; details of the UI interaction shall be in accordance with the MMI spec. |  | 2 | 80% |  | 06 Apr (08 Apr) | Arjun |
| Idle Screen | 4_3 | Idle UI adaption on network selection |  | 2 | 0 |  | 23 Apr | Arjun |
|  | 4_4 | show call setting: call barring incoming/outgoing if abroad (new ), effect in Idle |  | 2 | 25% |  | 23 Apr | Roohi |
|  | 4_10 | Digital clock with big font in idle screen, including smaller font when date is also displayed. |  | 2 | 25% |  | 16 Apr | Gagan |
|  | 4_11 | Clock in smaller font when date is also displayed. |  | 2 | 0 |  | 23 Apr | Gagan |
| Remove or hide or disable features | 10_6 | showing UI notification about accessory from connectivity (disable) |  | 2 | 0 |  | 23 Apr | Arjun |
| Tips | 11_1 | Phone Basics, Contacts, Calls, Manage contents on PC, International |  | 2 |  |  | 23 Apr | Sunil |
|  | 11_2 | Messages, Events and Alerts, Settings, Accessories |  | 2 |  |  | 17 Apr | Sunil |
| Volume side key, Ringer side key and lock key invocation | 12_1 | ringer side key in idle |  | 2 | 70% |  | 10 Apr | Gurpreet |
|  | 12_2 | volume side key in In-call |  | 2 | 0 |  | 16 Apr | Gurpreet |
|  | 12_3 | lock key |  | 2 | 0 |  | 23 Apr | Gurpreet |
| Contact list and menu options after pressing Contact hard key | 13_3 | contact editor |  | 2 | 25% |  | 23 Apr | Nitin |
|  | 13_4 | merge entry in SIM to Contact list (Unified Contact w/o duplicate check) |  | 2 | 50% |  | 20 Apr | Sunisha |
|  | 13_5 | complicated functions: add reminder |  | 2 | 25% |  | 16 Apr | Avijit |
|  | 13_13 | complicated functions: Edit Reminder |  | 2 | 0 |  | 23 Apr | Avijit |
|  | 13_12 | complicated functions: sim backup w/o view log |  | 2 | 25% |  | 23 Apr | Sunisha,Anuj |
|  | 13_9 | call record look and feel |  | 2 | 50% |  | 20 Apr | Gurbrinder, Saroj |
| Unified Inbox (Layout) | 15_1 | Jerry look and feel of Unified Inbox in SGL functionality w/o MMS |  | 2 | 40% |  | 13 Apr | Akash |
| Synchronization including remote sync and sync with SIM | 16_1 | SyncML UI screens |  | 2 | 20% |  | 23 Apr | Asit |
|  | 16_2 | Startup dialog |  | 2 | 0 |  | 10 Apr | Asit |
|  | 16_3 | Data updations at server and SIM |  | 2 | 30% |  | 23 Apr | Asit, Yogesh |
|  | 16_4 | Data retrieval - address book and phone book |  | 2 | 30% |  | 23 Apr | Indra |
|  | 16_5 | Data synchronization - AE |  | 2 | 40% |  | 23 Apr | Vikram |
|  | 16_6 | server data updation - AE |  | 2 | 0 |  | 16 Apr | Yogesh |
| Settings | 18_1 | ring tone |  | 2 | 0 |  | 13 Apr | Parul |
|  | 18_2 | keypad tone |  | 2 | 100% |  | 06 Apr | Parul |
|  | 18_3 | time & date |  | 2 | 0 |  | 20 Apr | Parul |
|  | 18_4 | display my number |  | 2 | 0 |  | 20 Apr | Sanjeev |
|  | 18_5 | phone language |  | 2 | 0 |  | 13 Apr | Sanjeev |
|  | 18_6 | change PIN |  | 2 | 80% |  | 06 Apr (08 Apr) | Sanjeev |
| Contact log | 19_1 | new msg info table support in PIM AE |  | 2 | 80% |  | 20 Apr | Anuj, Sunisha |
|  | 19_2 | sorting mechanism |  | 2 | 60% |  | 23 Apr | Anuj, Sunisha |
| MsgAE | 32_1 | Detailed design |  | 2 | 100% |  | 31 Mar | Rajeev Bhatia |
| Templates/Drafts | 33_1 | Implementation of Templates/Drafts support in AE |  | 2 | 40% |  | 23 Apr | Kusum |
|  | 33_2 | Templates/draft list visible, with Options menu (without functionality) |  | 2 | 30% |  | 20 Apr | Pushp |
| Planned for Next Week: 7th Apr to 13th Apr |  |  |  |  |  |  |  |  |
| Picture Messaging | 23_1 | Picture Messaging |  | 3 | 10% |  | 20 May | Kapil |
| VF Simply Alarm Clock | 21_1 | list all alarm events |  | 3 | 0 |  | 20 May | Vijay |
| Volume side key, Ringer side key and lock key invocation | 12_2 | volume side key in In-call |  | 2 | 0 |  | 16 Apr | Gurpreet |
| Settings | 18_5 | phone language |  | 2 | 0 |  | 13 Apr | Sanjeev |
|  | 18_1 | ring tone |  | 2 | 0 |  | 13 Apr | Parul |
| SyncML | 16_6 | server data updation - AE |  | 2 | 0 |  | 16 Apr | Yogesh |
| MsgAE | 32_5 | Msg AE - Core (State Machine) |  | 3 | 20% |  | 27 Apr | Ravi |

- Risks

| S. No. | Risk | Impact |
| --- | --- | --- |
| 1. |  |  |

- Open Points / special events

| S. No. | Work Package | Open Issues/Dependencies | To be followed by / Responsible |
| --- | --- | --- | --- |
| 1. | SyncML | Test procedures | BenQ System Test |
| 2. | Tips | Requirement clarification for Tips – Do It and Show me features | Shen Yu Kai |

- Action Items

| No. | Action Item | Responsibility | Complete By | Status |
| --- | --- | --- | --- | --- |
| 1. | Vodafone fonts are defined in .RC file | BenQ Beijing | ASAP | Closed |
| 2. | Devices with BFC unlocked | BenQ Aalborg | ASAP | Closed |
| 3. | Skin file for Jerry PC Simulation | BenQ Beijing | ASAP | Closed |

### DATE: 06.04.2006			        Prepared BY: Rajeev Chauhan