## Jerry Overall
Plan : Overall
| Project Name: Jerry Overall |  |  |  | Planner: Jiang Hui Wen Date: 2006-2-28
[6 empty] | The board outline is only 80% fixed. Purpose is to have a first test of the HW circuits. PCB maturity must be B1 except EMC/ESD, Audio/Acustic, Display and Antenna | Board outline/stack up/screw towers are 100% fixed. PCB maturity must be B1+ except EMC/ESD, Audio/Acustic, Display and Antenna. |  |  |  |  | PCB is compliat over full temperature range | [7 empty] | Final prototype B2.
Department | Location | Contact Person | Function | Tele | Email | A1 | A1+ |  |  |  |  | B1 | [7 empty] | B2 | [7 empty] | Pilot series
[6 empty] | Single PCB Populated | single PCB not populated | panel ( * 6 PCB ) not populated | panel ( * 6 PCB ) populated | boards populated with function | boards w/o function | single PCB not populated | panel ( * 6 PCB ) not populated | panel ( * 6 PCB ) populated | boards populated with function | boards w/o function | Internaltiona Variant |  | Special | single PCB not populated | panel ( * 6 PCB ) not populated | panel ( * 6 PCB ) populated | boards populated with function | boards w/o function | Internaltiona Variant |  | Special
[17 empty] | DV1 | [7 empty] | DV1
[10 empty] | BV1 |  |  |  |  | BV1 |  | with hole | w/o hole NA |  |  |  |  | BV1 |  | with hole | w/o hole NA
China Site | BJ |  | PL-T
China Site | BJ | Zhang Shuai | PM | +86 10 6474-8800 ext 7313 | Shai.Zhang@benq.com | [11 empty] | 10 |  | 6 | [5 empty] | 20 |  | 6 | 30
China Site | BJ | Wu Yu Jin | BB | +86 10 6474-8800 ext8794 | yujin.wu@benq.com |  |  |  |  | 2 |  | 2 |  |  | 22 |  | 22 |  |  | 2 |  |  | 22 |  | 28
China Site | BJ | Li Jian | RF | +86 10 6474-8800 ext8205 | jian.lee@benq.com |  |  | 1 |  | 14 |  |  | 1 |  | 14 |  | 18 |  |  |  | 1 |  | 8 |  | 16
China Site | BJ | Peter Loeber | EA | +86 10 6474-8800 ext7865 | peter.lober@benq.com |  |  |  |  | 8 |  |  |  |  | 5 |  | 17 | [5 empty] | 5 |  | 20
China Site | BJ | Yang Yong Qiang | SW | +86 10 6474-8800 ext8285 | yongqiang.yang@benq.com |  |  |  |  | 6 |  |  |  |  | 6 |  | 42 | [5 empty] | 6 |  | 24
China Site | BJ | xxx | L1 | xxxx | xxxx
China Site | BJ | Yang LI | ST1 | +86 10 6474-8800 ext7566 | li.yang@benq.com | [11 empty] | 41 | [7 empty] | 41
China Site | BJ | Wei Xue Kai | ST2 | +86 10 6474-8800 ext8059 | XueKai.Wei@benq.com |  |  |  |  | 10 | [6 empty] | 33 | [7 empty] | 52
China Site | BJ | Wu Li Bo | LPD/FPC | +86 10 6474-8800 ext7518 | LiBo.Wu@benq.com |  |  | 1 |  | 1 |  |  | 1 |  | 1 |  | 5 |  |  |  | 1 |  | 1 |  | 5
China Site | BJ | Thomas Bartel | PQA | +49 (89) 722-40029 | thomas.bartel.ext@benq.com | [11 empty] | 23 | [7 empty] | 240
China Site | BJ | Zhang Qiu Ping | SW QA | +86 10 64748800-8046 | QiuPing.Zhang@benQ.com | [11 empty] | 2 | [7 empty] | 2
| BJ | Andreas Springer | CC | [13 empty] | 3 | [7 empty] | 12 |  |  | 44
China Site | BJ | Fu Lin Ping | MD | +86 10 6474-8800 ext 7545 | linping.fu@benq.com | 0 |  |  |  | 10 |  |  |  |  | 10 |  | 124 | [5 empty] | 10 |  | 30 |  |  | 0
China Site | BJ | Jiang Hui wen | ST2/Prototype | +86 10 6474-8800 ext 8668 | huiwen.jiang@benq.com | 6 |  |  |  | 3 | [6 empty] | 10 | [7 empty] | 15
Subtotal | [5 empty] | 6 | 0 | 2 | 0 | 54 | 0 | 2 | 2 | 0 | 58 | 0 | 350 | 0 | 6 | 2 | 2 | 0 | 52 | 0 | 505 | 0 | 6 | 74
China Site | SHA | Li Jian Hong | MD | +86 10 6474-8800 ext 7087 | JianHong.Li@benq.com | 0 |  |  |  | 2 | [17 empty] | 0
China Site | SHA | Shen Xiao Zhong | CCQ QM | +86 21 61012713 | xiaozhong.shen@benq.com | [19 empty] | 81
China Site | SHA | Gong Jing Wen | LCM3 | +86021-61012679 | jingwen.gong@benq.com |  |  | 2 | 2 | 18 |  |  | 8 | 5 | 14 | 6 | 17 |  |  |  | 4 | 6 | 25 | 9 | 27
China Site | SHA | Hu Xian Gui | SQM | +86021-61011903 | xiangui.hu@benq.com | [11 empty] | 1 | [7 empty] | 5
Subtotal | [5 empty] | 0 | 0 | 2 | 2 | 20 | 0 | 0 | 8 | 5 | 14 | 6 | 18 | 0 | 0 | 0 | 4 | 6 | 25 | 9 | 113 | 0 | 0 | 0
China Site | KLF | Thomas Krokowski | PAS/Field test | +49 (2842) 95-4659 | thomas.krokowski@benq.com | [11 empty] | 3 | [7 empty] | 156
Denmark Site | KLF | Katharina Hilker | LCM3 |  |  | 5 | 1 | 2 | 5 | 17 | 10 | 1 | 2 | 1 | 26 | 16 | 54 |  |  | 1 | 2 | 1 | 28 | 7 | 65
Denmark Site | KLF | Jens Riedel | LCM1
Subtotal | [5 empty] | 5 | 1 | 2 | 5 | 17 | 10 | 1 | 2 | 1 | 26 | 16 | 57 | 0 | 0 | 1 | 2 | 1 | 28 | 7 | 221 | 0 | 0 | 0
China Site | MCH | Steven Mueller | Safety Lab (EN60950) | +49 89 / 722 - 22505 F33 | steven.mueller@siemens.com | [19 empty] | 3
Denmark Site | MCH | Thomas Bartl Monika Reiss | VF PM | [13 empty] | 4 | [7 empty] | 2
| MCH | Wolfgang Klebsch Jürgen Schmidt |  |  |  | 1 |  |  |  | 2 | [6 empty] | 2 | [7 empty] | 2
| MCH | Alessandro Valtorta | Sales Academy | [13 empty] | 2 | [7 empty] | 2 |  |  | 2
| MCH | Juerg Karpinski | BMG SC | [21 empty] | 2
| MCH | Karin Falkenberger | VM | [21 empty] | 6 |  |  | 4
| MCH | Nicole Kohler | User Guide | [21 empty] | 2
| MCH | Edmund Trageser | BO Mobicon | [21 empty] | 2
| MCH | Edmund Trageser | TMP Musterkoffer | [21 empty] | 1
| MCH | Antonia Wüstenberg | SCM TLM PT1 | [13 empty] | 6 | [7 empty] | 6
| MCH | Gary Vincent | GAM | [13 empty] | 50 | [7 empty] | 50 |  |  | 50
| MCH | Franz Billich (for Vodafone) | VF GPM |  |  | 1 |  |  |  | 1 | [6 empty] | 20 |  | 11 data cable | [5 empty] | 630 |  | 139 data cable + 10 cradle + 4 dummy batteries
Denmark Site | MCH | Clemens Lutch | [14 empty] | 2 | [7 empty] | 1
| MCH | Birgit Scheidle | Marketing | [13 empty] | 3 | [7 empty] | 4 |  |  | 4
Denmark Site | MCH | Thorsten Lange | AD |  |  | 0 | [10 empty] | 8 | [7 empty] | 20
Denmark Site | MCH | Andreas Michael Mairhof | AD | [13 empty] | 2 | [7 empty] | 4 |  |  | 2
Subtotal | [5 empty] | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 737 | 0 | 0 | 62
China Site | AAL | Brian Mortensen | SW QA | +45 7219 5787 | brian.mortensen@benq.com | [11 empty] | 2 | [7 empty] | 2
Denmark Site | AAL | Lars Bonde | PLT |  |  | 1 |  |  |  | 10 | [6 empty] | 10 | [7 empty] | 10 |  |  | 2
Denmark Site | AAL | Flemming Bach Kristensen | BB |  |  | 21 |  |  |  | 22 | [6 empty] | 23 | [7 empty] | 15
Denmark Site | AAL | Michael Brammer | RF |  |  | 5 |  |  |  | 5 | [6 empty] | 5 | [7 empty] | 5
Denmark Site | AAL | Christian Primdahl Nielsen | ME |  |  | 1 |  |  |  | 5 | [6 empty] | 5 | [7 empty] | 5
Denmark Site | AAL | Arne Bisgaard Kristensen | EA |  |  | 1 |  |  |  | 10 |  |  |  |  | 5 |  | 20 | [5 empty] | 3 |  | 10
Denmark Site | AAL | Poul Søndergaard | PQA
Denmark Site | BEJ | Allan Hansen | SW |  |  | 9 |  |  |  | 10 | [6 empty] | 10 | [7 empty] | 10
Denmark Site | AAL
Denmark Site | AAL
Denmark Site | AAL | Henning Boll | CC |  |  | 0 |  |  |  | 0 | [17 empty] | 0
Denmark Site | AAL | Flemming Kokholm | ST |  |  | 1 |  |  |  | 1 | [6 empty] | 3 | [7 empty] | 3
Subtotal | [5 empty] | 39 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 5 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 60 | 0 | 0 | 2
Total | [5 empty] | 52 | 1 | 6 | 7 | 157 | 10 | 3 | 12 | 6 | 103 | 22 | 602 | 0 | 6 | 3 | 8 | 7 | 108 | 16 | 1636 | 0 | 6 | 138
[6 empty] | 52 |  |  | 209 |  |  |  |  | 161 |  |  | 602 |  |  |  |  | 166 |  |  | 1636 |  |  | 138
Note on K12: Jiang Hui wen Change from 13 to 14
Note on K17: Jiang Huiwen: add From 4 to 10
Note on P14: Jiang Hui wen Change from 0 to 6
Note on R10: Jiang Huiwen: adding from 10 to 94 Sean changed back from 94 to 10
Note on R13: Poul Erik Rask: 5 pcs added for two HW variants
Note on R19: Jiang Huiwen: Adding from 13 to 23
Note on R21: Poul Erik Rask: Added by Sean
Note on R45: all samples required for Vf global headquarter
Note on R47: Poul Erik Rask: Added by Sean
Note on R56: Poul Erik Rask: 5 pcs added for two HW variants
Note on R61: Poul Erik Rask Changed from 2 to 0 by Sean
Note on R62: Poul Erik Rask: Flemming changed 23rd of March from 25 to 3
Note on T10: Jiang Huiwen: Non Fuction phone adding from 0 to 6
Note on X14: Jiang Hui wen Change from 0 to 6
Note on Z10: Jiang Huiwen: Adding from 20 to 739 Sean changed from 739 pcs to 20
Note on Z19: Poul Erik Rask: Changed from 25 to 40 Jiang Hui wen Change form 40 to 240
Note on Z21: Poul Erik Rask: Added by Sean
Note on Z47: Poul Erik Rask: Added by Sean
Note on Z61: Poul Erik Rask: Changed from 15 to 0 by Sean
Note on Z62: Poul Erik Rask: Flemming chenged 23rd of March fro 5 to 3
Note on AB10: Jiang Huiwen: Non Fuction phone adding from 0 to 6
Note on AC10: Jiang Huiwen, Adding form 30 to 136 Sean changed from 136 to 30 Changed by Sean
Note on AC21: Poul Erik Rask: Added by Sean
Note on AC47: Poul Erik Rask: Added by Sean

## Variant Definision
Component | Name | SAP# | Hardware 1 (HW1) | Hardware 2 (HW2)
PMU | Mozart/Twigo4+ | A5B00075644155 | Dialog | STM
Memory FLASH | FLASH 256MBit x 16 | A5B00075317458 | Intel, NZ48F4000L0YTQ0 | Spansion, S99-50003
Memory SDRAM | SDRAM 64Mbit | A5B00075066848 | Hynix, HY5S6B6DLF-SEDR | Samsung, K4M64163PH-RG1L
Power supply | POWER SUPPLY/L55/E/C39280Z 4C404 1 | A5B00075004777 | Astec | Friwo
SIM-Filter | EMIF03 | A5B00075175039 | STM, EMIF03-SIM01 | Philips, IP4044CX8/LEADED
Battery pack | BATTERY PACK/ARIES/LI-ION/820MAH | A5B00075547043 | Samsung | NEC
Speaker | Penelope Speaker | A5B00075156731 | Bujeon | Hosiden
Microphone | Penelope Microphone | A5B00075098861 | Bujeon | Hosiden
Vibra | VIBRAMOTOR/11MM*4M/C39453Z 5C251 | A5B00075040075 | Shicoh | Nidec
Battery connector | STV/BATTERY 3-POL SMD-SPRINFORCE | A5B00075012176 | FCI | Lumberg
RF connector | standard coax connector | A5B00075530183 | Hirose | Tyco
Display connector |  | A5B00075004245 | ITT | Tyco
For A1, B1 and B2 the prototype series will be split in two equal halves with HW1 and HW2