## Change History
Jerry Prioritized Feature cluster
History of Change
Version | Date | Editor | Status | Description
1.0_001 | 2006-02-14 | Huang Qian | in work | First draft created during the requirement and feature list workshop.
1.1_000 | 2006-02-20 | Yang Yong Qiang | in review | refined in workshop. Offline review.
1.1_003 | 2006-03-02 | Yang Yong Qiang Rajeev Chauhan | in review | Rearranged all WPs according to the Sprint. Feature and WP IDs defined. Added 2 WPs for Contacts: delete wizard and duplicate check. Offline review.
1.1_004 | 2006-03-16 | Rajeev Chauhan | in review | Moved (PIM) Contact Log work packages from Sprint 2 to Sprint 3
1.2_001 | 2006-03-16 | Hu Chun Yan | in review | Add 4 text editor WPs and 1 system message WP Offline review
1.2_002 | 2006-03-16 | Hu Chun Yan | in review | Merge the change between 1.1_004 and 1.2_001 offline review
1.2_003 | 2006-03-18 | Hu Chun Yan | in review | Add 10 text editor WPs in sprint2 Add 1 WP (System message) in sprint1 Make the WP ID unique, change WPID from 3_1 to 3_3 in sprint3 Offline review
1.2_004 | 2006-04-07 | Rajeev Chauhan Hu Chun Yan | in review | Moved 19_1 and 19_2 from Sprint 3 to Sprint 2 Moved 14_2 and 14_3 from sprint3 to sprint 2 Moved 28_1 from sprint4 to sprint 3 Added new WP 0_6, 0_7, 0_10, 36_17, 32_8, 36_18 in Sprint 2. Added new WP 0_8, 0_11, 11_3,12_4, 13_15, 38_1, 36_19 in Sprint 3. Added new WP 13_14, 21_6, 39_1, 40_1 in sprint 4 Remove WP 19_5 ( duplicate of 13_8). Remove 36_12 from Sprint 2 because it is covered by 36_4. Split the Setings WP (18) in Sprint 2 into smaller WPs. Responsibility changed from SISL to PEK for Sprint 2 WPs 10_1, 10_2 and 10_4 and Sprint 3 WP 10_3 and 3_3.
1.2_005 | 2006-04-21 | Rajeev Chauhan Hu Chun Yan | in review | Changes are marked in Blue Colour
1.2_006 | 2006-04-30 | Rajeev Chauhan Hu Chun Yan | in review | Changes are marked in Blue Colour

## All Features
ID | Feature | Sprint | Timeline | Remark
1 | Start-up/power on dialogs | sprint 1 | 31.03.2006 | Only PIN input in sprint 1, rest by sprint 3
2 | Show Startup Assistant | sprint 3 | 31.05.2006
3 | PC Simu setup | sprint 1 | 31.03.2006
4 | Idle screen | sprint 1 | 31.03.2006 | Only as VF Simply Styleguide (version 1.5, 02.02.2006) page 5 figure 1.Idle, incl all functional scenario, w/o transition, headline, softkeys effect. Rest by sprint 4
5 | Home/Contact/Menu hard key invocation | sprint 1 | 31.03.2006
6 | Phone spaces, color schemes, Icons, Fonts | sprint 1 | 31.03.2006
7 | Voice call screens basic | sprint 1 | 31.03.2006 | Full functions by sprint 3
8 | Headline and soft key look and feel | sprint 1 | 31.03.2006
9 | Menu look and feel basic | sprint 1 | 31.03.2006 | Full compliance by sprint 3
10 | Remove or hide or disable features | sprint 1 | 31.03.2006
11 | Tips | sprint 2 | 28.04.2006
12 | Volume side key, Ringer side key and lock key invocation | sprint 2 | 28.04.2006
13 | Contact list and menu options (without functionality inside) after pressing Contact hard key | sprint 1 | 31.03.2006 | Full functions by sprint 3
14 | Screen transitions | sprint 2 | 28.04.2006 | Only sliding effect. Menu and popup selection transitions by sprint 3.
15 | Unified Inbox (Layout) | sprint 2 | 28.04.2006 | Full functions by sprint 4
16 | Synchronization including remote sync and sync with SIM | sprint 2 | 28.04.2006
17 | Key lock screen after switching the key lock hard key. | sprint 3 | 31.05.2006
18 | Settings | sprint 3 | 31.05.2006 | Ring tong, keypad tone, time/date, display my number, language and change PIN shall be available by sprint 2
19 | Contact log | sprint 2 | 28.04.2006
20 | Voice call screens (full functions) | sprint 3 | 31.05.2006
21 | VF Simply Alarm Clock | sprint 4 | 07.07.2006
22 | Voice messaging | sprint 3 | 31.05.2006
23 | Picture messaging | sprint 3 | 31.05.2006
24 | Message setting | sprint 3 | 31.05.2006
25 | Inbox UI (all message list) | sprint 3 | 31.05.2006
26 | Menu look and feel - full compliance | sprint 3 | 31.05.2006
27 | Sleep mode with timer settings | sprint 4 | 07.07.2006
28 | Hover functionality in Contact list | sprint 4 | 07.07.2006
29 | Unified Inbox Functionality | sprint 4 | 07.07.2006
30 | Text message (SMS) | sprint 4 | 07.07.2006
31 | Idle split screen | sprint 4 | 07.07.2006
32 | MsgAE | sprint 4 | 07.07.2006
33 | Templates/Drafts | sprint 4 | 07.07.2006
34 | Unified sent message | sprint 4 | 07.07.2006
35 | Delete (All) wizard | sprint 4 | 07.07.2006
36 | Text editor | sprint 2 | 28.04.2006
37 | System message | sprint 1 | 31.03.2006
38 | Remove lint errors | sprint 3 | 31.05.2006
39 | Power Save mode | Sprint 4 | 07.07.2006
40 | Voice mail | Sprint 4 | 07.07.2006
41 | Delete (All) wizard for Message | Sprint 4 | 07.07.2006

## Sprint 1
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
BL ID | Backlog Item | WP ID | Workpackage Description | #wks | #rce | Mwk | Mwk | SITE | contact person | Dependency | comment | Effort Spent (MW) | % complete | Expected Finish Date | Actual Finish Date | Deviation (Effort)
0 | Preparation | 0_1 | Identify all text/icon resources and delivery to ResUI team for integration into project database for sprint 1 | 2 | 1 | 2 |  | SISL | Lovleen
|  | 0_3 | Integration of texts/graphics/fonts into project database for sprint 1 | 2 | 1 | 2 |  | SISL | Rajeev |  |  | 3 | 100% | 20-03-06 | 29-03-06 | 1 MW
|  | 0_5 | define Font in UIOS | 1 | 1 |  | 1 | Beijing | Lu Qi Wen | text resources
1 | Start-up/power on dialogs | 1_1 | PIN input, incl. error handling | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | text resources
3 | PC Simu setup | 3_1 | 3 hard keys (Home, Contact, Menu) simu, blinking effect for home key | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | DL
|  | 3_2 | side keys simu | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | DL
4 | Idle screen | 4_1 | Refer to VF Simply Styleguide (version 1.5, 02.02.2006) page 5 figure 1.Idle, incl all functional scenario, w/o transition, headline, softkeys effect | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | text/icon
5 | Home/Contact/Menu hard key invocation | 5_1 | Invocation of native applications on hard keys press, light effect at home space | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | UIOS, DL
6 | Phone spaces, color schemes, Icons, Fonts | 6_1 | color scheme switching interface, define additional virtual colors | 2 | 1 |  | 2 | Beijing | Lu Qi Wen | text resource
|  | 6_2 | text resource to define color scheme | 1 | 1 |  | 1 | Beijing | Wu Ying Yu
|  | 6_3 | phone space color scheme switching (IDC) | 1 | 1 | 1 |  | SISL | Rajeev Chauhan | color scheme switching in UIOS
7 | Voice call screens basic | 7_1 | calling use case: call origination, termination, call setup | 4 | 3 | 12 |  | SISL with Beijing IDC support | Rajeev Chauhan Xu Peng
8 | Headline and soft key look and feel | 8_1 | UIOS | 4 | 3 | 12 |  | SISL | Rajeev
9 | Menu look and feel basic | 9_1 | look and feel w/o transition effects | 4 | 2 |  | 8 | Beijing | Lu Qi Wen
|  | 9_2 | scroll bar | 2 | 1 | 2 |  | SISL | Rajeev Chauhan
10 | Remove or hide or disable features | 10_5 | Java (remove) | 2 | 1 |  | 2 | Beijing
13 | Contact list and menu options after pressing Contact hard key | 13_1 | list address book (without functionality inside) | 2 | 2 | 4 |  | SISL | Rajeev Chauhan
|  | 13_2 | display menu options with some functions, e.g. copy, delete contact (w/o delete wizard), add new contact (w/o new UI) | 3 | 2 | 6 |  | SISL | Rajeev Chauhan
36 | Text editor | 36_1 | undesired deletion of words | 1 | 1 |  | 1 | Beijing | Lu Qi Wen
|  | 36_2 | emotion icons in symbol list | 2 | 1 |  | 2 | Beijing | Lu Qi Wen
|  | 36_3 | 2-way navigation in predictive entry | 1 | 1 |  | 1 | Beijing | Lu Qi Wen
|  | 36_4 | change of entry mode | 2 | 1 |  | 2 | Beijing | Lu Qi Wen
|  | 36_5 | draw line | 1 | 1 |  | 1 | Beijing | Lu Qi Wen
37 | System message | 37_1 | system message | 2 | 1 |  | 2 | Beijing | Lu Qi Wen
| Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
| Preparation for sprint N+1 | [5 empty] | 0 | Beijing
[6 empty] | 77 | 23
| total effort(MW) |  |  |  |  | 100

## Sprint 2
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
BL ID | Backlog Item | WP ID | Workpackage Description | #wks | #rce | Mwk | Mwk | SITE | contact person | Dependency | comment | Component | Effort Spent (MW) | % complete | Remaining Effort (MW) | Expected Finish Date
0 | Preparation | 0_6 | Identify all text/icon resources and delivery to ResUI team for integration into project database for sprint 2 | 2 | 1 | 2 |  | SISL | Lovleen |  |  | MMI_Spec | 2 | 100% | 0 | 2006-04-07
|  | 0_7 | Integration of graphics/fonts into project database for Sprint 2 | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | ResUI | 1 | 100% | 0 | 2006-04-06
|  | 0_9 | Integration of texts into project database for Sprint 2 | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | ResUI | 1 | 100% | 0 | 2006-04-13
|  | 0_13 | Integration of additional fonts/icons | 0.8 | 1 | 0.8 |  | SISL |  |  |  | ResUI | 0.8 | 100% | 0 | 2006-04-20
|  | 0_14 | Integration of updated texts into project database | 0.4 | 1 | 0.4 |  | SISL |  |  |  | ResUI | 4 | 100% | 0 | 2006-04-23
|  | 0_10 | rc file incl. all language and characters | 1 | 1 |  | 1 | PEK | Cao Dong Dong |  |  |  | 0 | 0% | 1 | 2006-04-13
1 | Start-up/power on dialogs | 1_2 | Date and Time settings (covered by 18_3) |  |  |  |  | SISL | Rajeev Chauhan
2 | Show Startup Assistant | 2_1 | (TCD-MESG_SIM-990002) At power on, the device shall check EF_MSISDN on the SIM for the presence of an MSISDN. If the field is blank then the device shall prompt the user to "Enter own number"; details of the UI interaction shall be in accordance with the MMI spec. | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 1.4 | 100% | 0 | 4/6/2006 (4/8/2006)
4 | Idle screen | 4_3 | Idle UI adaption on network selection | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 2 | 100% | 0 | 2006-04-23
|  | 4_4 | show call setting: call barring incoming/outcoming if abroad (new ), effect in Idle | 4 | 1 | 4 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 4 | 100% | 0 | 2006-04-23
|  | 4_10 | Digital clock with big font in idle screen, including smaller font when date is also displayed. | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 2 | 100% | 0 | 2006-04-16
|  | 4_11 | Clock in smaller font when date is also displayed. | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 0 | 100% | 0 | 2006-04-16
10 | Remove or hide or disable features | 10_1 | IrDA, BT (remove) | 2 | 1 |  | 2 | PEK | Zhang Nan |  |  |  | 1.2 | 60% | 0.8 | 2006-04-14
|  | 10_2 | Camera (remove) | 2 | 1 |  | 2 | PEK | Zhang Jing |  |  |  | 0.6 | 30% | 1.4 | 2006-04-21
|  | 10_4 | Browser (hide) | 4 | 1 |  | 4 | PEK | Yang Hong Hui |  |  |  | 2 | 50% | 2 | 2006-04-21
|  | 10_6 | showing UI notification about accessory from connectivity (disable) | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 2 | 100% | 0 | 2006-04-20
11 | Tips | 11_1 | Phone Basics, Contacts, Calls, Manage contents on PC, International | 2 | 2 | 4 |  | SISL | Rajeev Chauhan | UIOS |  | AppBase | 4 | 100% | 0 | 2006-04-23
|  | 11_2 | Messages, Events and Alerts, Settings, Accessories | 2 | 2 | 4 |  | SISL | Rajeev Chauhan |  |  | AppBase | 4 | 100% | 0 | 2006-04-17
12 | Volume side key, Ringer side key and lock key invocation | 12_1 | ringer side key in idle | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 2 | 100% | 0 | 2006-04-10
|  | 12_2 | volume side key in In-call | 1 | 1 | 1 |  | SISL | Rajeev |  |  | AppIDC | 1 | 100% | 0 | 2006-04-16
|  | 12_3 | lock key | 1 | 1 | 1 |  | SISL | Rajeev | UIOS | With Beijing PIM team support | AppIDC | 1 | 100% | 0 | 2006-04-20
13 | Contact list and menu options after pressing Contact hard key | 13_3 | contact editor | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | UIOS | With Beijing PIM team support | AppPIM | 4 | 100% | 0 | 2006-04-23
|  | 13_4 | merge entry in SIM to Contact list (Unified Contact w/o duplicate check) | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | list address book | With Beijing PIM team support | AppPIM | 4 | 100% | 0 | 4/20/2006 (21 Apr)
|  | 13_5 | complicated functions: add reminder | 3 | 1 | 3 |  | SISL | Rajeev Chauhan | display menu options | With Beijing PIM team support | AppPIM | 3.4 | 100% | 0 | 4/16/2006 (21 Apr)
|  | 13_9 | call record look and feel | 4 | 2 | 8 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 8 | 100% | 0 | 2006-04-20
|  | 13_12 | complicated functions: sim backup w/o view log | 4 | 1 | 4 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 4 | 100% | 0 | 2006-04-23
|  | 13_13 | complicated functions: Edit Reminder | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 1 | 100% | 0 | 2006-04-23
14 | Screen transitions | 14_1 | sliding effect | 4 | 2 |  | 8 | PEK | Yi Xiao Qiang |  |  |  | 7.2 | 90% | 0.8 | 2006-04-14
|  | 14_2 | menu selection transition | 4 | 1 |  | 4 | PEK | Yi Xiao Qiang |  |  |  | 1.6 | 40% | 2.4 | 2006-04-21
|  | 14_3 | popup transition | 4 | 1 |  | 4 | PEK | Luo Xu |  |  |  | 1.6 | 40% | 2.4 | 2006-04-21
15 | Unified Inbox (Layout) | 15_1 | Jerry look and feel of Unified Inbox in SGL functionality w/o MMS | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | could start in parallel beginning of Mar |  | Messaging | 2 | 100% | 0 | 2006-04-13
16 | Synchronization including remote sync and sync with SIM | 16_1 | SyncML UI screens | 2 | 2 | 4 |  | SISL | Rajeev Chauhan | could start in parallel beginning of Mar |  | SyncML | 3.4 | 100% | 0 | 2006-04-23
|  | 16_2 | Startup dialog UI | 0.4 | 1 | 0.4 |  | SISL | Rajeev Chauhan |  |  | SyncML | 0.4 | 100% | 0 | 2006-04-10
|  | 16_3 | Data updations at server and SIM - UI | 1.8 | 2 | 3.6 |  | SISL | Rajeev Chauhan |  |  | SyncML | 4 | 100% | 0 | 2006-04-23
|  | 16_4 | Data retrieval - address book and phone book - AE | 2 | 2 | 4 |  | SISL | Rajeev |  |  | SyncML | 4 | 100% | 0 | 2006-04-23
|  | 16_5 | Data syncronization - AE | 2.5 | 2 | 5 |  | SISL | Rajeev |  |  | SyncML | 5 | 100% | 0 | 2006-04-23
|  | 16_6 | server data updation - AE | 1 | 1 | 1 |  | SISL | Rajeev |  |  | SyncML | 1 | 100% | 0 | 2006-04-23
18 | Settings | 18_1 | ring tone UI part | 1 | 1 | 1 |  | SISL | Rajeev |  |  | AppBase | 1 | 100% | 0 | 2006-04-13
|  | 18_2 | keypad tone | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 1 | 100% | 0 | 2006-04-06
|  | 18_3 | time & date | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 1.4 | 100% | 0 | 4/20/2006 (22 Apr)
|  | 18_4 | display my number | 1 | 1 | 1 |  | SISL | Rajeev |  |  | AppBase | 1 | 100% | 0 | 2006-04-20
|  | 18_5 | phone language | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 1 | 100% | 0 | 2006-04-13
|  | 18_6 | change PIN | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 1.4 | 100% | 0 | 4/6/2006 (08 Apr)
19 | Contact log | 19_1 | new msg info table support in PIM AE | 4 | 2 | 8 |  | SISL | Rajeev |  |  | AppPIM | 8.2 | 100% | 0 | 4/20/2006 (21 Apr)
|  | 19_2 | sorting mechanism | 4 | 1 | 4 |  | SISL | Rajeev |  |  | AppPIM | 4 | 100% | 0 | 2006-04-23
26 | Menu look and feel - full compliance | 26_3 | icon highlight switching | 3 | 1 |  | 3 | PEK | Zhou Tong |  |  |  | 1.5 | 50% | 1.5 | 2006-04-14
32 | MsgAE | 32_8 | Detailed design | 2 | 1 | 2 |  | SISL |  |  |  | Messaging | 2 | 100 | 0 | 2006-03-31
33 | Templates/Drafts | 33_1 | Implementation of Templates/Drafts support in AE | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | Messaging | 2 | 100% | 0 | 2006-04-23
|  | 33_2 | Templates/draft list visible, with Options menu (without functionality) | 2 | 1 | 2 |  | SISL |  |  |  | Messaging | 2 | 100% | 0 | 2006-04-20
36 | Text editor | 36_6 | tool tip | 1 | 1 |  | 1 | PEK | Luo Xu | 1 | 100% |  | 1 | 100% | 0 | 2006-04-06
|  | 36_7 | toggling through the candidates in predictive text entry | 4 | 1 |  | 4 | PEK | Luo Xu | 4 | 100% |  | 4 | 100% | 0 | 2006-04-06
|  | 36_8 | dynamic reordering of the candidates list | 2 | 1 |  | 2 | PEK | Song Wen Juan | 1 | 50% |  | 1 | 50% | 1 | 2006-04-14
|  | 36_10 | special characters | 1 | 1 |  | 1 | PEK | Zhang Jing | 0.4 | 100% |  | 0.4 | 100% | 0 | 2006-03-28
|  | 36_11 | cursor flashing in predictive entry | 1 | 1 |  | 1 | PEK | Zhang Jing | 1 | 100% |  | 1 | 100% | 0 | 2006-04-03
|  | 36_12 | Support for Multiple Language Character Sets | 2 | 1 |  | 2 | PEK | Song Wen Juan | 1.4 | 70% |  | 1.4 | 70% | 0.6 | 2006-04-14
|  | 36_13 | 0/1 key symbol list in multitap/singletap | 1 | 1 |  | 1 | PEK | Cao Dong Dong | 1 | 100% |  | 1 | 100% | 0 | 2006-04-04
|  | 36_16 | clear softkey label/add space after interrogation symbol | 1 | 1 |  | 1 | PEK | Zhang Nan | 1 | 100% |  | 1 | 100% | 0 | 2006-04-03
|  | 36_17 | Transition adaption in T9 word choice list | 0.5 | 1 |  | 0.5 | PEK | Luo Xu | 0 | 0% |  | 0 | 0% | 1 | 2006-04-21
|  | 36_18 | Transition adaption in tool tip | 0.5 | 1 |  | 0.5 | PEK | Luo Xu | 0 | 0% |  | 0 | 0% | 1 | 2006-04-21
| customization(mapping, FFS) |  |  | 2 | 1 |  | 2 | PEK
| Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 2 | 8 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 1 |  | 4 | PEK
| Preparation for sprint N+1 | [5 empty] | 0 | PEK
[6 empty] | 117.2 | 48
| total effort(MW) |  |  |  |  | 165.2 | [6 empty] | 127.9 |  | 15.9
Note on D39: ic000637: Dependant on APO implementation of phone book data retrieval

## Sprint 3
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
BL ID | Backlog Item | WP ID | Workpackage Description | #wks | #rce | Mwk | Mwk | SITE | contact person | Dependency | comment | Component | Effort Spent (MW) | % complete | Remaining Effort (MW) | Expected Finish Date
0 | Preparation | 0_2 | Identify all text/icon resources and delivery to ResUI team for integration into project database (cover all sprints) | 2 | 1 | 2 |  | SISL | Lovleen |  |  | MMI_Spec | 2 | 100% | 0 | 2006-04-25
|  | 0_4 | Integration of graphics/fonts into project database for Sprint 3 | 1 | 1 | 1 |  | SISL | Rajeev |  |  | ResUI | 0.6 | 0 | 0.4 | 2006-05-02
|  | 0_12 | Integration of texts into project database for Sprint 3 | 1 | 1 | 1 |  | SISL | Rajeev |  |  | ResUI | 0 | 0 | 1 | 2006-05-06
|  | 0_8 | Integration of Tips animations/bitmaps provided by VF | 2 | 1 | 2 |  | SISL | Rajeev |  |  | ResUI | 0 | 0 | 2 | 2006-05-18
|  | 0_11 | Infineon change PS of voice mail |  |  |  |  | Infineion
2 | Show Startup Assistant | 2_2 | invoke SyncML and Sync between SIM and phone | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 1 | 100% | 0 | 2006-04-23
3 | PC Simu setup | 3_3 | Changes in C_MobSIM for removing/disabling/hiding features | 2 | 1 |  | 2 | PEK | Zhang Jing |  |  |  | 0 | 0% | 2 | 2006-05-15
4 | Idle screen | 4_2 | new event dialog (part of Info Prompt) | 2 | 1 | 2 |  | SISL |  |  |  | AppIDC | 0 | 0 | 2 | 2006-05-22
7 | Voice call screens basic | 7_2 | all calls list (call records) | 2 | 1 | 2 |  | SISL |  |  |  | AppPIM | 0 |  | 2 | 2006-05-11
10 | Remove or hide or disable features | 10_3 | MultiMedia removing | 2 | 1 |  | 2 | PEK | Yang Hong Hui |  |  |  | 2 | 100% | 0 | 2006-05-15
|  | 10_7 | DRM (disable) | 4 | 1 |  | 4 | PEK | Song Wen Juan |  |  |  | 2 | 70% | 2 | 2006-05-15
11 | Tips | 11_3 | Verification of integrated animations/bitmaps provided by Vodafone (ShowMe functionality) | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppBase | 0 |  | 2 | 2006-05-22
|  | 11_4 | Implementation of DoIt functionality | 2 | 1 | 2 |  | SISL |  |  |  | AppBase | 1 | 30% | 1 | 2006-05-08
12 | Volume side key, Ringer side key and lock key invocation | 12_4 | Handling of Volume side key in applicaitions such Playing a voice message, listening to voice mail, ring tone volume, message tone volume, alarm | 5 | 1 | 5 |  | SISL |  |  |  |  | 0 |  | 5
13 | Contact list and menu options after pressing Contact hard key | 13_6 | launch external application, e.g. Voice Messaging, SMS, call | 3 | 1 | 3 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 0 | 0 | 3 | 2006-05-22
|  | 13_7 | Contacts settings | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 0 |  | 2 | 2006-05-10
|  | 13_8 | export inteface (insert contact, select contact) to external appl. i.e. messaging, IDC | 2 | 1 |  | 2 | PEK | Lu Qi Wen |  |  |  | 0 | 0 | 2 | 2006-05-24
|  | 13_15 | Frequently used counter of the contact | 6 | 1 |  | 6 | PEK | Lu Qi Wen |  |  |  | 1 | 10% | 5 | 2006-05-24
|  | 13_16 | Call list options | 2 | 1 | 2 |  | SISL |  |  |  | AppPIM | 0 |  | 2 | 2006-05-09
|  | 13_17 | Reminder (birthday, etc.) alerts on UI | 4 | 1 | 4 |  | SISL |  |  |  | AppPIM | 0 |  | 4 | 2006-05-22
|  | 13_18 | Exception hadling for reminders | 2 | 1 | 2 |  | SISL |  |  |  | AppPIM | 0 |  | 2 | 2006-05-22
|  | 13_19 | Error handling for contacts including call records | 2 | 1 | 2 |  | SISL |  |  |  | AppPIM | 0 |  | 2 | 2006-05-16
|  | 13_20 | Delete (All) wizard of Call record | 2 | 1 | 2 |  | SISL | Rajeev |  |  | AppPIM | 0 |  | 2 | 2006-05-22
|  | 13_21 | Detailed View Editor | 2 | 1 | 2 |  | SISL |  |  |  | AppPIM | 0 |  | 2 | 2006-05-15
|  | 13_22 | Options for Detailed View Editor | 2 | 1 | 2 |  | SISL |  |  |  | AppPIM | 0 |  | 2 | 2006-05-22
|  | 13_23 | Delete reminder and Delete all reminders. | 1 | 1 | 1 |  | SISL |  |  |  | AppPIM | 0 |  | 2 | 2006-05-18
17 | Key lock screen after switching the key lock hard key. | 17_1 | implementation of keylock screen | 4 | 1 | 4 |  | SISL | Rajeev |  |  | AppIDC | 1 | 30% | 3 | 2006-05-20
18 | Settings | 18_7 | Settings menu setup | 0.4 | 1 | 0.4 |  | SISL |  |  |  | AppBase | 0.4 | 100% | 0 | 2006-04-10
|  | 18_9 | Voice Mail number | 0.6 | 1 | 0.6 |  | SISL |  |  |  | AppIDC | 0.2 | 40% | 0.4 | 2006-05-01
|  | 18_10 | Call Waiting | 0.6 | 1 | 0.6 |  | SISL |  |  |  | AppIDC | 0 | 0 | 0.6 | 2006-05-04
|  | 18_11 | Call Divert | 1 | 1 | 1 |  | SISL |  |  |  | AppIDC | 0 | 0 | 1 | 2006-05-10
|  | 18_12 | Power saving | 0.6 | 1 | 0.6 |  | SISL |  |  |  | AppBase | 0 |  | 0.6 | 2006-05-04
|  | 18_13 | Area info | 0.6 | 1 | 0.6 |  | SISL |  |  |  | AppBase | 0 |  | 0.6 | 2006-05-04
|  | 18_14 | Master reset | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 0 |  | 1 | 2006-05-04
|  | 18_15 | Vodafone services | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 0 |  | 1 | 2006-05-10
|  | 18_16 | ring tone AE part | 2 | 1 | 2 |  | SISL |  |  |  | AppBase | 0 |  | 2 | 2006-05-16
19 | Contact log | 19_3 | UI implementation in PIM | 4 | 1 | 4 |  | SISL | Rajeev |  |  | AppPIM | 0 |  | 4 | 2006-05-22
|  | 19_4 | call record adaption | 2 | 1 |  | 2 | PEK | Lu Qi Wen |  |  |  | 0 | 0 | 2 | 2006-05-19
|  | 19_5 | adaption in messaging | 2 | 1 | 2 |  | SISL |  |  |  | Messaging | 0 |  | 2 | 2006-05-22
20 | Voice call screens (full functions) | 20_1 | handling different network release codes: 34, 38 44, 17,18 and 21 | 3 | 2 | 6 |  | SISL |  |  |  | AppIDC | 0 |  | 6 | 2006-05-13
|  | 20_4 | handling different network release codes: 28 | 1 | 1 | 1 |  | SISL |  |  |  | AppIDC | 0 |  | 1 | 2006-05-19
|  | 20_2 | call reminder | 4 | 1 | 4 |  | SISL |  | list all alarm events |  | AppIDC | 1 | 25% | 3 | 2006-05-17
|  | 20_3 | in-call menu adaption | 1.5 | 2 | 3 |  | SISL |  |  |  | AppIDC | 0 |  | 3 | 2006-05-17
|  | 20_5 | Prompt for saving the number after the call is ended when it is not already stored in the Contacts. | 2 | 1 | 2 |  | SISL |  |  |  | AppIDC | 0 | 0 | 2 | 2006-05-20
21 | VF Simply Alarm Clock | 21_2 | time/date editor | 2 | 2 | 4 |  | SISL |  |  |  | AppPIM | 0 | 0 | 4 | 2006-05-22
|  | 21_3 | alarm text | 1 | 1 | 1 |  | SISL |  |  |  | AppPIM | 0 |  | 1 | 2006-05-22
22 | Voice messaging | 22_1 | view and editor UI | 7 | 2 | 14 |  | SISL |  |  | depending on resource situation | Messaging | 4 | 25% | 10 | 2006-05-22
|  | 22_2 | send and receive | 2 | 2 | 4 |  | SISL |  |  |  | Messaging | 0 | 0 | 4 | 2006-05-22
|  | 22_3 | Voice Messaging AE | 4 | 1 | 4 |  | SISL |  |  |  | Messaging | 1 | 20% | 3 | 2006-05-18
23 | Picture messaging | 23_1 | Picture messaging | 4 | 2 | 8 |  | SISL |  |  |  | Messaging | 2 | 20% | 6 | 2006-05-22
24 | Message setting | 24_1 | Message setting | 3 | 1 | 3 |  | SISL |  |  |  | Messaging | 2.2 | 70% | 0.8 | 2006-05-04
25 | Inbox UI (all message list) | 25_1 | Inbox UI (list includs MMS and all options w/o options functionality) | 4 | 1 | 4 |  | SISL |  |  |  | Messaging | 1 | 10% | 3 | 2006-05-22
26 | Menu look and feel - full compliance | 26_1 | UIOS full compliance | 3 | 2 |  | 6 | PEK | Zhou Tong |  |  |  | 2 | 20% | 4 | 2006-05-22
28 | Hover functionality in Contact list | 28_1 | UIOS provide this function | 2 | 1 |  | 2 | PEK | Zhou Tong | Idle |  |  | 1 | 50% | 1 | 2006-05-15
32 | MsgAE | 32_1 | Implementation of Incoming list (backend engine) | 3 | 1 | 3 |  | SISL |  |  |  | Messaging
|  | 32_2 | Implementation of Sent list (backend engine) | 3 | 1 | 3 |  | SISL |  |  |  | Messaging
|  | 32_5 | Msg AE - Core (State Machine) | 2 | 2 | 4 |  | SISL |  |  |  | Messaging | 3 | 80% | 1 | 2006-05-04
|  | 32_6 | delete msg and delete all | 4 | 1 | 4 |  | SISL |  |  |  | Messaging
|  | 32_7 | SMS/MMS client updation | 2 | 1 | 2 |  | SISL |  |  |  | Messaging
33 | Templates/Drafts | 33_3 | Full functional templates/drafts | 4 | 1 | 4 |  | SISL |  |  |  | Messaging | 0 | 0% | 4 | 2006-05-18
36 | Text editor | 36_14 | T9 guide | 1 | 1 |  | 1 | PEK | Lu Qi Wen | 0 | 0 |  | 0 | 0 | 1 | 2006-04-21
|  | 36_19 | New text editor widget | 4 | 1 |  | 4 | PEK | Chu Hong Tao |  |  |  | 2 | 50% | 2 | 2006-05-19
|  | 36_20 | Date/time clear functionality | 1 | 1 |  | 1 | PEK | Luo Xu | 0% | 1 |  | 0.5 | 50% | 0.5 | 2006-05-12
38 | Remove lint error | 38_1 | Remove lint error (Beijing) | 3 | 1 |  | 3 | PEK | Zhang Nan |  |  |  | 0.5 | 10% | 2.5 | 2006-05-22
| customization(mapping, FFS) |  |  | 2 | 1 |  | 2 | PEK
| Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 3 | 12 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 1 |  | 4 | PEK
| Preparation for sprint N+1 | [5 empty] | 0 | PEK
[6 empty] | 161.8 | 41
| total effort (MW) |  |  |  |  | 202.8 | [6 empty] | 31.4 |  | 130.4

## Sprint 4
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
BL ID | Backlog Item | WP ID | Workpackage Description | #wks | #rce | Mwk | Mwk | SITE | contact person | Dependency | comment | Component | Effort Spent (MW) | % complete | Remaining Effort (MW) | Expected Finish Date
0 | Preparation | 0_15 | Adaptation of *#06# screens to Idle space | 1 | 1 |  | 1 | PEK |  |  |  | AppBase | 0 |  | 1 | 2006-06-18
4 | Idle screen | 4_5 | TCD-USRX-BAS-008053 Interruption by Events (Partly (nearly not) implemented in X75, needs separate call CSM. (Part 1) Separation of Call functionality from the Idle | 5 | 3 | 15 |  | SISL | Gagan |  |  | AppIDC | 8 | 50% | 7 | 2006-06-18
|  | 4_6 | (Part 2) Call CSM Message Handling | 5 | 3 | 15 |  | SISL | Gagan |  |  | AppIDC | 8 | 50% | 7 | 2006-06-18
|  | 4_7 | (Part 3) Dial Dialog Updation Handling | 4 | 3 | 12 |  | SISL | Gagan |  |  | AppIDC | 4 | 30% | 8 | 2006-06-18
|  | 4_8 | Welcome tour | 1 | 1 | 1 |  | SISL | Gagan |  |  | AppIDC
|  | 4_9 | Charging display adaption | 1 | 1 | 1 |  | SISL | Gagan |  |  | AppIDC
13 | Contact list and menu options after pressing Contact hard key | 13_11 | Delete wizard for Contacts | 4 | 1 | 4 |  | SISL | Sunisha |  |  | AppPIM
|  | 13_10 | duplicates check functionality in PIM-AE | 4 | 2 |  | 8 | PEK | Lu Qi Wen |  |  |  | 0 | 0 | 8 | 2006-06-18
|  | 13_14 | Top3 contacts in the Contacts list | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | AppPIM
21 | VF Simply Alarm Clock | 21_1 | list all alarm events | 4 | 1 | 4 |  | SISL | Sunisha |  |  | AppPIM
|  | 21_4 | alarm tone/volume/vibration | 3 | 2 | 6 |  | SISL | Sunisha |  |  | AppPIM
|  | 21_5 | menu options in alarm clock, i.e. delete, add | 2 | 2 | 4 |  | SISL | Sunisha |  |  | AppPIM
|  | 21_6 | Handling alarm notifications when mobile is switched off | 1 | 1 | 1 |  | SISL | Sunisha |  |  | AppPIM
23 | Picture messaging | 23_2 | Picture message integration with the new text editor | 2 | 1 | 2 |  | SISL | Rajeev Bhatia |  |  | Messaging
26 | Menu look and feel - full compliance | 26_2 | VF menu full compliance | 4 | 2 |  | 8 | PEK | Zhou Tong |  |  |  | 0 | 0 | 8 | 2006-06-18
27 | Sleep mode with timer settings | 27_1 | back to last screen from where the sleep mode was activated | 4 | 2 | 8 |  | SISL | Gagan |  |  | AppIDC |  |  |  | 2006-06-22
|  | 27_2 | screen saver handling in idle | 2 | 1 | 2 |  | SISL | Gagan |  |  | AppIDC
28 | Hover functionality in Contact list | 28_2 | PIM adaption | 2 | 1 | 2 |  | SISL | Sunisha |  |  | AppPIM
|  | 28_3 | messaging adaption | 2 | 1 | 2 |  | SISL | Rajeev Bhatia |  |  | Messaging
29 | Unified Inbox Functionality | 29_1 | Unified Inbox Functionality | 6 | 2 | 12 |  | SISL | Rajeev Bhatia |  |  | Messaging |  |  |  | 2006-06-22
|  | 29_2 | welcome tour handling | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging
30 | Text message (SMS) | 30_1 | view and editor | 3.5 | 2 |  | 7 | PEK |  |  |  |  | 0 | 0 | 7 | 2006-06-16
|  | 30_2 | send and receive | 2 | 2 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging
31 | Idle split screen | 31_1 | Full functional Idle split screen (Info Prompt) | 4 | 1 | 4 |  | SISL | Gagan |  |  | AppIDC
|  | 31_2 | Info list Functionality (MessageAE) | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging
|  | 31_3 | Welcome tour handling (Tips) | 3 | 1 | 3 |  | SISL | Yogesh |  |  | AppBase
32 | MsgAE | 32_3 | sync between msg table in PIM and msg DB in AppMsg | 3 | 2 | 6 |  | SISL | Rajeev Bhatia |  |  | Messaging
34 | Unified sent message | 34_1 | Unified sent message | 3 | 2 | 6 |  | SISL | Rajeev Bhatia |  |  | Messaging
35 | Delete (All) wizard for contact | 35_1 | Delete (All) wizard for contact | 4 | 2 | 8 |  | SISL | Sunisha |  |  | AppPIM
39 | Power Save mode | 39_1 | Power save mode handling | 2 | 1 |  | 2 | PEK |  |  |  |  | 0 | 0 | 2 | 2006-06-09
40 | Voice mail | 40_1 | Voice mail | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging | 0 | 0 | 3 | 2006-06-22
41 | Delete (All) wizard for Message | 41_1 | Delete (All) wizard for Message | 4 | 1 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging
| customization(mapping, FFS) |  |  | 3 | 1 |  | 3 | PEK | Chai Chun Qian
| bugfix for Sprint N-1 |  |  | 4 | 4 | 16 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 2 |  | 8 | PEK
[6 empty] | 152 | 36 | [5 empty] | 20 |  | 51
| total effort (MW) |  |  |  |  | 188
[6 empty] | 508 | 148
| Overall Effort (MW) |  |  |  |  | 656
(30 SISL+12PEK)*4=168 manweeks
how to cover big effort gap:
10% overtime::168+16 - 42 =142MW
20% overtime::5 days+weekend (168 + 16 + 15*3 - 42 = 185 MW)
expected capacity: 170MW