## Change History
Jerry Prioritized Feature cluster
History of Change
Version | Date | Editor | Status | Description
1.0_001 | 2006-02-14 | Huang Qian | in work | First draft created during the requirement and feature list workshop.
1.1_000 | 2006-02-20 | Yang Yong Qiang | in review | refined in workshop. Offline review.
1.1_003 | 2006-03-02 | Yang Yong Qiang Rajeev Chauhan | in review | Rearranged all WPs according to the Sprint. Feature and WP IDs defined. Added 2 WPs for Contacts: delete wizard and duplicate check. Offline review.
1.1_004 | 2006-03-16 | Rajeev Chauhan | in review | Moved (PIM) Contact Log work packages from Sprint 2 to Sprint 3
1.2_001 | 2006-03-16 | Hu Chun Yan | in review | Add 4 text editor WPs and 1 system message WP Offline review
1.2_002 | 2006-03-16 | Hu Chun Yan | in review | Merge the change between 1.1_004 and 1.2_001 offline review
1.2_003 | 2006-03-18 | Hu Chun Yan | in review | Add 10 text editor WPs in sprint2 Add 1 WP (System message) in sprint1 Make the WP ID unique, change WPID from 3_1 to 3_3 in sprint3 Offline review
1.2_004 | 2006-04-07 | Rajeev Chauhan Hu Chun Yan | in review | Moved 19_1 and 19_2 from Sprint 3 to Sprint 2 Moved 14_2 and 14_3 from sprint3 to sprint 2 Moved 28_1 from sprint4 to sprint 3 Added new WP 0_6, 0_7, 0_10, 36_17, 32_8, 36_18 in Sprint 2. Added new WP 0_8, 0_11, 11_3,12_4, 13_15, 38_1, 36_19 in Sprint 3. Added new WP 13_14, 21_6, 39_1, 40_1 in sprint 4 Remove WP 19_5 ( duplicate of 13_8). Remove 36_12 from Sprint 2 because it is covered by 36_4. Split the Setings WP (18) in Sprint 2 into smaller WPs. Responsibility changed from SISL to PEK for Sprint 2 WPs 10_1, 10_2 and 10_4 and Sprint 3 WP 10_3 and 3_3.
1.2_005 | 2006-04-21 | Rajeev Chauhan Hu Chun Yan | in review | Changes are marked in Blue Colour
1.2_006 | 2006-04-30 | Rajeev Chauhan Hu Chun Yan | in review | Changes are marked in Blue Colour
1.2_007 | 2006-05-05 | Rajeev Chauhan | in review | Sprint3 progress of SISL part updated
1.2_008 | 2006-05-08 | Hu Chun Yan | in review | Move 36_14 from sprint3 to sprint4
1.2_009 | 2006-05-11 | Rajeev Chauhan | in review | Update the status for SISL WPs of Sprint 3.
1.2_010 | 2006-05-15 | Hu Chun Yan | in review | Move 13_8 from sprint 3 to sprint 4
1.2_011 | 2006-05-19 | Yang Yong Qiang Rajeev Chauhan | in review | updated ECD. Updated progress of WPs.

## All Features
ID | Feature | Sprint | Timeline | Remark
1 | Start-up/power on dialogs | sprint 1 | 31.03.2006 | Only PIN input in sprint 1, rest by sprint 3
2 | Show Startup Assistant | sprint 3 | 31.05.2006
3 | PC Simu setup | sprint 1 | 31.03.2006
4 | Idle screen | sprint 1 | 31.03.2006 | Only as VF Simply Styleguide (version 1.5, 02.02.2006) page 5 figure 1.Idle, incl all functional scenario, w/o transition, headline, softkeys effect. Rest by sprint 4
5 | Home/Contact/Menu hard key invocation | sprint 1 | 31.03.2006
6 | Phone spaces, color schemes, Icons, Fonts | sprint 1 | 31.03.2006
7 | Voice call screens basic | sprint 1 | 31.03.2006 | Full functions by sprint 3
8 | Headline and soft key look and feel | sprint 1 | 31.03.2006
9 | Menu look and feel basic | sprint 1 | 31.03.2006 | Full compliance by sprint 3
10 | Remove or hide or disable features | sprint 1 | 31.03.2006
11 | Tips | sprint 2 | 28.04.2006
12 | Volume side key, Ringer side key and lock key invocation | sprint 2 | 28.04.2006
13 | Contact list and menu options (without functionality inside) after pressing Contact hard key | sprint 1 | 31.03.2006 | Full functions by sprint 3
14 | Screen transitions | sprint 2 | 28.04.2006 | Only sliding effect. Menu and popup selection transitions by sprint 3.
15 | Unified Inbox (Layout) | sprint 2 | 28.04.2006 | Full functions by sprint 4
16 | Synchronization including remote sync and sync with SIM | sprint 2 | 28.04.2006
17 | Key lock screen after switching the key lock hard key. | sprint 3 | 31.05.2006
18 | Settings | sprint 3 | 31.05.2006 | Ring tong, keypad tone, time/date, display my number, language and change PIN shall be available by sprint 2
19 | Contact log | sprint 2 | 28.04.2006
20 | Voice call screens (full functions) | sprint 3 | 31.05.2006
21 | VF Simply Alarm Clock | sprint 4 | 07.07.2006
22 | Voice messaging | sprint 3 | 31.05.2006
23 | Picture messaging | sprint 3 | 31.05.2006
24 | Message setting | sprint 3 | 31.05.2006
25 | Inbox UI (all message list) | sprint 3 | 31.05.2006
26 | Menu look and feel - full compliance | sprint 3 | 31.05.2006
27 | Sleep mode with timer settings | sprint 4 | 07.07.2006
28 | Hover functionality in Contact list | sprint 4 | 07.07.2006
29 | Unified Inbox Functionality | sprint 4 | 07.07.2006
30 | Text message (SMS) | sprint 4 | 07.07.2006
31 | Idle split screen | sprint 4 | 07.07.2006
32 | MsgAE | sprint 4 | 07.07.2006
33 | Templates/Drafts | sprint 4 | 07.07.2006
34 | Unified sent message | sprint 4 | 07.07.2006
35 | Delete (All) wizard | sprint 4 | 07.07.2006
36 | Text editor | sprint 2 | 28.04.2006
37 | System message | sprint 1 | 31.03.2006
38 | Remove lint errors | sprint 3 | 31.05.2006
39 | Power Save mode | Sprint 4 | 07.07.2006
40 | Voice mail | Sprint 4 | 07.07.2006
41 | Delete (All) wizard for Message | Sprint 4 | 07.07.2006

## Sprint 1
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
BL ID | Backlog Item | WP ID | Workpackage Description | #wks | #rce | Mwk | Mwk | SITE | contact person | Dependency | comment | Effort Spent (MW) | % complete | Expected Finish Date | Actual Finish Date | Deviation (Effort)
0 | Preparation | 0_1 | Identify all text/icon resources and delivery to ResUI team for integration into project database for sprint 1 | 2 | 1 | 2 |  | SISL | Lovleen
|  | 0_3 | Integration of texts/graphics/fonts into project database for sprint 1 | 2 | 1 | 2 |  | SISL | Rajeev |  |  | 3 | 100% | 20-03-06 | 29-03-06 | 1 MW
|  | 0_5 | define Font in UIOS | 1 | 1 |  | 1 | Beijing | Lu Qi Wen | text resources
1 | Start-up/power on dialogs | 1_1 | PIN input, incl. error handling | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | text resources
3 | PC Simu setup | 3_1 | 3 hard keys (Home, Contact, Menu) simu, blinking effect for home key | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | DL
|  | 3_2 | side keys simu | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | DL
4 | Idle screen | 4_1 | Refer to VF Simply Styleguide (version 1.5, 02.02.2006) page 5 figure 1.Idle, incl all functional scenario, w/o transition, headline, softkeys effect | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | text/icon
5 | Home/Contact/Menu hard key invocation | 5_1 | Invocation of native applications on hard keys press, light effect at home space | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | UIOS, DL
6 | Phone spaces, color schemes, Icons, Fonts | 6_1 | color scheme switching interface, define additional virtual colors | 2 | 1 |  | 2 | Beijing | Lu Qi Wen | text resource
|  | 6_2 | text resource to define color scheme | 1 | 1 |  | 1 | Beijing | Wu Ying Yu
|  | 6_3 | phone space color scheme switching (IDC) | 1 | 1 | 1 |  | SISL | Rajeev Chauhan | color scheme switching in UIOS
7 | Voice call screens basic | 7_1 | calling use case: call origination, termination, call setup | 4 | 3 | 12 |  | SISL with Beijing IDC support | Rajeev Chauhan Xu Peng
8 | Headline and soft key look and feel | 8_1 | UIOS | 4 | 3 | 12 |  | SISL | Rajeev
9 | Menu look and feel basic | 9_1 | look and feel w/o transition effects | 4 | 2 |  | 8 | Beijing | Lu Qi Wen
|  | 9_2 | scroll bar | 2 | 1 | 2 |  | SISL | Rajeev Chauhan
10 | Remove or hide or disable features | 10_5 | Java (remove) | 2 | 1 |  | 2 | Beijing
13 | Contact list and menu options after pressing Contact hard key | 13_1 | list address book (without functionality inside) | 2 | 2 | 4 |  | SISL | Rajeev Chauhan
|  | 13_2 | display menu options with some functions, e.g. copy, delete contact (w/o delete wizard), add new contact (w/o new UI) | 3 | 2 | 6 |  | SISL | Rajeev Chauhan
36 | Text editor | 36_1 | undesired deletion of words | 1 | 1 |  | 1 | Beijing | Lu Qi Wen
|  | 36_2 | emotion icons in symbol list | 2 | 1 |  | 2 | Beijing | Lu Qi Wen
|  | 36_3 | 2-way navigation in predictive entry | 1 | 1 |  | 1 | Beijing | Lu Qi Wen
|  | 36_4 | change of entry mode | 2 | 1 |  | 2 | Beijing | Lu Qi Wen
|  | 36_5 | draw line | 1 | 1 |  | 1 | Beijing | Lu Qi Wen
37 | System message | 37_1 | system message | 2 | 1 |  | 2 | Beijing | Lu Qi Wen
| Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
| Preparation for sprint N+1 | [5 empty] | 0 | Beijing
[6 empty] | 77 | 23
| total effort(MW) |  |  |  |  | 100

## Sprint 2
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
BL ID | Backlog Item | WP ID | Workpackage Description | #wks | #rce | Mwk | Mwk | SITE | contact person | Dependency | comment | Component | Effort Spent (MW) | % complete | Remaining Effort (MW) | Expected Finish Date
0 | Preparation | 0_6 | Identify all text/icon resources and delivery to ResUI team for integration into project database for sprint 2 | 2 | 1 | 2 |  | SISL | Lovleen |  |  | MMI_Spec | 2 | 100% | 0 | 2006-04-07
|  | 0_7 | Integration of graphics/fonts into project database for Sprint 2 | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | ResUI | 1 | 100% | 0 | 2006-04-06
|  | 0_9 | Integration of texts into project database for Sprint 2 | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | ResUI | 1 | 100% | 0 | 2006-04-13
|  | 0_13 | Integration of additional fonts/icons | 0.8 | 1 | 0.8 |  | SISL |  |  |  | ResUI | 0.8 | 100% | 0 | 2006-04-20
|  | 0_14 | Integration of updated texts into project database | 0.4 | 1 | 0.4 |  | SISL |  |  |  | ResUI | 4 | 100% | 0 | 2006-04-23
|  | 0_10 | rc file incl. all language and characters | 1 | 1 |  | 1 | PEK | Cao Dong Dong |  |  |  | 0 | 0% | 1 | 2006-04-13
1 | Start-up/power on dialogs | 1_2 | Date and Time settings (covered by 18_3) |  |  |  |  | SISL | Rajeev Chauhan
2 | Show Startup Assistant | 2_1 | (TCD-MESG_SIM-990002) At power on, the device shall check EF_MSISDN on the SIM for the presence of an MSISDN. If the field is blank then the device shall prompt the user to "Enter own number"; details of the UI interaction shall be in accordance with the MMI spec. | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 1.4 | 100% | 0 | 4/6/2006 (4/8/2006)
4 | Idle screen | 4_3 | Idle UI adaption on network selection | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 2 | 100% | 0 | 2006-04-23
|  | 4_4 | show call setting: call barring incoming/outcoming if abroad (new ), effect in Idle | 4 | 1 | 4 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 4 | 100% | 0 | 2006-04-23
|  | 4_10 | Digital clock with big font in idle screen, including smaller font when date is also displayed. | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 2 | 100% | 0 | 2006-04-16
|  | 4_11 | Clock in smaller font when date is also displayed. | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 0 | 100% | 0 | 2006-04-16
10 | Remove or hide or disable features | 10_1 | IrDA, BT (remove) | 2 | 1 |  | 2 | PEK | Zhang Nan |  |  |  | 1.2 | 60% | 0.8 | 2006-04-14
|  | 10_2 | Camera (remove) | 2 | 1 |  | 2 | PEK | Zhang Jing |  |  |  | 0.6 | 30% | 1.4 | 2006-04-21
|  | 10_4 | Browser (hide) | 4 | 1 |  | 4 | PEK | Yang Hong Hui |  |  |  | 2 | 50% | 2 | 2006-04-21
|  | 10_6 | showing UI notification about accessory from connectivity (disable) | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 2 | 100% | 0 | 2006-04-20
11 | Tips | 11_1 | Phone Basics, Contacts, Calls, Manage contents on PC, International | 2 | 2 | 4 |  | SISL | Rajeev Chauhan | UIOS |  | AppBase | 4 | 100% | 0 | 2006-04-23
|  | 11_2 | Messages, Events and Alerts, Settings, Accessories | 2 | 2 | 4 |  | SISL | Rajeev Chauhan |  |  | AppBase | 4 | 100% | 0 | 2006-04-17
12 | Volume side key, Ringer side key and lock key invocation | 12_1 | ringer side key in idle | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppIDC | 2 | 100% | 0 | 2006-04-10
|  | 12_2 | volume side key in In-call | 1 | 1 | 1 |  | SISL | Rajeev |  |  | AppIDC | 1 | 100% | 0 | 2006-04-16
|  | 12_3 | lock key | 1 | 1 | 1 |  | SISL | Rajeev | UIOS | With Beijing PIM team support | AppIDC | 1 | 100% | 0 | 2006-04-20
13 | Contact list and menu options after pressing Contact hard key | 13_3 | contact editor | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | UIOS | With Beijing PIM team support | AppPIM | 4 | 100% | 0 | 2006-04-23
|  | 13_4 | merge entry in SIM to Contact list (Unified Contact w/o duplicate check) | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | list address book | With Beijing PIM team support | AppPIM | 4 | 100% | 0 | 4/20/2006 (21 Apr)
|  | 13_5 | complicated functions: add reminder | 3 | 1 | 3 |  | SISL | Rajeev Chauhan | display menu options | With Beijing PIM team support | AppPIM | 3.4 | 100% | 0 | 4/16/2006 (21 Apr)
|  | 13_9 | call record look and feel | 4 | 2 | 8 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 8 | 100% | 0 | 2006-04-20
|  | 13_12 | complicated functions: sim backup w/o view log | 4 | 1 | 4 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 4 | 100% | 0 | 2006-04-23
|  | 13_13 | complicated functions: Edit Reminder | 1 | 1 | 1 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 1 | 100% | 0 | 2006-04-23
14 | Screen transitions | 14_1 | sliding effect | 4 | 2 |  | 8 | PEK | Yi Xiao Qiang |  |  |  | 7.2 | 90% | 0.8 | 2006-04-14
|  | 14_2 | menu selection transition | 4 | 1 |  | 4 | PEK | Yi Xiao Qiang |  |  |  | 1.6 | 40% | 2.4 | 2006-04-21
|  | 14_3 | popup transition | 4 | 1 |  | 4 | PEK | Luo Xu |  |  |  | 1.6 | 40% | 2.4 | 2006-04-21
15 | Unified Inbox (Layout) | 15_1 | Jerry look and feel of Unified Inbox in SGL functionality w/o MMS | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | could start in parallel beginning of Mar |  | Messaging | 2 | 100% | 0 | 2006-04-13
16 | Synchronization including remote sync and sync with SIM | 16_1 | SyncML UI screens | 2 | 2 | 4 |  | SISL | Rajeev Chauhan | could start in parallel beginning of Mar |  | SyncML | 3.4 | 100% | 0 | 2006-04-23
|  | 16_2 | Startup dialog UI | 0.4 | 1 | 0.4 |  | SISL | Rajeev Chauhan |  |  | SyncML | 0.4 | 100% | 0 | 2006-04-10
|  | 16_3 | Data updations at server and SIM - UI | 1.8 | 2 | 3.6 |  | SISL | Rajeev Chauhan |  |  | SyncML | 4 | 100% | 0 | 2006-04-23
|  | 16_4 | Data retrieval - address book and phone book - AE | 2 | 2 | 4 |  | SISL | Rajeev |  |  | SyncML | 4 | 100% | 0 | 2006-04-23
|  | 16_5 | Data syncronization - AE | 2.5 | 2 | 5 |  | SISL | Rajeev |  |  | SyncML | 5 | 100% | 0 | 2006-04-23
|  | 16_6 | server data updation - AE | 1 | 1 | 1 |  | SISL | Rajeev |  |  | SyncML | 1 | 100% | 0 | 2006-04-23
18 | Settings | 18_1 | ring tone UI part | 1 | 1 | 1 |  | SISL | Rajeev |  |  | AppBase | 1 | 100% | 0 | 2006-04-13
|  | 18_2 | keypad tone | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 1 | 100% | 0 | 2006-04-06
|  | 18_3 | time & date | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 1.4 | 100% | 0 | 4/20/2006 (22 Apr)
|  | 18_4 | display my number | 1 | 1 | 1 |  | SISL | Rajeev |  |  | AppBase | 1 | 100% | 0 | 2006-04-20
|  | 18_5 | phone language | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 1 | 100% | 0 | 2006-04-13
|  | 18_6 | change PIN | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 1.4 | 100% | 0 | 4/6/2006 (08 Apr)
19 | Contact log | 19_1 | new msg info table support in PIM AE | 4 | 2 | 8 |  | SISL | Rajeev |  |  | AppPIM | 8.2 | 100% | 0 | 4/20/2006 (21 Apr)
|  | 19_2 | sorting mechanism | 4 | 1 | 4 |  | SISL | Rajeev |  |  | AppPIM | 4 | 100% | 0 | 2006-04-23
26 | Menu look and feel - full compliance | 26_3 | icon highlight switching | 3 | 1 |  | 3 | PEK | Zhou Tong |  |  |  | 1.5 | 50% | 1.5 | 2006-04-14
32 | MsgAE | 32_8 | Detailed design | 2 | 1 | 2 |  | SISL |  |  |  | Messaging | 2 | 100 | 0 | 2006-03-31
33 | Templates/Drafts | 33_1 | Implementation of Templates/Drafts support in AE | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | Messaging | 2 | 100% | 0 | 2006-04-23
|  | 33_2 | Templates/draft list visible, with Options menu (without functionality) | 2 | 1 | 2 |  | SISL |  |  |  | Messaging | 2 | 100% | 0 | 2006-04-20
36 | Text editor | 36_6 | tool tip | 1 | 1 |  | 1 | PEK | Luo Xu | 1 | 100% |  | 1 | 100% | 0 | 2006-04-06
|  | 36_7 | toggling through the candidates in predictive text entry | 4 | 1 |  | 4 | PEK | Luo Xu | 4 | 100% |  | 4 | 100% | 0 | 2006-04-06
|  | 36_8 | dynamic reordering of the candidates list | 2 | 1 |  | 2 | PEK | Song Wen Juan | 1 | 50% |  | 1 | 50% | 1 | 2006-04-14
|  | 36_10 | special characters | 1 | 1 |  | 1 | PEK | Zhang Jing | 0.4 | 100% |  | 0.4 | 100% | 0 | 2006-03-28
|  | 36_11 | cursor flashing in predictive entry | 1 | 1 |  | 1 | PEK | Zhang Jing | 1 | 100% |  | 1 | 100% | 0 | 2006-04-03
|  | 36_12 | Support for Multiple Language Character Sets | 2 | 1 |  | 2 | PEK | Song Wen Juan | 1.4 | 70% |  | 1.4 | 70% | 0.6 | 2006-04-14
|  | 36_13 | 0/1 key symbol list in multitap/singletap | 1 | 1 |  | 1 | PEK | Cao Dong Dong | 1 | 100% |  | 1 | 100% | 0 | 2006-04-04
|  | 36_16 | clear softkey label/add space after interrogation symbol | 1 | 1 |  | 1 | PEK | Zhang Nan | 1 | 100% |  | 1 | 100% | 0 | 2006-04-03
|  | 36_17 | Transition adaption in T9 word choice list | 0.5 | 1 |  | 0.5 | PEK | Luo Xu | 0 | 0% |  | 0 | 0% | 1 | 2006-04-21
|  | 36_18 | Transition adaption in tool tip | 0.5 | 1 |  | 0.5 | PEK | Luo Xu | 0 | 0% |  | 0 | 0% | 1 | 2006-04-21
| customization(mapping, FFS) |  |  | 2 | 1 |  | 2 | PEK
| Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 2 | 8 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 1 |  | 4 | PEK
| Preparation for sprint N+1 | [5 empty] | 0 | PEK
[6 empty] | 115.2 | 48
| total effort(MW) |  |  |  |  | 163.2 | [6 empty] | 127.9 |  | 15.9
Note on D39: ic000637: Dependant on APO implementation of phone book data retrieval

## Sprint 3
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
BL ID | Backlog Item | WP ID | Workpackage Description | #wks | #rce | Mwk | Mwk | SITE | contact person | Dependency | comment | Component | Effort Spent (MW) | % complete | Remaining Effort (MW) | Expected Finish Date
0 | Preparation | 0_2 | Identify all text/icon resources and delivery to ResUI team for integration into project database (cover all sprints) | 2 | 1 | 2 |  | SISL | Lovleen |  |  | MMI_Spec | 2 | 100% | 0 | 2006-04-25
|  | 0_4 | Integration of graphics/fonts into project database for Sprint 3 | 1 | 1 | 1 |  | SISL | Rajeev |  |  | ResUI | 1 | 100% | 0 | 2006-05-02
|  | 0_12 | Integration of texts into project database for Sprint 3 | 1 | 1 | 1 |  | SISL | Rajeev |  |  | ResUI | 0.8 | 100% | 0 | 5/6/2006 (5 May)
|  | 0_8 | Integration of Tips animations/bitmaps provided by VF | 2 | 1 | 2 |  | SISL | Rajeev |  |  | ResUI | 1 | 100% | 0 | 2006-05-18
|  | 0_11 | Infineon change PS of voice mail |  |  |  |  | Infineion
2 | Show Startup Assistant | 2_2 | invoke SyncML and Sync between SIM and phone | 1 | 1 | 1 |  | SISL | Gagan |  |  | AppIDC | 1 | 100% | 0 | 2006-04-23
3 | PC Simu setup | 3_3 | Changes in C_MobSIM for removing/disabling/hiding features | 2 | 1 |  | 2 | PEK | Zhang Jing |  |  |  | 2 | 100% | 0 | 2006-05-15
4 | Idle screen | 4_2 | new event dialog (part of Info Prompt) | 2 | 1 | 2 |  | SISL |  |  |  | AppIDC | 0.8 | 30% | 1.2 | 2006-05-25
7 | Voice call screens basic | 7_2 | all calls list (call records) | 2 | 1 | 2 |  | SISL |  |  |  | AppPIM | 2 | 100% | 0 | 2006-05-11
10 | Remove or hide or disable features | 10_3 | MultiMedia removing | 2 | 1 |  | 2 | PEK | Yang Hong Hui |  |  |  | 2 | 100% | 0 | 2006-05-15
|  | 10_7 | DRM (disable) | 4 | 1 |  | 4 | PEK | Song Wen Juan |  |  |  | 4 | 100% | 0 | 2006-05-15
11 | Tips | 11_3 | Verification of integrated animations/bitmaps provided by Vodafone (ShowMe functionality) | 2 | 1 | 2 |  | SISL | Yogesh |  |  | AppBase | 1.4 | 80% | 0.6 | 2006-05-22
|  | 11_4 | Implementation of Do It functionality | 2 | 1 | 2 |  | SISL | Yogesh |  |  | AppBase | 2 | 100% | 0 | 2006-05-08
12 | Volume side key, Ringer side key and lock key invocation | 12_4 | Handling of Volume side key in applicaitions such Playing a voice message, listening to voice mail, ring tone volume, message tone volume, alarm | 5 | 1 | 5 |  | SISL | Yogesh |  |  | AppBase | 3 | 60% | 2 | 2006-05-22
13 | Contact list and menu options after pressing Contact hard key | 13_6 | launch external application, e.g. Voice Messaging, SMS, call | 3 | 1 | 3 |  | SISL | Sunisha |  |  | AppPIM | 1.8 | 95% | 1.2 | 5/22/2006 (18 May)
|  | 13_7 | Contacts settings | 2 | 1 | 2 |  | SISL | Rajeev Chauhan |  |  | AppPIM | 2 | 100% | 0 | 2006-05-10
|  | 13_15 | Frequently used counter of the contact | 6 | 1 |  | 6 | PEK | Lu Qi Wen |  |  | AppPIM | 6 | 100% | 0 | 2006-05-22
|  | 13_16 | Call list options | 2 | 1 | 2 |  | SISL | Sunisha |  |  | AppPIM | 1.8 | 100% | 0 | 5/9/2006 (18 May)
|  | 13_17 | Reminder (birthday, etc.) alerts on UI | 4 | 1 | 4 |  | SISL | Sunisha |  |  | AppPIM | 4 | 60% | 1 | 5/22/2006 (26 May)
|  | 13_18 | Exception handling for reminders (depending on 13-17) | 2 | 1 | 2 |  | SISL | Sunisha |  |  | AppPIM | 2 | 80% | 0.4 | 2006-05-22
|  | 13_19 | Error handling for contacts including call records | 2 | 1 | 2 |  | SISL | Sunisha |  |  | AppPIM | 2 | 100% | 0 | 2006-05-16
|  | 13_20 | Delete (All) wizard of Call record | 2 | 1 | 2 |  | SISL | Sunisha |  |  | AppPIM | 2 | 100% | 0 | 5/22/2006 (10 May)
|  | 13_21 | Detailed View Editor | 2 | 1 | 2 |  | SISL | Sunisha |  |  | AppPIM | 2 | 100% | 0 | 2006-05-15
|  | 13_22 | Options for Detailed View Editor | 2 | 1 | 2 |  | SISL | Sunisha |  |  | AppPIM | 1.2 | 80% | 0.8 | 2006-05-22
|  | 13_23 | Delete reminder and Delete all reminders. | 1 | 1 | 1 |  | SISL | Sunisha |  |  | AppPIM | 1 | 80% | 0.2 | 5/18/2006 (20 May)
17 | Key lock screen after switching the key lock hard key. | 17_1 | implementation of keylock screen | 4 | 1 | 4 |  | SISL | Gagan |  |  | AppIDC | 3.4 | 100% | 0 | 5/20/2006 (17 May)
18 | Settings | 18_7 | Settings menu setup | 0.4 | 1 | 0.4 |  | SISL |  |  |  | AppBase | 0.4 | 100% | 0 | 2006-04-10
|  | 18_9 | Voice Mail number | 0.6 | 1 | 0.6 |  | SISL | Gagan |  |  | AppIDC | 0.6 | 100% | 0 | 5/1/2006 (5-May)
|  | 18_10 | Call Waiting | 0.6 | 1 | 0.6 |  | SISL | Gagan |  |  | AppIDC | 0.8 | 100% | 0 | 5/4/2006 (11-May)
|  | 18_11 | Call Divert | 1 | 1 | 1 |  | SISL | Gagan |  |  | AppIDC | 1 | 100% | 0 | 5/10/2006 (11 May)
|  | 18_12 | Power saving | 0.6 | 1 | 0.6 |  | SISL |  |  |  | AppBase | 0.4 | 100% | 0 | 5/4/2006 (09 May)
|  | 18_13 | Area info | 0.6 | 1 | 0.6 |  | SISL |  |  |  | AppBase | 0.8 | 100% | 0 | 5/4/2006 (09 May)
|  | 18_14 | Master reset | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 0.2 | 20% | 0.8 | 2006-05-23
|  | 18_15 | Vodafone services | 1 | 1 | 1 |  | SISL |  |  |  | AppBase | 0.6 | 100% | 0 | 5/10/2006 (11 May)
|  | 18_16 | ring tone AE part | 2 | 1 | 2 |  | SISL |  |  |  | AppBase | 2 | 100% | 0 | 2006-05-16
19 | Contact log | 19_3 | UI implementation in PIM | 4 | 1 | 4 |  | SISL | Sunisha |  |  | AppPIM | 3 | 75% | 1 | 2006-05-22
|  | 19_4 | call record adaption(testing) | 2 | 1 |  | 2 | PEK | Lu Qi Wen |  |  | AppPIM | 1.5 | 75% | 0.5 | 2006-05-22
|  | 19_5 | adaption in messaging | 2 | 1 | 2 |  | SISL | Rajeev Bhatia |  |  | Messaging | 1.2 | 60% | 0.8 | 2006-05-22
20 | Voice call screens (full functions) | 20_1 | handling different network release codes: 34, 38 44, 17,18 and 21 | 3 | 2 | 6 |  | SISL |  |  |  | AppIDC | 5 | 100% | 0 | 2006-05-13
|  | 20_4 | handling different network release codes: 28 | 1 | 1 | 1 |  | SISL |  |  |  | AppIDC | 0.4 | 70% | 0.6 | 5/19/2006 (22 May)
|  | 20_2 | call reminder | 4 | 1 | 4 |  | SISL |  | list all alarm events |  | AppIDC | 3.6 | 100% | 0 | 5/17/2006 (15 May)
|  | 20_3 | in-call menu adaption | 1.5 | 2 | 3 |  | SISL |  |  |  | AppIDC | 2.4 | 100% | 0 | 5/17/2006 (15 May)
|  | 20_5 | Prompt for saving the number after the call is ended when it is not already stored in the Contacts. | 2 | 1 | 2 |  | SISL |  |  |  | AppIDC | 1 | 100% | 0 | 5/20/2006 (11 May)
21 | VF Simply Alarm Clock | 21_2 | time/date editor | 2 | 2 | 4 |  | SISL |  |  |  | AppPIM | 3.6 | 80% | 0.4 | 2006-05-22
|  | 21_3 | alarm text | 1 | 1 | 1 |  | SISL |  |  |  | AppPIM | 0.6 | 70% | 0.4 | 2006-05-22
22 | Voice messaging | 22_1 | view and editor UI | 7 | 2 | 14 |  | SISL | Rajeev Bhatia |  | depending on resource situation | Messaging | 11 | 75% | 3 | 2006-05-22
|  | 22_2 | send and receive | 2 | 2 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging | 2.4 | 60% | 1.6 | 2006-05-22
|  | 22_3 | Voice Messaging AE | 4 | 1 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging | 3 | 70% | 2 | 5/18/2006 (31 May)
23 | Picture messaging | 23_1 | Picture messaging | 4 | 2 | 8 |  | SISL | Rajeev Bhatia |  |  | Messaging | 6 | 70% | 2 | 5/22/2006 (31 May)
24 | Message setting | 24_1 | Message setting | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging | 3.6 | 100% | 0 | 5/4/2006 (08-May)
25 | Inbox UI (all message list) | 25_1 | Inbox UI (list includs MMS and all options w/o options functionality) | 4 | 1 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging | 3.6 | 90% | 0.4 | 2006-05-22
26 | Menu look and feel - full compliance | 26_1 | UIOS full compliance | 3 | 2 |  | 6 | PEK | Zhou Tong |  |  | UIOS | 6 | 100% | 0 | 2006-05-22
28 | Hover functionality in Contact list | 28_1 | UIOS provide this function | 2 | 1 |  | 2 | PEK | Zhou Tong | Idle |  | UIOS | 2 | 100% | 0 | 2006-05-15
32 | MsgAE | 32_1 | Implementation of Incoming list (backend engine) | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging | 2.8 | 100% | 0 | 2006-05-11
|  | 32_2 | Implementation of Sent list (backend engine) | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging | 2.6 | 100% | 0 | 2006-05-17
|  | 32_5 | Msg AE - Core (State Machine) | 2 | 2 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging | 4 | 100% | 0 | 2006-05-04
|  | 32_6 | delete msg and delete all | 4 | 1 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging | 3 | 70% | 1 | 2006-05-22
|  | 32_7 | SMS/MMS client updation | 2 | 1 | 2 |  | SISL | Rajeev Bhatia |  |  | Messaging | 1.4 | 70% | 0.6 | 2006-05-22
33 | Templates/Drafts | 33_3 | Full functional templates/drafts | 4 | 1 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging | 4 | 90% | 1 | 2006-05-18
36 | Text editor | 36_19 | New text editor widget | 4 | 1 |  | 4 | PEK | Chu Hong Tao |  |  | UIOS | 4 | 100% | 0 | 2006-05-19
|  | 36_20 | Date/time clear functionality | 1 | 1 |  | 1 | PEK | Luo Xu | 0% | 1 | UIOS | 1 | 100% | 0 | 2006-05-12
38 | Remove lint error | 38_1 | Remove lint error (Beijing) | 3 | 1 |  | 3 | PEK | Zhang Nan |  |  |  | 3 | 100% | 0 | 2006-05-22
| customization(mapping, FFS) |  |  | 2 | 1 |  | 2 | PEK
| Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 3 | 12 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 1 |  | 4 | PEK
| Preparation for sprint N+1 | [5 empty] | 0 | PEK
[6 empty] | 161.8 | 38
| total effort (MW) |  |  |  |  | 199.8 | [6 empty] | 144.7 |  | 23.5
Note on Q8: 19 May: Due to changes in Tips texts after the VF review, there is a need to split them again into smaller parts so that each part fits completely on one single display (without scroll bar). We might be able to deliver the new texts by 27 May.
Note on Q12: 19 May: Depends upon the availability of working interfaces from UIOS; integration and testing afterwards. Might get delayed!
Note on Q16: 19 May: After the animation playback is complete, Replay function is currently not defined in MMI spec. Would require 1 MW of effort.
Note on Q17: 11 May: Some missing interfaces are still to be called.
Note on Q18: 19 May: Base code has been modified and tested. However, it has not been tested for Alarms and voice messages.
Note on Q19: 19 May: Integration for Messaging is still pending, expected to complete on 22 May. Some rework is expected after suggestions on a better solution from Beijing experts.
Note on Q20: 11 May: Anuj was travelling from Beijing and the status will be updated on 12 May. sound AE is open.
Note on Q22: 05 May: Dependency on other components: AppIDC, AppMsg. So this might be delayed. 10 May: To be finished by 22- May. In the mean while, WP 13_20 was finished.
Note on Q23: 11 May: Reminder alerts not showing in PC Simu (even in the very first PC Simu based on Aries). Clarifications on going with PIM experts in Beijing. In the mean time, adaptations have been done for the changed requirements for reminders such as Add Birthday. 19.05: Doesn't work on target even with the new BL. DL is tracking the RTC. 19 May: partly checked-in today. Expected to complete by 26 May provided it works in PC Simu.
Note on Q24: yangyq: Might have to shifted to Sprint 4 19 May: we might be able to finish it in Sprint 3.
Note on Q27: 11 May: Support for UCS2 bitmap is required from UIOS. 12 May: delivered to Rajeev again.
Note on Q28: 19 May: Mostly complete. Some crash is currently being investigated.
Note on Q30: 11 May: WP 20_5 finished earlier.
Note on Q32: 04-May: Delay due to investigation of startup animation problem
Note on Q33: 05 May: Effort spent on Call divert in parallel.
Note on Q35: 04 May: Effort spent for Time setting due to new spec.
Note on Q36: 04 May: Effort spent for Time setting due to new spec.
Note on Q37: 05 May: Only the UI part is complete. Clarifications are on going with VF about the features to be included in Master Reset. 19 May: Work has been started on this WP.
Note on Q40: 11 May: Lots of dependencies to Messaging and integration effort. Might get delayed by a day or so.
Note on Q44: 19 May: Complete from functionality point of view. Some text ids are still missing (not yet integrated) and expected to be complete on 22 May.
Note on Q46: yangyq: No specific task to it.
Note on Q50: 19 May: Functionally working, complete complaince to look and feel expected to be completed later (1st week of June).
Note on Q51: 19 May: Functionally working, complete complaince to look and feel expected to be completed later (1st week of June).
Note on Q52: 19 May: Partly done. More Effort in integration with Picture messages.
Note on Q53: 19 May: Forward/Receive/View is working fine. Some UI specific issues to be resolved.
Note on Q58: 11 May: partly checked-in. 19 May: completed
Note on Q59: 11 May: partly checked-in. 19 May: Complete
Note on Q63: 11 May: The requirements for templates have been changed (text id based) and so some extra effort. The 'delete template' functionality will be delivered later, by 24th May. 19 May: Except 'delete template', rest is complete.

## Sprint 4
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
BL ID | Backlog Item | WP ID | Workpackage Description | #wks | #rce | Mwk | Mwk | SITE | contact person | Dependency | comment | Component | Effort Spent (MW) | % complete | Remaining Effort (MW) | Expected Finish Date
0 | Preparation | 0_15 | Adaptation of *#06# screens to Idle space | 1 | 1 |  | 1 | PEK |  |  |  | AppBase | 0 |  | 1 | 2006-06-18
4 | Idle screen | 4_5 | TCD-USRX-BAS-008053 Interruption by Events (Partly (nearly not) implemented in X75, needs separate call CSM. (Part 1) Separation of Call functionality from the Idle | 5 | 3 | 15 |  | SISL | Gagan |  |  | AppIDC | 8 | 50% | 7 | 2006-06-18
|  | 4_6 | (Part 2) Call CSM Message Handling | 5 | 3 | 15 |  | SISL | Gagan |  |  | AppIDC | 8 | 50% | 7 | 2006-06-18
|  | 4_7 | (Part 3) Dial Dialog Updation Handling | 4 | 3 | 12 |  | SISL | Gagan |  |  | AppIDC | 4 | 30% | 8 | 2006-06-18
|  | 4_8 | Welcome tour | 1 | 1 | 1 |  | SISL | Gagan |  |  | AppIDC
|  | 4_9 | Charging display adaption | 1 | 1 | 1 |  | SISL | Gagan |  |  | AppIDC
13 | Contact list and menu options after pressing Contact hard key | 13_8 | export inteface (insert contact, select contact) to external appl. i.e. messaging, IDC | 2 | 1 |  | 2 | SISL | Sunisha |  |  | AppPIM | 0 | 0 | 2 | 2006-06-02
|  | 13_11 | Delete wizard for Contacts | 4 | 1 | 4 |  | SISL | Sunisha |  |  | AppPIM
|  | 13_10 | duplicates check functionality in PIM-AE | 4 | 2 |  | 8 | PEK | Lu Qi Wen |  |  |  | 0 | 0 | 8 | 2006-06-18
|  | 13_14 | Top3 contacts in the Contacts list | 1 | 1 | 1 |  | SISL | Sunisha |  |  | AppPIM
21 | VF Simply Alarm Clock | 21_1 | list all alarm events | 4 | 1 | 4 |  | SISL | Sunisha |  |  | AppPIM
|  | 21_4 | alarm tone/volume/vibration | 3 | 2 | 6 |  | SISL | Sunisha |  |  | AppPIM
|  | 21_5 | menu options in alarm clock, i.e. delete, add | 2 | 2 | 4 |  | SISL | Sunisha |  |  | AppPIM
|  | 21_6 | Handling alarm notifications when mobile is switched off | 1 | 1 | 1 |  | SISL | Sunisha |  |  | AppPIM
23 | Picture messaging | 23_2 | Picture message integration with the new text editor | 2 | 1 | 2 |  | SISL | Rajeev Bhatia |  |  | Messaging
26 | Menu look and feel - full compliance | 26_2 | VF menu full compliance | 4 | 2 |  | 8 | PEK | Zhou Tong |  |  |  | 0 | 0 | 8 | 2006-06-18
27 | Sleep mode with timer settings | 27_1 | back to last screen from where the sleep mode was activated | 4 | 2 | 8 |  | SISL | Gagan |  |  | AppIDC |  |  |  | 2006-06-22
|  | 27_2 | screen saver handling in idle | 2 | 1 | 2 |  | SISL | Gagan |  |  | AppIDC
28 | Hover functionality in Contact list | 28_2 | PIM adaption | 2 | 1 | 2 |  | SISL | Sunisha |  |  | AppPIM
|  | 28_3 | messaging adaption | 2 | 1 | 2 |  | SISL | Rajeev Bhatia |  |  | Messaging
29 | Unified Inbox Functionality | 29_1 | Unified Inbox Functionality | 6 | 2 | 12 |  | SISL | Rajeev Bhatia |  |  | Messaging | 1.4 | 10% | 10 | 2006-06-22
|  | 29_2 | welcome tour handling | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging
30 | Text message (SMS) | 30_1 | view and editor | 3.5 | 2 |  | 7 | PEK |  |  |  |  | 0 | 0 | 7 | 2006-06-16
|  | 30_2 | send and receive | 2 | 2 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging
31 | Idle split screen | 31_1 | Full functional Idle split screen (Info Prompt) | 4 | 1 | 4 |  | SISL | Gagan |  |  | AppIDC
|  | 31_2 | Info list Functionality (MessageAE) | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging
|  | 31_3 | Welcome tour handling (Tips) | 3 | 1 | 3 |  | SISL | Yogesh |  |  | AppBase
32 | MsgAE | 32_3 | sync between msg table in PIM and msg DB in AppMsg | 3 | 2 | 6 |  | SISL | Rajeev Bhatia |  |  | Messaging
34 | Unified sent message | 34_1 | Unified sent message | 3 | 2 | 6 |  | SISL | Rajeev Bhatia |  |  | Messaging
35 | Delete (All) wizard for contact | 35_1 | Delete (All) wizard for contact | 4 | 2 | 8 |  | SISL | Sunisha |  |  | AppPIM
36 | Text editor | 36_14 | T9 guide | 1 | 1 |  | 1 | PEK | Luo Xu | 0 | 0 |  | 0 | 0 | 1 | 2006-06-09
39 | Power Save mode | 39_1 | Power save mode handling | 2 | 1 |  | 2 | PEK |  |  |  |  | 0 | 0 | 2 | 2006-06-09
40 | Voice mail | 40_1 | Voice mail | 3 | 1 | 3 |  | SISL | Rajeev Bhatia |  |  | Messaging | 0 | 0 | 3 | 2006-06-22
41 | Delete (All) wizard for Message | 41_1 | Delete (All) wizard for Message | 4 | 1 | 4 |  | SISL | Rajeev Bhatia |  |  | Messaging
| customization(mapping, FFS) |  |  | 3 | 1 |  | 3 | PEK | Chai Chun Qian
| bugfix for Sprint N-1 |  |  | 4 | 4 | 16 |  | SISL
| bugfix for Sprint N-1 |  |  | 4 | 2 |  | 8 | PEK
[6 empty] | 152 | 39 | [5 empty] | 21.4 |  | 64
| total effort (MW) |  |  |  |  | 191
[6 empty] | 506 | 148
| Overall Effort (MW) |  |  |  |  | 654
(30 SISL+12PEK)*4=168 manweeks
how to cover big effort gap:
10% overtime::168+16 - 42 =142MW
20% overtime::5 days+weekend (168 + 16 + 15*3 - 42 = 185 MW)
expected capacity: 170MW
Note on Q11: yyq: switched back to SISL on 12 May. One part will be done in Sprint 3 and the other one in Sprint 4. Rajeev will input details of WP breakdown.