## Slide 1: STATUS REPORT 30.03.05 BenQ Jerry VS x
Key Points
1/ Software development:
Sprint 1 planning has been finalized as was tested by System Test this week; test results positive – will be presented to Vf on Tuesday, 4th April 06
2/ HW development:
Testing of A1 PCB has been finalized, minor changes are necessary for A1+ PCB
3/ ID / Mechanics:
Final Mock-up will be provided to Vodafone on Tuesday, 04th April 06
4/ Project schedule:
Slight changes of UG timeline due to availability of Text Database
5/ UE / UI
UE part in TCD has been finalized
some icons for UI development missing from Vf
Decisions Required from Vodafone/Short term Actions
Project plan
Commercial agreements
Resources
Supply chain
Mechanics & Cosmetics
Electronic board
Content developer support
Packaging/ User Manual
Overall
Industrialisation
Software development
Accessories
On Critical path / launch endangered
Urgent actions and decisions required
Not according to plan /might endanger the
Launch; Countermeasures have been defined
On track
Notes: <number>
<footer>
<header>
<date/time>

## Slide 2
Area | Status | Planned progress achieved | Current issues & Further steps
Project plan & TPD/TCD |  | Project plan TCD | Current MPP version: Final_BenQ_Jerry_V1.0 Version 1.1 will be uploaded on Friday, 31.03.06 UG timeline changed due to availability of Text database TCD provided 06.03. Feedback cycle 4 ongoing, still 11 items open, current showstopper: easy voicemail notification Targeted finalization date: 31st March 06
Commercial agreements |  | Contract OpCo list | Negotiations of contract between BenQ GAM /Legal services and Vf ongoing Agreement on IPR portion is reached, project schedule discussion pending finalization on 4th April 06 Targeted finalization date: 31st March 06 Mock-up is currently shown to Vf OpCo’s OpCo Interest in product is captured in a preliminery OpCo participation list by BenQ and Vf
STATUS REPORT BenQ Jerry VS x

## Slide 3
Area | Status | Planned progress achieved | Current issues & Further steps
Supply chain |  | Production site Production capacity | Shanghai BenQ volume planning for Ramp up: 15.10.06* 15k 5 OpCo’s 15.11.06* 60k 10 OpCo’s 15.12.06* 60k 12 OpCo’s 15.01.07* 15k 12-14 OpCo’s *available in OpCo stock
Mechanics & Cosmetics |  | Branding Partner Branding Material selection Colour selection Rendering/ Mock up Mechanical detailing | Finalized (position is approved, wrong logo used on the latest rendering) Proposal available, Project Team checking MOQ at the moment Softtouch: Abbrasion test failed Samples available to Vodafone on 4th April BenQ recommendation to go for pure plastic with mat finish Softtouch keypad: Touch and feel sample will be available Beg of May Colour chip for silver front housing will be provided on Tuesday, 4th April New rendering has been provided to Vf on 24.03.06 but without delta description to previous rendering Adjusted rendering will be delivered on 30th March 06 1 final Mock up available on 31.03.06 on-going Suppliers selected PCB outline and stack-up fixed for A1+
STATUS REPORT BenQ Jerry VS x

## Slide 4
Area | Status | Planned progress achieved | Current issues & Further steps
Resources |  |  | All resources in place
Hardware/ Electronic board |  | Tape out / Testing | Testing of A1 PCB has been performed No major RF issues have been found (Minor adjustments of power ramps needed is SW) Minor corrections found in BB that are being revised for A1+ PCB (Display connector error, Leakage current to 1 keypad LCD, noise issue in PMU area) A1+ PCB will be sent to supplier on 03.04.06 (1 working day delay, no impact on schedule) Antenna measurements/trails on-going in order to align final antenna design with mechanical design
STATUS REPORT BenQ Jerry VS x

## Slide 5
Area | Status | Open issues | Description/ Further steps
Software development |  | Sprint 1 development | Sprint 1 planning integration is done (all workpackages are implemented, SW is working on target and PC simulator) ST is testing Sprint 1. Results will be presented to Vf on Tuesday Workshop held this week in order to discuss possible schedule improvements On Tuesday a PC simulator and modified Aries phone with Jerry Sprint 1 Software will be shown Sprint 2 planning/ specification is on track Implemeted Features in Sprint 1: Start-up/power on dialogs, PC Simu setup, Idle screen, Home/Contact/Menu hard key invocation, Phone spaces, color schemes, Icons, Fonts, Voice call screens basic,Headline and soft key look and feel, Menu look and feel basic, Remove or hide or disable features, Contact list and menu options after pressing Contact hard key, Removing java, Text editor, System Message
STATUS REPORT BenQ Jerry VS x

## Slide 6
Area | Status | Planned progress achieved | Current issues & Further steps
Accessories |  | In box bundle | Headset and desktop stand will be bundled Accessory portfolio available
Content Development |  | Start up / Shut down/ Ringtone | Vodafone has provided Start up / Shut down animation on 27th March 06 Content for selection by Vodafone will be provided by Beg of May
STATUS REPORT BenQ Jerry VS x

## Slide 7
Area | Status | Planned progress achieved | Current issues & Further steps
Packaging User Manuals Dummies |  | Packaging UG QSG Dummies | Packaging dimension/ cutter guide will be provided to Vodafone in CW 13 Discussions about dimensions not finalized yet New date for Cutter Guide delivery will be communicated to Vf Kick-off Meeting successfully conducted Specification requested from Vodafone Required Dummy quantity is collected by BenQ to start e-bidding with suppliers
Sample distribution |  | Sample planning | Sample repository sheet provided by Vf has been used for sample planning Currently 620 samples have been planned for Vf global and OpCo’s
STATUS REPORT BenQ Jerry VS x

## Slide 8
TCD(UE part) / UE Spec finalized 15.03.2006
TG2 27.03.2006
Pre Acceptance Testing finished 21.07.2006
Acceptance Samples 04.08.2006
Start Phase A 07.08.2006
English User Guide approved postponed to 10.07.2006
Packaging, UG/ QSG cover approved 25.05.2006
Lenticular sign off 13.06.2006
Start Phase B 04.09.2006
Start Phase C 02.10.2006
Factory Pre-delivery Inspection completed 12.10.2006
First shipment ex BenQ 13.10.2006
STATUS REPORT BenQ Jerry VS x Major Project Milestones
Notes: <number>
<footer>
<header>
<date/time>