## Project_Account_Opening
After Approval | [5 empty] | Editor (Project Manager): | [5 empty] | V2.6
by BMG PH RD SPC | [5 empty] | Name: | Schmitz, Jürgen |  |  |  |  | 03.07.06
to BMG PH RD BA | [5 empty] | Dep.: | BMG PHE TPM
[6 empty] | Phone Nr. | +49 89 4111 |  | Ext.: | 2660
Project account opening
(Project leader in close cooperation with SPC and/or responsible planner and according to PMC data base)
| Project Name: |  | Moonsoul
| Kind of Project: |  | Product Project | [5 empty] | Gen./Platf.: |  |  | PG 95 | Class: |  | III (45 w)
| Project Type: | [7 empty] | PMC Vers. Nr.: |  |  | Account Opening
| Target Product: | [7 empty] | Delivery Start: |  |  | Jun 2007
| Project Start: |  | 11.09.2006 |  |  | M0 |  |  | Product House: |  |  | Europe
| Project End: |  | 30.09.2008 |  |  | End of Project (EOP) |  |  | Effort needed after |  |  | EOP |  | YES | x | NO
Project Short Description: (mandatory input for each Project)
GSM/EDGE phone Mechanics as Onyx, but smaller in all dimensions PCB based on Diamond and Kaolin Retail phone, no global accounts Software Apoxe Gemstone 1.5 further details see "Steckbrief" in PMC
| Reference Project: |  |  | Onyx / Diamond |  |  |  |  | Total Costs (EUR): |  |  | 0
R&D planned resources / costs acc. to enclosed project planning (extract from PMC data base)
(Extract of values supported by BA, SPC and/or responsible planner)
| Summary planned resources: |  |  |  | (From Sep 2006 until Sep 2008) |  |  | Costs (EUR) for CY: (mandatory input for each site)
|  | Effort (hrs) |  |  | 83737 |  |  |  | CY 2006 |  | 1854384
|  | Consultant (EUR) |  |  | 60000 |  |  |  | CY 2007 |  | 5871170
|  | Material (EUR) |  |  | 1074102 |  |  |  | CY 2008 |  | 40243
|  | Miscellaneous (EUR) |  |  | 726680 |  |  |  | Total |  | 7765797
| Primavera project plan available and up to date: | [7 empty] | YES | x | Not relevant
| Project validation by: BMG PH RD SPC | [9 empty] | Project validated |  |  | YES |  | NO
| BMG PH RD SPC | [6 empty] | Responsible Planner
| sign./date |  | ----- |  |  |  |  | sign./date |  |  |  | -----
| TPM (Product) | [6 empty] | Predev. Responsible IPM (agreed)
| sign./date |  | Schmitz, Jürgen |  |  |  |  | sign./date |  |  |  | name
(With this signature the Project Manager confirms that the planning is correct
| and has been updated) | [6 empty] | (Not necessary in terms of product-, platf.-, module-proj. and Basic Act. / Supp.)
Program Manager
[8 empty] | sign./date |  |  |  | name
(Not necessary in terms of Product Project and Basic Act. / Supp.)
Head of Technical Project Management:
[8 empty] | sign./date |  |  |  | -----
(With this signature the Head of TPM / CoC confirm(s) also the availibility of own
resources as well as the feasibilty of the project)
| Budget Approval by: BMG PH RD BA | [9 empty] | Project approval |  |  | YES |  | NO
| Responsible RD BA controller | [6 empty] | Head of RD BA
| sign./date |  |  | ----- |  |  |  | sign./date |  |  |  | -----
| R&D Management (project approval) | [10 empty] | Relevant: | x | YES |  | NO
| sign./date |  | Bocionek, Dr. Siegrfried
(MD Top management approval, if required according to 2.2. of MP R&D Project Approval Guideline No. 2)
| BMG PH RD BA / BMG PH P BA: Project acc. opened | [6 empty] | Project Account:
[8 empty] | Primavera PSO / all rel. persons informed: | [7 empty] | YES
Note on B46: Peter Farrenkothen: Strategic Planning and Controlling
Note on B59: Peter Farrenkothen: HW-/SW- or Platform Program Manager