## Slide 1: Hawk M81 “Urban Active“ OPC Status Report at S25/M2
TPM: Jürgen Schmitz
TPM BA: Jan Strecker / Christopher Vogel
CPM: Antje Heinen
CPM BA: Markus Aicher
Jürgen Schmitz
Technical Project Management
13th June 2006

## Slide 2: Quality Gate Rating Hawk S25/M2 Status
Cost vs. target
Direct R&D 3’23€ (current) vs. 2’97€ (target)
(R&D cost deviation of 9%)
HK deviation 2% (1,23€) (because of volume and
CoC decrease)
Time-to-market
S25/M2 19.06.06 (current) vs.12.06.06 (target)
DS 11.08.06 vs. DS 11.08.06 (M1 target)
SCM
Allocation
Minor risk seen on production capacity vs. demand (in connection with Philippe overall capacity 210k/month; Hawk orders: Oct 110k/Nov. 114k; Philippe: Oct. 80k/Nov. 75k)
Material availability/Production Technology
No issues
SP
BOM 75,4€ (current, incl. 2% variant adder) vs. 72,6€ (target)

## Slide 3: Quality Gate Rating Hawk S25/M2 Status
R&D
Hardware/Radio
0,5 dB decrease on edges in PCS band
Compliance and Approvals
No issues
Mechanics
Critical timeline; partial delay
Still poor cosmetic quality of TPE material
Blue/white variant samples very late due to late design fixing and delay in material availability
QM
Overall Prod. Quality / System Test
Current return rate estimation 9% (5,4%SW+3,6%HW)
Critical: time schedule for S3 because less than 50%
of B2 Test run will be finished until start of Pilot (07.07.06)
Project Quality
Team declared M2/S25 on 19.06.06

## Slide 4: HAWK status at S25/M2 Product House Costs

## Slide 5: Required management support
OPC
accepts the milestone declaration
rejects the milestone declaration

## Slide 6: Backup