## Action & Information
Hawk
Dated | 2006-07-30
General | Action/information | Who | When | Status | Show
| Forecast from BenQ missing on Steel blue variant | Mr Zieminski | 2006-07-21 | Open | Y
| Forecast from BenQ missing on Grey variant | Mr Zieminski | 2006-07-21 | Done | Y
| 25 kg PC/ABS for steel blue version on stock | info |  |  | Y
| 25 kg TPE for steel blue version on stock | info |  |  | Y
| 1000 kg of white PC/ABS (M9157/970A) for steel blue version is ordered Preliminary delivery day is 2006-08-09 | Rickard Nilsson | 2006-08-09 |  | Y
| 1000 kg of blue TPE for steel blue version is ordered. Confirmed day is 2006-08-24. Check this! | Ingemar du Hane | 2006-08-24 |  | Y
| New colorplates in the new TPE for grey variant (sweat resistance) Kraiburg need material from master batch to be able to do the color matching. Nolato have ordered the total stock from Teknisk Agentur. Decision if Nolato shall send MB direct to Kraiburg will be taken during today (Tue). Lead time of material after approved color matching is approx 2 weeks. | Petter Andersson | 2006-07-25 | Done | n
| Material specification for new TPE (Data sheet) send to BenQ All available documentation have been sent to Bernhard Pavicsits. | Petter Andersson | 2006-07-24 | Done | n
| MB from Teknisk Agentur is not any longer available (last time buy!). New batch will be manufactured (2-3kg) this week. Colormatching will take place at Kreiburg in next week (Cw631) | Petter Andersson | 2006-07-31 | Done | n
| Kraiburg will get new MB from an other supplier (not Teknisk Agentur). | Petter Andersson | 2006-07-31 | Done | n
| BenQ will investigate the possibility to attend during the color matching at Kraiburg, in order to speed up the approval. | BenQ | 2006-07-27 | Open | Y
| Color samples will be available for approval w631-5. Already in KLF? | Petter Andersson | 2006-07-28 | Open | Y
Y
Battery Cover 2 cav | Action/information | Who | When | Status | Y
| Tool is at WBL for final adjustments | WBL | 2006-07-24 | Done | n
| Ribbs will be removed this week. | Ingemar du Hane |  |  | Y
| Production starts Cw630-1 Have not been started due to prioritzing of other tools. Production will start today (Tue 25). Production will start Today Wed 26. | Petter Andersson | 2006-07-24 | Done | n
| FOT made yesterday (Wed26). Parts stick to hard to the ejectors. Tool will be adjusted during the day, according to tool prio list. | WBL | 2006-07-27 | Done | n
| Tool is sent back to WBL in Denmark for adjustments. | WBL | To be updated | Open | Y
Y
Lower Case Impax | Action/information | Who | When | Status | Y
| Production of parts in Impax tool is started (3 500 pcs) | info |  |  | Y
| Still problem att the plastic part, a small burr on the hooks for the light guide assy, will be re-worked at Nolato Tallinn. | Vadim Badjanov | ongoing | Open | Y
| Approx. 1.400 pcs per day will be produced. White/Blue will decrease capacity (cleaning process takes time) | info |  |  | Y
| Tool is back at WBL for adjustments (ejector pins). Plan to start production today in Denmark (Tue 25). Confirmation from WBL is still missing. Production is planned in Denmark today Wed 26. | WBL | 2006-07-25 | Done | n
| WBL is trying to find a moulder who can start up the process from the impax tool. This tool wasn´t made for production purpose, and is not compatible with different 2K mould machines. The supplier who have made all sample moulding is closed for summer vacation. | WBL/Petter Andersson | 2006-07-28 | Done | Y
Y
Lower Case 2 cav | Action/information | Who | When | Status | Y
| First mould trial at Nolato | WBL | 2006-07-21 | Done | Y
| 20 FOT pcs will be at BenQ 25/7. FOT done, but tool have to be adjusted. Could not mould with any holding pressure in the first shot. WBL at Nolato on Monday morning for speeding up corrective actions. | Petter Andersson | 2006-07-24 | Open | Y
| Ready for production | info | 2006-07-26 | Open | Y
| When there is enough buffer to cover the ramp-up, the tool will be modified with the "light guide and sidekey" until then all parts from LC will be reworked (glued in light guide assy) at Nolato | Petter Andersson |  |  | Y
| Tool is sent back to WBL for adjustments. FOT is planned on Thursday 27. | WBL | 2006-07-24 | Done | Y
| Tool arrived tis morning (Thu 27). Arrival inspection is ongoing. Waiting for next trial (FOT) during the day. | Petter Andersson | 2006-07-27 | Done | Y
| Parts stick to hard to the cav. in first shot. Needs to be polished. Activity started at Nolato by WBL. | WBL | To be updated | Open | Y
Y
Upper Case Impax | Action/information | Who | When | Status | Y
| Tool are at WBL to repair a damage in the cavity for the first shot (PC/ABS) | WBL | 2006-07-19 | Done | Y
| Tool are at WBL to repair a damage in the cavity for the second shot (TPE) | WBL | 2006-07-22 | Done | Y
| Tool back at Nolato and ready for production | info | 2006-07-23 | Done | Y
| No production started due to machine problems (nozzle). Production will start Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | Y
| No parts for production are ready due to a damage in the cavity (same problem as last week). Tool will be fixed in Nolato tool shop before lunch time. | WBL | 2006-07-25 | Done | Y
| Tool is running in production since yestrday afternoon. Approx 2000pcs will be sent to AMB for Vacuum Metallzation before lunchtime (Wed 26) | Petter Andersson | 2006-07-26 | Done | Y
| 2400pcs where delivered to AMB yesterday (Wed 26). Tool is in Nolato tool shop for adjustments (see 2cav tool for detail explanation) | WBL | 2006-07-27 | Done | Y
| Tool trial yesterday evening (Thu27), but parts did not look 100% cosmetic ok. New trial started this morning. Cosmetic evaluation & report will be carried out during the day. Decision if q is accepted must take place. | Nolato /BenQ | 2006-07-28 | Open | Y
Y
Upper Case 2 cav | Action/information | Who | When | Status | Y
| First mould trial at Nolato. | WBL | 2006-07-21 | Done | Y
| 20 FOT pcs will be at BenQ 25/7. Tool did not fit in mould machine due to wrong dimension on ejector pin. WBL will be at Nolato on Monday morning for speeding up corrective actions. | Petter Andersson | 2006-07-24 | Open | Y
| Ready for production | info | 2006-07-31 | Open | Y
| Ejector pins have been modified to fit in the machine. FOT Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | Y
| Tool is ready for FOT today (Tue 25) | Petter Andersson | 2006-07-25 | Done | Y
| FOT is done. Som difficulties with second shot (TPE) due to the slider in MCC-slot area. New trial this morning. After 2:nd trial, the tool will be sent back to WBL for adjustments | Petter Andersson | 2006-07-26 | Done | Y
| Tool is in Nolato tool shop. Holes for screw towers in second shot cavities must be larger for 1:st shot part to fit. Same adjustment will be done for Impax tool. Next trial during the day (Thu 27). Action started today (Fri28). Next trial according to prio list | WBL | 2006-07-27 | Open | Y
Y
Rear Cover 2 cav | Action/information | Who | When | Status | Y
| Tool is at WBL for final adjustments. | WBL | 2006-07-20 | Done | Y
| Production will start Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | Y
| Tool is running, but parts from one cavity is NOK due to burr/flash (TPE). We are checking if the parts can be de-flashed. Cykle time to high due to problems with ejecting the sprue. | Petter Andersson | 2006-07-25 | Done | Y
| Production is ongoing. De-flashing is possible, and we will continue to produce in automatic. Process parameter is trimmed for first time to improve all cosmetic surfaces. | Petter Andersson | 2006-07-26 | Done | Y
| 3200pcs have been sent to Tallinn yesterday (Wed26). Tool is running. | Info | 2006-07-26 | Open | Y
| Production is running | info |  |  | Y
Y
I/O cover 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
| 20 pcs will be at BenQ 24/7 | Petter Andersson | 2006-07-21 | Done | Y
| The parts gets deformated wit automatic robot handling. Cavities needs to be polished. Action will be planned according to tool prio list. | WBL | 2006-07-27 | Open | Y
Y
Side Key 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
| Tool will be sent to WBL for "fine tuning" | WBL | 2006-07-24 | Done | Y
| Tool is back at Nolato and ready for production, Thu 27 | Info |  |  | Y
Y
Speaker Cover 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
Y
Y
Light Guide 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
Y
Y
Camera Lid 4 cav IMD | Action/information | Who | When | Status | Y
| Tool is in Nissha toolshop for adjustments, leadtime 4-5 days. | Nissha | 2006-07-24 | Done | Y
| Foil with correct artwork is produced and in stock at Nissha | info |  |  | n
| Production of minimum 4000 will be shipped to Tallinn Tuesday 25/7, ETA Tallinn 29/7 | info |  |  | n
| To secure the information flow Jalil Chigha from Nolato will be at Nissha from 22/7 and following week (cw30) | info |  |  | n
| Artwork for Steel blue variant is still open, (Chrome or not chrome) The Camera lid should be without chrome. | Andreas Hülsmann | 2006-07-21 | Done | Y
| IMD foil for steel blue version is ordered | Jalil Chigha | 2006-08-07 | Done | Y
| Waiting for confirmation from Nissha, regarding speeding up next deliveries from Japan. | Jalil Chigha | 2006-07-24 | Done | Y
| Nissha have increased the numbers of Camera Lid sent out from Japan Fri 28 , from 5K to 16K. ETA Tallinn Mo 31. | Jalil Chigha | 2006-07-31 | Open | Y
| Nissha deliveres according to plan. Tool will be transfered to Tallin as scheduled. | Jalil Chigha |  | Open | Y
Display lens 2 cav IMD | Action/information | Who | When | Status | Y
| OK, tool in production |  |  |  | Y
| Nissha will send IMD foil with correct color (black) to Tallinn | Nissha | 2006-07-20 | Done | Y
| IMD foil for steel blue version is ordered | Jalil Chigha | 2006-08-07 | Done | Y
Y
To be updated

## Delivery schedule
Hawk Delivery schedule |  |  | BenQ Forecast | Upper case |  | Lower case |  |  |  | Rear cover |  | Battery cover |  | I/O cover
Dated | 2006-07-30 |  |  | C39158-A211-A50 |  | C39158-A211-A200 |  | C39158-A122-A5 |  | C39158-A211-A540 |  | C39158-A211-B500 |  | C39158-A211-B920
Rev | 1.3 |  |  | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual
|  |  |  | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day
w629 | 2006-07-17 | Mon
| 2006-07-18 | Tue | [13 empty] | Explanation
| 2006-07-19 | Wen
| 2006-07-20 | Thu | [14 empty] | = from Impax tool
| 2006-07-21 | Fri | 12000
| 2006-07-22 | Sat | [14 empty] | = Production tools
| 2006-07-23 | Sun | [14 empty] | in production
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
w630 | 2006-07-24 | Mon |  | 600 | 634 | 900 | 900 | [6 empty] | 3000
| 2006-07-25 | Tue
| 2006-07-26 | Wen
| 2006-07-27 | Thu
| 2006-07-28 | Fri | 20700 |  |  | 900 | 1075
| 2006-07-29 | Sat
| 2006-07-30 | Sun
| Total |  |  | 600 | 634 | 1800 | 1975 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0
w631 | 2006-07-31 | Mon |  | 1500 | 1440 |  |  |  |  | 4000 | 2016
| 2006-08-01 | Tue
| 2006-08-02 | Wen
| 2006-08-03 | Thu
| 2006-08-04 | Fri | 19500 | 1000 |  | 700 | [7 empty] | 1000
| 2006-08-05 | Sat
| 2006-08-06 | Sun
| Total |  |  | 2500 | 1440 | 700 | 0 | 0 | 0 | 4000 | 2016 | 0 | 0 | 1000 | 0
w632 | 2006-08-07 | Mon |  | 1000 |  | 700 | [7 empty] | 10000
| 2006-08-08 | Tue |  | 1000 |  | 700
| 2006-08-09 | Wen |  | 1000 |  | 700
| 2006-08-10 | Thu | 18000 | 1000 |  | 700
| 2006-08-11 | Fri |  | 1000 |  | 700 | [5 empty] | 2000
| 2006-08-12 | Sat
| 2006-08-13 | Sun
| Total |  |  | 5000 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 10000 | 0
w633 | 2006-08-14 | Mon |  | 1000 |  | 700 | [5 empty] | 4000 |  | 18800
| 2006-08-15 | Tue |  | 1000 |  | 700 | [5 empty] | 6000
| 2006-08-16 | Wen |  | 1000 |  | 700 | [5 empty] | 6000
| 2006-08-17 | Thu | 18800 | 1000 |  | 700 |  |  |  | 3500 |  | 6000
| 2006-08-18 | Fri |  | 1000 |  | 700 |  |  |  | 3500 |  | 6000
| 2006-08-19 | Sat
| 2006-08-20 | Sun
| Total |  |  | 5000 | 0 | 3500 | 0 | 0 | 0 | 7000 | 0 | 28000 | 0 | 18800 | 0
w634 | 2006-08-21 | Mon |  | 1000 |  | 700 |  |  |  | 3500 |  | 6000 |  | 16000
| 2006-08-22 | Tue |  | 1000 |  | 700 |  |  |  | 3500 |  | 6000
| 2006-08-23 | Wen |  | 1000 |  | 700 |  |  |  | 3500 |  | 6000
|  |  |  | 15K |  | 10K |  |  |  | 18K |  | 46K |  | 46K |  | exclusive der 1,5K Pilot-Menge
ohne Berücksichtigung von Scrap
| 2006-08-24 | Thu | 16000 | 1200 |  | 700 |  |  |  | 3500 |  | 6000
| 2006-08-25 | Fri |  | 1500 |  | 700 |  |  |  | 3500
| 2006-08-26 | Sat
| 2006-08-27 | Sun
| Total |  |  | 5700 | 0 | 3500 | 0 | 0 | 0 | 17500 | 0 | 24000 | 0 | 16000 | 0
w635 | 2006-08-28 | Mon |  | 2000 |  | 2000 |  |  |  | 3500 |  | 6000 |  | 16000
| 2006-08-29 | Tue |  | 4000 |  | 4000 |  |  |  | 3500 |  | 6000
| 2006-08-30 | Wen |  | 5000 |  | 5000 |  |  |  | 3500 |  | 6000
|  |  |  | 13,7K |  | 12,4K |  |  |  | 17,5K | [5 empty] | ohne Berücksichtigung von Scrap
| 2006-08-31 | Thu | 16000 | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-01 | Fri |  | 7000 |  | 7000 |  |  |  | 3500
| 2006-09-02 | Sat
| 2006-09-03 | Sun
| Total |  |  | 25000 | 0 | 25000 | 0 | 0 | 0 | 17500 | 0 | 24000 | 0 | 16000 | 0
w636 | 2006-09-04 | Mon |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000 |  | 16000
| 2006-09-05 | Tue |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-06 | Wen |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-07 | Thu | 16000 | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-08 | Fri |  | 7000 |  | 7000 |  |  |  | 3500
| 2006-09-09 | Sat
| 2006-09-10 | Sun
| Total |  |  | 35000 | 0 | 35000 | 0 | 0 | 0 | 17500 | 0 | 24000 | 0 | 16000 | 0
w637 | 2006-09-11 | Mon |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000 |  | 16000
| 2006-09-12 | Tue |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-13 | Wen |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-14 | Thu | 16000 | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-15 | Fri |  | 7000 |  | 7000 |  |  |  | 3500
| 2006-09-16 | Sat
| 2006-09-17 | Sun
| Total |  |  | 35000 | 0 | 35000 | 0 | 0 | 0 | 17500 | 0 | 24000 | 0 | 16000 | 0
w638 | 2006-09-18 | Mon |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000 |  | 16000
| 2006-09-19 | Tue |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-20 | Wen |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-21 | Thu | 20000 | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-22 | Fri |  | 7000 |  | 7000 |  |  |  | 3500
| 2006-09-23 | Sat
| 2006-09-24 | Sun
| Total |  |  | 35000 | 0 | 35000 | 0 | 0 | 0 | 17500 | 0 | 24000 | 0 | 16000 | 0
w639 | 2006-09-25 | Mon |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000 |  | 16000
| 2006-09-26 | Tue |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-27 | Wen |  | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-28 | Thu | 20000 | 7000 |  | 7000 |  |  |  | 3500 |  | 6000
| 2006-09-29 | Fri |  | 7000 |  | 7000 |  |  |  | 3500
| 2006-09-30 | Sat
| 2006-10-01 | Sun
| Total |  |  | 35000 | 0 | 35000 | 0 | 0 | 0 | 17500 | 0 | 24000 | 0 | 16000 | 0
Note on F13: alprini: 400 arriving in KLF with hand carry on Sunday night, the rest with TNT on Monday morning
Note on I13: alprini: 400 arriving in KLF with hand carry on Sunday night, the rest with TNT on Monday morning
LC is the bottle neck: 700 pcs / day
Cap. of Impax tool
1.000 pcs / day
Cap. Appx.
3.500 pcs / day
Cap. Appx.
6.000 pcs / day
Cap. Appx.
10.000 pcs / day