## Action & Information
Hawk
Dated | 2006-08-03
General | Action/information | Who | When | Status | Show
| Forecast from BenQ missing on Steel blue variant | Mr Zieminski | 2006-07-21 | Open | Y
| Forecast from BenQ missing on Grey variant | Mr Zieminski | 2006-07-21 | Done | n
| 25 kg PC/ABS for steel blue version on stock | info |  |  | Y
| 25 kg TPE for steel blue version on stock | info |  |  | Y
| 1000 kg of white PC/ABS for steel blue version is ordered Confirmed day is 2006-08-10. | info | 2006-08-10 |  | Y
| 1000 kg of blue TPE for steel blue version is ordered. Confirmed day is 2006-08-24. | info | 2006-08-24 |  | Y
| New colorplates in the new TPE for grey variant (sweat resistance) Kraiburg need material from master batch to be able to do the color matching. Nolato have ordered the total stock from Teknisk Agentur. Decision if Nolato shall send MB direct to Kraiburg will be taken during today (Tue). Lead time of material after approved color matching is approx 2 weeks. | Petter Andersson | 2006-07-25 | Done | n
| Material specification for new TPE (Data sheet) send to BenQ All available documentation have been sent to Bernhard Pavicsits. | Petter Andersson | 2006-07-24 | Done | n
| MB from Teknisk Agentur is not any longer available (last time buy!). New batch will be manufactured (2-3kg) this week. Colormatching will take place at Kreiburg in next week (Cw631) | Petter Andersson | 2006-07-31 | Done | n
| Kraiburg will get new MB from an other supplier (not Teknisk Agentur). | Petter Andersson | 2006-07-31 | Done | n
| BenQ will investigate the possibility to attend during the color matching at Kraiburg, in order to speed up the approval. | BenQ | 2006-07-27 | Done | n
| Color match of grey color not appoved by BenQ, Andreas H. Infomation when new samples are available 2006-08-03 | Andreas Hülsmann | 2006-08-03 | Open | Y
| Plan needed in case of minor color miss match, not to mix new and old rev.stat of color. | BenQ | TBD | Open | Y
| Is it possible to use soft-tools for initial color samples due to rev. Level of tools? 50-70 kit might be possible to do in ST.Check this. | Andreas Hülsmann | 2006-08-02 | Open | Y
| Two tooling engineers from Nolato Alpha are added to the project to assist WBL in troube shooting tools. | Ingemar du Hane | 2006-07-31 | Done | Y
| Meeting at WBL today to review tool plans and find faster solutions, if possible. | Tommy Johansson | 2006-08-02 | Done | Y
| List of faults per tool to be reviewed and updated together with WBL and Andreas H. | Fedrik O | 2006-08-02 | Open
| As mentioned before, tools needs to be coated (PWD-surface treatment) when we need to produce high volumes of white color. We need a plan when to coat the tools based on volume cenario for white or other colors. This effects the capacity plan, it´s based on existing color. | BenQ | TBD | Open | Y
| Set up information matrix for all involved to avoid confusion. | Philipp Lutzny | 2006-08-03 | Open
Y
Battery Cover 2 cav | Action/information | Who | When | Status | Y
| Tool is at WBL for final adjustments | WBL | 2006-07-24 | Done | n
| Ribbs (modification) will be removed this week. | WBL | 2006-08-02 | Open | Y
| Production starts Cw630-1 Have not been started due to prioritzing of other tools. Production will start today (Tue 25). Production will start Today Wed 26. | Petter Andersson | 2006-07-24 | Done | n
| FOT made yesterday (Wed26). Parts stick to hard to the ejectors. Tool will be adjusted during the day, according to tool prio list. | WBL | 2006-07-27 | Done | n
| Tool is sent back to WBL in Denmark for adjustments. New tiral on Friday. | WBL | 2006-08-04 | Done | Y
| Trial today, Thursday | Info | 2006-08-03 | Open | Y
Lower Case Impax | Action/information | Who | When | Status | Y
| Production of parts in Impax tool is started (3 500 pcs) | info |  |  | n
| Still problem att the plastic part, a small burr on the hooks for the light guide assy, will be re-worked at Nolato Tallinn. | Vadim Badjanov | ongoing | Open | Y
| Approx. 1.400 pcs per day will be produced. White/Blue will decrease capacity (cleaning process takes time) | info |  |  | n
| Tool is back at WBL for adjustments (ejector pins). Plan to start production today in Denmark (Tue 25). Confirmation from WBL is still missing. Production is planned in Denmark today Wed 26. | WBL | 2006-07-25 | Done | n
| WBL is trying to find a moulder who can start up the process from the impax tool. This tool wasn´t made for production purpose, and is not compatible with different 2K mould machines. The supplier who have made all sample moulding is closed for summer vacation. | WBL/Petter Andersson | 2006-07-28 | Done | n
| Task force to speed up production of LC are in Denmark today. Result will be presented at 16.00. | Tommy Johansson | 2006-08-02 | Open
| Improved output. 24/7production => capacity of Approx. 10-12k/week of assy parts. | Tommy Joahnsson | ongoing | Open | Y
| Check color, compare with parts produced at NA. | Ingemar du Hane, Philipp Lutzny | 2006-08-03 | Open | Y
Y
Y
Lower Case 2 cav | Action/information | Who | When | Status | Y
| First mould trial at Nolato | WBL | 2006-07-21 | Done | n
| 20 FOT pcs will be at BenQ 25/7. FOT done, but tool have to be adjusted. Could not mould with any holding pressure in the first shot. WBL at Nolato on Monday morning for speeding up corrective actions. | Petter Andersson | 2006-07-24 | Done | n
| Tool is sent back to WBL for adjustments. FOT is planned on Thursday 27. | WBL | 2006-07-24 | Done | n
| Tool arrived tis morning (Thu 27). Arrival inspection is ongoing. Waiting for next trial (FOT) during the day. | Petter Andersson | 2006-07-27 | Done | n
| Parts stick to hard to the cav. in first shot. Needs to be polished. Activity started at Nolato by WBL. Next trial planned on Friday | WBL | 2006-08-04 | Open | Y
Y
Y
Upper Case Impax | Action/information | Who | When | Status | Y
| Tool are at WBL to repair a damage in the cavity for the first shot (PC/ABS) | WBL | 2006-07-19 | Done | n
| Tool are at WBL to repair a damage in the cavity for the second shot (TPE) | WBL | 2006-07-22 | Done | n
| Tool back at Nolato and ready for production | info | 2006-07-23 | Done | n
| No production started due to machine problems (nozzle). Production will start Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | n
| No parts for production are ready due to a damage in the cavity (same problem as last week). Tool will be fixed in Nolato tool shop before lunch time. | WBL | 2006-07-25 | Done | n
| Tool is running in production since yestrday afternoon. Approx 2000pcs will be sent to AMB for Vacuum Metallzation before lunchtime (Wed 26) | Petter Andersson | 2006-07-26 | Done | n
| 2400pcs where delivered to AMB yesterday (Wed 26). Tool is in Nolato tool shop for adjustments (see 2cav tool for detail explanation) | WBL | 2006-07-27 | Done | n
| Tool trial yesterday evening (Thu27), but parts did not look 100% cosmetic ok. New trial started this morning. Cosmetic evaluation & report will be carried out during the day. Decision if q is accepted must take place. New review today. | Nolato /BenQ | 2006-08-02 | Done | Y
Y
Upper Case 2 cav | Action/information | Who | When | Status | Y
| First mould trial at Nolato. | WBL | 2006-07-21 | Done | n
| 20 FOT pcs will be at BenQ 25/7. Tool did not fit in mould machine due to wrong dimension on ejector pin. WBL will be at Nolato on Monday morning for speeding up corrective actions. | Petter Andersson | 2006-07-24 | Open | n
| Ready for production | info | 2006-07-31 | Done | n
| Ejector pins have been modified to fit in the machine. FOT Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | n
| Tool is ready for FOT today (Tue 25) | Petter Andersson | 2006-07-25 | Done | n
| FOT is done. Som difficulties with second shot (TPE) due to the slider in MCC-slot area. New trial this morning. After 2:nd trial, the tool will be sent back to WBL for adjustments | Petter Andersson | 2006-07-26 | Done | n
| Tool is in Nolato tool shop. Holes for screw towers in second shot cavities must be larger for 1:st shot part to fit. Same adjustment will be done for Impax tool. New adjustment, Trials today. Robotfixture modified and will also be tested today. | WBL | 2006-08-02 | Done | Y
| Tool transfer to WBL. Robot fixture to be adjusted.Next trial planned 2006-08-09 | WBL | 2006-08-09 | Open | Y
Rear Cover 2 cav | Action/information | Who | When | Status | Y
| Tool is at WBL for final adjustments. | WBL | 2006-07-20 | Done | n
| Production will start Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | n
| Tool is running, but parts from one cavity is NOK due to burr/flash (TPE). We are checking if the parts can be de-flashed. Cykle time to high due to problems with ejecting the sprue. | Petter Andersson | 2006-07-25 | Done | n
| Production is ongoing. De-flashing is possible, and we will continue to produce in automatic. Process parameter is trimmed for first time to improve all cosmetic surfaces. | Petter Andersson | 2006-07-26 | Done | n
| 3200pcs have been sent to Tallinn yesterday (Wed26). Tool is running. | Info | 2006-07-26 | Done | n
| In production to cover initial needs, then to WBL for adjustments. | info |  |  | Y
Y
I/O cover 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
| 20 pcs will be at BenQ 24/7 | Petter Andersson | 2006-07-21 | Done | n
| The parts gets deformated wit automatic robot handling. Cavities needs to be polished. Action will be planned according to tool prio list. | WBL | 2006-07-27 | Done | n
| Tool is running. | info |  |  | Y
Side Key 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | n
| Tool will be sent to WBL for "fine tuning" | WBL | 2006-07-24 | Done | n
| Tool is back at Nolato and ready for production, Thu 27 | Info |  |  | n
| Tool repair right now. Approx. 4.000 parts in stock in Tallin. | info |  |  | Y
| Tool trial / production today | info | 2006-08-03 | Open | Y
Speaker Cover 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
Y
Y
Light Guide 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
Y
Y
Camera Lid 4 cav IMD | Action/information | Who | When | Status | Y
| Tool is in Nissha toolshop for adjustments, leadtime 4-5 days. | Nissha | 2006-07-24 | Done | n
| Foil with correct artwork is produced and in stock at Nissha | info |  |  | n
| Production of minimum 4000 will be shipped to Tallinn Tuesday 25/7, ETA Tallinn 29/7 | info |  |  | n
| To secure the information flow Jalil Chigha from Nolato will be at Nissha from 22/7 and following week (cw30) | info |  |  | n
| Artwork for Steel blue variant is still open, (Chrome or not chrome) The Camera lid should be without chrome. | Andreas Hülsmann | 2006-07-21 | Done | n
| IMD foil for steel blue version is ordered | Jalil Chigha | 2006-08-07 | Done | n
| Waiting for confirmation from Nissha, regarding speeding up next deliveries from Japan. | Jalil Chigha | 2006-07-24 | Done | n
| Nissha have increased the numbers of Camera Lid sent out from Japan Fri 28 , from 5K to 16K. ETA Tallinn Mo 31. | Jalil Chigha | 2006-07-31 | Done | n
| Nissha deliveres according to plan. Tool will be transfered to Tallin as scheduled. | Jalil Chigha |  | Open | Y
Display lens 2 cav IMD | Action/information | Who | When | Status | Y
| OK, tool in production |  |  |  | Y
| Nissha will send IMD foil with correct color (black) to Tallinn | Nissha | 2006-07-20 | Done | Y
| IMD foil for steel blue version is ordered | Jalil Chigha | 2006-08-07 | Done | Y
| "Moviestar"-Waiting for confirmation of delivery time today from Nissha. | Nissha | 2006-08-02 | Open | Y

## Delivery schedule
Hawk Delivery schedule |  |  | BenQ Forecast | Upper case |  | Lower case |  |  |  | Rear cover |  | Battery cover |  | I/O cover
Dated | 2006-08-03 |  |  | C39158-A211-A50 |  | C39158-A211-A200 |  | C39158-A122-A5 |  | C39158-A211-A540 |  | C39158-A211-B500 |  | C39158-A211-B920
Rev | 1.3 |  |  | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual
|  |  |  | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day | per Day
w628 | 2006-07-17 | Mon
| 2006-07-18 | Tue | [13 empty] | Explanation
| 2006-07-19 | Wen
| 2006-07-20 | Thu | [14 empty] | = from Impax tool
| 2006-07-21 | Fri | 3500
| 2006-07-22 | Sat | [14 empty] | = Production tools
| 2006-07-23 | Sun | [14 empty] | in production
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
w629 | 2006-07-17 | Mon
| 2006-07-18 | Tue | [13 empty] | Note:
| 2006-07-19 | Wen | [13 empty] | Capacity is based on one
| 2006-07-20 | Thu | [13 empty] | color (existing)
| 2006-07-21 | Fri | 12000
| 2006-07-22 | Sat
| 2006-07-23 | Sun
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
w630 | 2006-07-24 | Mon |  | 600 | 634 | 900 | 900 | [6 empty] | 3000
| 2006-07-25 | Tue
| 2006-07-26 | Wen
| 2006-07-27 | Thu
| 2006-07-28 | Fri | 20700 |  |  | 900 | 1075
| 2006-07-29 | Sat
| 2006-07-30 | Sun
| Total |  |  | 600 | 634 | 1800 | 1975 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0
w631 | 2006-07-31 | Mon |  | 1500 | 1440 |  |  |  |  | 4000 | 2016 |  | 250
| 2006-08-01 | Tue
| 2006-08-02 | Wen
| 2006-08-03 | Thu |  |  | 451 |  | 746 |  |  |  | 500 |  |  |  | 3200
| 2006-08-04 | Fri | 19500 | 500 |  | 700 | [7 empty] | 1000 | 15000
| 2006-08-05 | Sat
| 2006-08-06 | Sun
| Total |  |  | 2000 | 1891 | 700 | 746 | 0 | 0 | 4000 | 2516 | 0 | 250 | 1000 | 18200
w632 | 2006-08-07 | Mon |  | 1000 |  | 700 |  |  |  | 2450 |  |  |  | 10000
| 2006-08-08 | Tue |  | 1500 |  | 900 |  |  |  | 2450
| 2006-08-09 | Wen |  | 1700 |  | 1100 |  |  |  | 2450
| 2006-08-10 | Thu | 18000 | 1900 |  | 1500 |  |  |  | 2450
| 2006-08-11 | Fri |  | 1900 |  | 1600 |  |  |  | 2450 |  | 1500
| 2006-08-12 | Sat |  | 1900 |  | 1600 |  |  |  | 2450 |  | 2000
| 2006-08-13 | Sun |  | 1900 |  | 1600 |  |  |  | 2450 |  | 3000
| Total |  |  | 11800 | 0 | 9000 | 0 | 0 | 0 | 17150 | 0 | 6500 | 0 | 10000 | 0
w633 | 2006-08-14 | Mon |  | 2100 |  | 1600 | [5 empty] | 4500 |  | 25000
| 2006-08-15 | Tue |  | 2100 |  | 1600 | [5 empty] | 5000
| 2006-08-16 | Wen |  | 2100 |  | 1600 | [5 empty] | 5100
| Aufrechnung |  |  | 20,6K |  | 17K |  |  |  | 19,6K |  | 21,3K |  | 53,2K
| 2006-08-17 | Thu | 18800 | 2100 |  | 1600 | [5 empty] | 5100
| 2006-08-18 | Fri |  | 2100 |  | 1600 | [5 empty] | 5100
| 2006-08-19 | Sat |  | 2100 |  | 1900 | [5 empty] | 5100
| 2006-08-20 | Sun |  | 2100 |  | 2300 | [5 empty] | 5100
| Total |  |  | 14700 | 0 | 12200 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 25000 | 0
w634 | 2006-08-21 | Mon |  | 2100 |  | 3300 | [5 empty] | 5100 |  | 25000
| 2006-08-22 | Tue |  | 2100 |  | 3700 | [5 empty] | 5100
| 2006-08-23 | Wen |  | 2100 |  | 3700 | [5 empty] | 5100
| 2006-08-24 | Thu | 16000 | 2500 |  | 3700 | [5 empty] | 5100
| 2006-08-25 | Fri |  | 2500 |  | 3700 |  |  |  | 3000 |  | 5100
| 2006-08-26 | Sat |  | 3000 |  | 3700 |  |  |  | 4000 |  | 5100
| 2006-08-27 | Sun |  | 3000 |  | 3700 |  |  |  | 5000 |  | 5100
| Total |  |  | 17300 | 0 | 25500 | 0 | 0 | 0 | 12000 | 0 | 35700 | 0 | 25000 | 0
w635 | 2006-08-28 | Mon |  | 4000 |  | 3700 |  |  |  | 5000 |  | 5100 |  | 25000
| 2006-08-29 | Tue |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-08-30 | Wen |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-08-31 | Thu | 16000 | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-01 | Fri |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-02 | Sat |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-03 | Sun |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| Total |  |  | 29800 | 0 | 25900 | 0 | 0 | 0 | 35000 | 0 | 35700 | 0 | 25000 | 0
w636 | 2006-09-04 | Mon |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100 |  | 16000
| 2006-09-05 | Tue |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-06 | Wen |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-07 | Thu | 16000 | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-08 | Fri |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-09 | Sat |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-10 | Sun |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| Total |  |  | 30100 | 0 | 25900 | 0 | 0 | 0 | 35000 | 0 | 35700 | 0 | 16000 | 0
w637 | 2006-09-11 | Mon |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100 |  | 16000
| 2006-09-12 | Tue |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-13 | Wen |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-14 | Thu | 16000 | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-15 | Fri |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-16 | Sat |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-17 | Sun |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| Total |  |  | 30100 | 0 | 25900 | 0 | 0 | 0 | 35000 | 0 | 35700 | 0 | 16000 | 0
w638 | 2006-09-18 | Mon |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100 |  | 16000
| 2006-09-19 | Tue |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-20 | Wen |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-21 | Thu | 20000 | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-22 | Fri |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-23 | Sat |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-24 | Sun |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| Total |  |  | 30100 | 0 | 25900 | 0 | 0 | 0 | 35000 | 0 | 35700 | 0 | 16000 | 0
w639 | 2006-09-25 | Mon |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100 |  | 16000
| 2006-09-26 | Tue |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-27 | Wen |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-28 | Thu | 20000 | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-29 | Fri |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-09-30 | Sat |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| 2006-10-01 | Sun |  | 4300 |  | 3700 |  |  |  | 5000 |  | 5100
| Total |  |  | 30100 | 0 | 25900 | 0 | 0 | 0 | 35000 | 0 | 35700 | 0 | 16000 | 0
Note on F21: alprini: 400 arriving in KLF with hand carry on Sunday night, the rest with TNT on Monday morning
Note on G32: TNT Tracking number 120432675 451 instead of 193 pcs
Note on I21: alprini: 400 arriving in KLF with hand carry on Sunday night, the rest with TNT on Monday morning
Note on J32: TNT Tracking number 120432675
Note on P32: TNT Tracking number 120432675
Note on S29: TNT 789208771
Note on W32: TNT 789208842
Time schedule based on no modification of snap function light guide