## Action & Information
Hawk
Dated | 2006-08-11
General | Action/information | Who | When | Status | Show
| Forecast from BenQ missing on Steel blue variant | Andreas Hülsmann | 2006-07-21 | Done | Y
| Forecast from BenQ missing on Grey variant | Mr Zieminski | 2006-07-21 | Done | n
| Initial need is 6K cw 34, 10k cw 36. Forecast still needed. | Info |  | Done | n
| Initial build of 80 + 20 assy parts from soft-tool to be in KLF 2006-08-14. | Ingemar du Hane | 2006-08-14 | Open | Y
| 25 kg PC/ABS for steel blue version on stock | info |  |  | n
| 25 kg TPE for steel blue version on stock | info |  |  | n
| 1000 kg of white PC/ABS for steel blue version is ordered Confirmed day is 2006-08-10. | info | 2006-08-10 |  | n
| 1000 kg of blue TPE for steel blue version is ordered. Confirmed day is 2006-08-24. | info | 2006-08-24 |  | n
| New colorplates in the new TPE for grey variant (sweat resistance) Kraiburg need material from master batch to be able to do the color matching. Nolato have ordered the total stock from Teknisk Agentur. Decision if Nolato shall send MB direct to Kraiburg will be taken during today (Tue). Lead time of material after approved color matching is approx 2 weeks. | Petter Andersson | 2006-07-25 | Done | n
| Material specification for new TPE (Data sheet) send to BenQ All available documentation have been sent to Bernhard Pavicsits. | Petter Andersson | 2006-07-24 | Done | n
| MB from Teknisk Agentur is not any longer available (last time buy!). New batch will be manufactured (2-3kg) this week. Colormatching will take place at Kreiburg in next week (Cw631) | Petter Andersson | 2006-07-31 | Done | n
| Kraiburg will get new MB from an other supplier (not Teknisk Agentur). | Petter Andersson | 2006-07-31 | Done | n
| BenQ will investigate the possibility to attend during the color matching at Kraiburg, in order to speed up the approval. | BenQ | 2006-07-27 | Done | n
| Color match of grey color not appoved by BenQ, Andreas H. Infomation when new samples are available 2006-08-03 | Andreas Hülsmann | 2006-08-03 | Done | n
| New color match 2006-08-08/09 at Kreiburg, 125 kg (100 kg to NA and 25 kr to WBL LC) will be produced. PM BenQ will attend to approve samples. Ingmar Svensson Nolato will also attend. | Andreas Hülsmann | 2006-08-09 | Done | Y
| Plan needed in case of minor color miss match, not to mix new and old rev.stat of color. | BenQ | TBD | Open | Y
| Is it possible to use soft-tools for initial color samples due to rev. Level of tools? 50-70 kit might be possible to do in ST.Check this. | Andreas Hülsmann | 2006-08-02 | Done | n
| Additional orange TPE color needed. Do color match according to M65 Orange according to part from previous BenQ project. | Ingmar Svensson | 2006-08-09 | Open | Y
| Two tooling engineers from Nolato Alpha are added to the project to assist WBL in troube shooting tools. | Ingemar du Hane | 2006-07-31 | Done | n
| Meeting at WBL today to review tool plans and find faster solutions, if possible. | Tommy Johansson | 2006-08-02 | Open | n
| List of faults per tool to be reviewed and updated together with WBL and Andreas H. | Fedrik O | 2006-08-02 | Done | n
| As mentioned before, tools needs to be coated (PWD-surface treatment) when we need to produce high volumes of white color. We need a plan when to coat the tools based on volume cenario for white or other colors. This effects the capacity plan, it´s based on existing color. | BenQ | TBD | Open | Y
| Set up information matrix for all involved to avoid confusion. | Philipp Lutzny | 2006-08-03 | Done | n
| Information matrix updated according to meeting yesterday | Info | 2006-08-04 | Done | n
| Hawk- Yields, capacity and Stock overview, "2nd shoot" done. To be discussed an finalized during the day. | Ingemar Zivko | 2006-08-08 | Open | y
Y
Battery Cover 2 cav | Action/information | Who | When | Status | Y
| Tool is at WBL for final adjustments | WBL | 2006-07-24 | Done | n
| Ribbs (modification) will be removed this week. | WBL | 2006-08-02 | Done | n
| Production starts Cw630-1 Have not been started due to prioritzing of other tools. Production will start today (Tue 25). Production will start Today Wed 26. | Petter Andersson | 2006-07-24 | Done | n
| FOT made yesterday (Wed26). Parts stick to hard to the ejectors. Tool will be adjusted during the day, according to tool prio list. | WBL | 2006-07-27 | Done | n
| Tool is sent back to WBL in Denmark for adjustments. New tiral on Friday. | WBL | 2006-08-04 | Done | n
| Trial today, Thursday | Info | 2006-08-03 | Done | n
| Adjustments still needed, will be done at Nolato Alpha will NA personal to assist. | Info | 2006-08-04 | Open | y
| Tool repair needed this week end. Approx. 500 OK parts will be shipped today | Info | 2006-08-07 | Done | n
| 2000 pce to be send to KLF this week. Andreas Z to review Q in incomming inspection. | Andreas Z | 2006-08-08 | Open | Y
| Tool down for investigation. Action plan to be finalized during the day. | Tommy Johansson | 2006-08-08 | Done | n
| Tool adjustment successful. Fintuning today, ejector pin marks still visible. Samples will be available for Andreas Z to review this afternoon. Approx. 1.500 parts produced on risk to night. | Tommy Ingemar | 2006-08-09 | Done | Y
| New trials. Ejector pin marks not visible anymore. We need to continue deburring until tool is 100% fixed. Tool in production. | Info |  | Done | Y
Lower Case Impax | Action/information | Who | When | Status | Y
| Production of parts in Impax tool is started (3 500 pcs) | info |  |  | n
| Still problem att the plastic part, a small burr on the hooks for the light guide assy, will be re-worked at Nolato Tallinn. | Vadim Badjanov | ongoing | Open | Y
| Approx. 1.400 pcs per day will be produced. White/Blue will decrease capacity (cleaning process takes time) | info |  |  | n
| Tool is back at WBL for adjustments (ejector pins). Plan to start production today in Denmark (Tue 25). Confirmation from WBL is still missing. Production is planned in Denmark today Wed 26. | WBL | 2006-07-25 | Done | n
| WBL is trying to find a moulder who can start up the process from the impax tool. This tool wasn´t made for production purpose, and is not compatible with different 2K mould machines. The supplier who have made all sample moulding is closed for summer vacation. | WBL/Petter Andersson | 2006-07-28 | Done | n
| Task force to speed up production of LC are in Denmark today. Result will be presented at 16.00. | Tommy Johansson | 2006-08-02 | Done | n
n
| Improved output. 24/7production => capacity of Approx. 10-12k/week of assy parts. | Tommy Joahnsson | ongoing | Open | n
| Check color, compare with parts produced at NA. | Ingemar du Hane, Philipp Lutzny | 2006-08-03 | Done | n
| Production report: 2300 parts OK, 91 scrap | Info | 2006-08-11 | Done | Y
| "Dot" on TPE ok to ship. | Info |  |  | Y
Lower Case 2 cav | Action/information | Who | When | Status | Y
| First mould trial at Nolato | WBL | 2006-07-21 | Done | n
| 20 FOT pcs will be at BenQ 25/7. FOT done, but tool have to be adjusted. Could not mould with any holding pressure in the first shot. WBL at Nolato on Monday morning for speeding up corrective actions. | Petter Andersson | 2006-07-24 | Done | n
| Tool is sent back to WBL for adjustments. FOT is planned on Thursday 27. | WBL | 2006-07-24 | Done | n
| Tool arrived tis morning (Thu 27). Arrival inspection is ongoing. Waiting for next trial (FOT) during the day. | Petter Andersson | 2006-07-27 | Done | n
| Parts stick to hard to the cav. in first shot. Needs to be polished. Activity started at Nolato by WBL. Next trial planned on Friday | WBL | 2006-08-04 | Done | n
| New trials during the week end + work in Nolato tool shop. Tool now at WBL acc to plan. | Info | 2006-08-07 | Done | Y
| Tool at WBL according to plan. Trial om Sunday ? | Info | 2006-08-11 | Open | Y
Y
Upper Case Impax | Action/information | Who | When | Status | Y
| Tool are at WBL to repair a damage in the cavity for the first shot (PC/ABS) | WBL | 2006-07-19 | Done | n
| Tool are at WBL to repair a damage in the cavity for the second shot (TPE) | WBL | 2006-07-22 | Done | n
| Tool back at Nolato and ready for production | info | 2006-07-23 | Done | n
| No production started due to machine problems (nozzle). Production will start Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | n
| No parts for production are ready due to a damage in the cavity (same problem as last week). Tool will be fixed in Nolato tool shop before lunch time. | WBL | 2006-07-25 | Done | n
| Tool is running in production since yestrday afternoon. Approx 2000pcs will be sent to AMB for Vacuum Metallzation before lunchtime (Wed 26) | Petter Andersson | 2006-07-26 | Done | n
| 2400pcs where delivered to AMB yesterday (Wed 26). Tool is in Nolato tool shop for adjustments (see 2cav tool for detail explanation) | WBL | 2006-07-27 | Done | n
| Tool trial yesterday evening (Thu27), but parts did not look 100% cosmetic ok. New trial started this morning. Cosmetic evaluation & report will be carried out during the day. Decision if q is accepted must take place. New review today. | Nolato /BenQ | 2006-08-02 | Done | Y
| Production report: 2600 parts OK, scrap 41 | Info | 2006-08-11 | Open | Y
| Burrs. Use only for retail. |  |  |  | Y
Upper Case 2 cav | Action/information | Who | When | Status | Y
| First mould trial at Nolato. | WBL | 2006-07-21 | Done | n
| 20 FOT pcs will be at BenQ 25/7. Tool did not fit in mould machine due to wrong dimension on ejector pin. WBL will be at Nolato on Monday morning for speeding up corrective actions. | Petter Andersson | 2006-07-24 | Open | n
| Ready for production | info | 2006-07-31 | Done | n
| Ejector pins have been modified to fit in the machine. FOT Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | n
| Tool is ready for FOT today (Tue 25) | Petter Andersson | 2006-07-25 | Done | n
| FOT is done. Som difficulties with second shot (TPE) due to the slider in MCC-slot area. New trial this morning. After 2:nd trial, the tool will be sent back to WBL for adjustments | Petter Andersson | 2006-07-26 | Done | n
| Tool is in Nolato tool shop. Holes for screw towers in second shot cavities must be larger for 1:st shot part to fit. Same adjustment will be done for Impax tool. New adjustment, Trials today. Robotfixture modified and will also be tested today. | WBL | 2006-08-02 | Done | n
| Tool transfer to WBL. Robot fixture to be adjusted.Next trial planned 2006-08-09 | WBL | 2006-08-09 | Done | n
| Tolol trial today at Nolato | Info | 2006-08-09 | Done | Y
| Transport to WBL today | Info | 2006-08-11 | Open | Y
Rear Cover 2 cav | Action/information | Who | When |  | Y
| Tool is at WBL for final adjustments. | WBL | 2006-07-20 | Done | n
| Production will start Monday afternoon (Cw630-1) | Petter Andersson | 2006-07-24 | Done | n
| Tool is running, but parts from one cavity is NOK due to burr/flash (TPE). We are checking if the parts can be de-flashed. Cykle time to high due to problems with ejecting the sprue. | Petter Andersson | 2006-07-25 | Done | n
| Production is ongoing. De-flashing is possible, and we will continue to produce in automatic. Process parameter is trimmed for first time to improve all cosmetic surfaces. | Petter Andersson | 2006-07-26 | Done | n
| 3200pcs have been sent to Tallinn yesterday (Wed26). Tool is running. | Info | 2006-07-26 | Done | n
| In production to cover initial needs, then to WBL for adjustments. | info |  |  | n
| Production according to plan, Yield >96% | info |  |  | n
| Tool down for improvments. Will be started before lunch. | info | 2006-08-08 | Open
| Review process of lubrication in Tallin | Anders Z Ingemar | 2006-08-09 | Done | y
| It´s done acc. to specification. WI is OK. | Info | 2006-08-11 | Open | y
y
I/O cover 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
| 20 pcs will be at BenQ 24/7 | Petter Andersson | 2006-07-21 | Done | n
| The parts gets deformated wit automatic robot handling. Cavities needs to be polished. Action will be planned according to tool prio list. | WBL | 2006-07-27 | Done | n
| Tool is running. | info |  |  | Y
| Delivery in bag: Proposal sent to Philipp. Qoutation will be send today | Petter Andersson | 2006-08-07 | Done | Y
| Decision of package needed. | Philipp | TBD | Open | Y
Side Key 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | n
| Tool will be sent to WBL for "fine tuning" | WBL | 2006-07-24 | Done | n
| Tool is back at Nolato and ready for production, Thu 27 | Info |  |  | n
| Tool repair right now. Approx. 4.000 parts in stock in Tallin. | info |  |  | n
| Tool trial / production today | info | 2006-08-03 | Done | n
| Tool repair at the moment. Approx. 3k parts produced. | info |  | Done | n
| Inprovement of gate chanel will be done in parallell to modification w33. Until then Nolato will polish the chanel | Peter WBL | 2006-08-17 | Open | Y
| Tool down for polish. Will be started before lunch. | Info | 2006-08-08 | Done | Y
| Plan for tool modification w33. Buffer needed acc.to delivery schedule. | Tommy | 2006-08-10 | Open | Y
Speaker Cover 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
Y
n
Light Guide 4 cav | Action/information | Who | When | Status | Y
| OK, tool in production | info |  |  | Y
Y
Y
Camera Lid 4 cav IMD | Action/information | Who | When | Status | Y
| Tool is in Nissha toolshop for adjustments, leadtime 4-5 days. | Nissha | 2006-07-24 | Done | n
| Foil with correct artwork is produced and in stock at Nissha | info |  |  | n
| Production of minimum 4000 will be shipped to Tallinn Tuesday 25/7, ETA Tallinn 29/7 | info |  |  | n
| To secure the information flow Jalil Chigha from Nolato will be at Nissha from 22/7 and following week (cw30) | info |  |  | n
| Artwork for Steel blue variant is still open, (Chrome or not chrome) The Camera lid should be without chrome. | Andreas Hülsmann | 2006-07-21 | Done | n
| IMD foil for steel blue version is ordered | Jalil Chigha | 2006-08-07 | Done | n
| Waiting for confirmation from Nissha, regarding speeding up next deliveries from Japan. | Jalil Chigha | 2006-07-24 | Done | n
| Nissha have increased the numbers of Camera Lid sent out from Japan Fri 28 , from 5K to 16K. ETA Tallinn Mo 31. | Jalil Chigha | 2006-07-31 | Done | n
| Nissha deliveres according to plan. Tool will be transfered to Tallin as scheduled. | Jalil Chigha |  | Open | Y
| White - Delivery time interfears with other BenQ project - to be solved | BenQ | 2008-08-08 | Done | Y
Display lens 2 cav IMD | Action/information | Who | When | Status | Y
| OK, tool in production |  |  |  | Y
| Nissha will send IMD foil with correct color (black) to Tallinn | Nissha | 2006-07-20 | Done | Y
| IMD foil for steel blue version is ordered | Jalil Chigha | 2006-08-07 | Done | Y
| White - Delivery time interfears with other BenQ project - to be solved | BenQ | 2008-08-08 | Open | Y
| CL and foil for DL will be in Tallin 21/8 | Info | 2008-08-21 | Open | Y
| "Moviestar"-Waiting for confirmation of delivery time today from Nissha. | Nissha | 2006-08-02 | Open | Y

## Delivery schedule
Hawk Delivery schedule |  |  | BenQ Forecast | Upper case |  | Lower case |  |  |  |  | Rear cover |  | Battery cover |  |  | I/O cover
Dated | 2006-08-11 |  |  | C39158-A211-A50 |  | C39158-A211-A200 |  | C39158-A122-A5 |  |  | C39158-A211-A540 |  | C39158-A211-B500 |  |  | C39158-A211-B920
Rev | 1.3 |  |  | Conf.PO | Actual | Conf.PO | Actual | Conf.PO | Actual |  | Conf.PO | Actual | Conf.PO | Actual |  | Conf.PO | Actual
|  |  |  | per Day | per Day | per Day | per Day | per Day | per Day |  | per Day | per Day | per Day | per Day |  | per Day | per Day
w628 | 2006-07-10 | Mon
| 2006-07-11 | Tue | [15 empty] | Explanation
| 2006-07-12 | Wen
| 2006-07-13 | Thu | [16 empty] | = from Impax tool
| 2006-07-14 | Fri | 3500
| 2006-07-15 | Sat | [16 empty] | = Production tools
| 2006-07-16 | Sun | [16 empty] | in production
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0
w629 | 2006-07-17 | Mon
| 2006-07-18 | Tue | [15 empty] | Note:
| 2006-07-19 | Wen | [15 empty] | Capacity is based on one
| 2006-07-20 | Thu | [15 empty] | color (existing)
| 2006-07-21 | Fri | 12000
| 2006-07-22 | Sat
| 2006-07-23 | Sun
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0
Delta ag. Forecast |  |  |  | -12000 | -12000 | -12000 | -12000 | 0 | 0 | 0 | -12000 | -12000 | -12000 | -12000 | 0 | -12000 | -12000
w630 | 2006-07-24 | Mon |  | 600 | 634 | 900 | 900 | [8 empty] | 3000
| 2006-07-25 | Tue
| 2006-07-26 | Wen
| 2006-07-27 | Thu
| 2006-07-28 | Fri | 20700 |  |  | 900 | 1075
| 2006-07-29 | Sat
| 2006-07-30 | Sun
| Total |  |  | 600 | 634 | 1800 | 1975 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 3000 | 0
Delta ag. Forecast |  |  |  | -20100 | -20066 | -18900 | -18725 | 0 | 0 | 0 | -20700 | -20700 | -20700 | -20700 | 0 | -17700 | -20700
Cum Delta ag. Forecast |  |  |  | -32100 | -32066 | -30900 | -30725 | 0 | 0 | 0 | -32700 | -32700 | -32700 | -32700 | 0 | -29700 | -32700
w631 | 2006-07-31 | Mon |  | 1500 | 1440 | [5 empty] | 4000 | 2016 |  | 250
| 2006-08-01 | Tue
| 2006-08-02 | Wen
| 2006-08-03 | Thu |  |  | 451 |  | 746 |  |  |  |  | 500 |  |  |  |  | 3200
| 2006-08-04 | Fri | 19500 | 500 |  | 700 | [9 empty] | 1000 | 15000
| 2006-08-05 | Sat |  |  | 400 |  | 1479 |  |  |  |  | 1233
| 2006-08-06 | Sun
| Total |  |  | 2000 | 2291 | 700 | 2225 | 0 | 0 |  | 4000 | 3749 | 0 | 250 |  | 1000 | 18200
Delta ag. Forecast |  |  |  | -17500 | -17209 | -18800 | -17275 | -500 | 0 | 0 | -15500 | -15751 | -19500 | -19250 | 0 | -18500 | -1300
Cum Delta ag. Forecast |  |  |  | -49600 | -49275 | -49700 | -48000 | -500 | 0 | 0 | -48200 | -48451 | -52200 | -51950 | 0 | -48200 | -34000
w632 | 2006-08-07 | Mon |  | 1000 |  | 700 |  |  |  |  | 2450 |  |  |  |  | 10000
| 2006-08-08 | Tue |  | 1500 | 560 | 900 | 1009 |  |  |  | 2450 | 3335 |  | 500
| 2006-08-09 | Wen |  | 1700 | 1400 | 1100 | 980 |  |  |  | 2450 | 2450 |  | 500
| 2006-08-10 | Thu | 18000 | 1900 | 806 | 1500 | 818 |  |  |  | 2450 | 2350 |  | 1000
| 2006-08-11 | Fri |  | 1900 | 900 | 1600 | 920 |  |  |  | 2450 | 1708 | 1500 | 2000
| 2006-08-12 | Sat |  | 1900 |  | 1600 |  |  |  |  | 2450 |  | 2000
| 2006-08-13 | Sun |  | 1900 |  | 1600 |  |  |  |  | 2450 |  | 3000
| Total |  |  | 11800 | 3666 | 9000 | 3727 | 0 | 0 |  | 17150 | 9843 | 6500 | 4000 |  | 10000 | 0
Delta ag. Forecast |  |  |  | -6200 | -14334 | -9000 | -14273 | -1900 | -900 | 0 | -850 | -8157 | -11500 | -14000 | -2450 | -8000 | -18000
Cum Delta ag. Forecast |  |  |  | -55800 | -63609 | -58700 | -62273 | -2400 | -900 | 0 | -49050 | -56608 | -63700 | -65950 | -2450 | -56200 | -52000
w633 | 2006-08-14 | Mon |  | 2100 |  | 1600 | [6 empty] | 4500 |  |  | 25000
| 2006-08-15 | Tue |  | 2100 |  | 1600 | [6 empty] | 5000
| 2006-08-16 | Wen |  | 2100 |  | 1600 | [6 empty] | 5100
|  |  |  | 16,9K |  | 15,9K |  |  |  |  | 18,5K |  | 23,8K
| 2006-08-17 | Thu | 18800 | 2100 |  | 1600 | [6 empty] | 5100
| 2006-08-18 | Fri |  | 2100 |  | 1600 | [6 empty] | 5100
| 2006-08-19 | Sat |  | 2100 |  | 1900 | [6 empty] | 5100
| 2006-08-20 | Sun |  | 2100 |  | 2300 | [6 empty] | 5100
| Total |  |  | 14700 | 0 | 12200 | 0 | 0 | 0 |  | 0 | 0 | 35000 | 0 |  | 25000 | 0
Delta ag. Forecast |  |  |  | -4100 | -18800 | -6600 | -18800 | -2100 | 0 | 0 | -18800 | -18800 | 16200 | -18800 | 0 | 6200 | -18800
Cum Delta ag. Forecast |  |  |  | -59900 | -82409 | -65300 | -81073 | -4500 | -900 | 0 | -67850 | -75408 | -47500 | -84750 | -2450 | -50000 | -70800
w634 | 2006-08-21 | Mon |  | 2100 |  | 3300 | [6 empty] | 5100 |  |  | 25000
| 2006-08-22 | Tue |  | 2100 |  | 3700 | [6 empty] | 5100
| 2006-08-23 | Wen |  | 2100 |  | 3700 | [6 empty] | 5100
| 2006-08-24 | Thu | 16000 | 2500 |  | 3700 | [6 empty] | 5100
| 2006-08-25 | Fri |  | 2500 |  | 3700 |  |  |  |  | 3000 |  | 5100
| 2006-08-26 | Sat |  | 3000 |  | 3700 |  |  |  |  | 4000 |  | 5100
| 2006-08-27 | Sun |  | 3000 |  | 3700 |  |  |  |  | 5000 |  | 5100
| Total |  |  | 17300 | 0 | 25500 | 0 | 0 | 0 |  | 12000 | 0 | 35700 | 0 |  | 25000 | 0
Delta ag. Forecast |  |  |  | 1300 | -16000 | 9500 | -16000 | -2500 | 0 | 0 | -4000 | -16000 | 19700 | -16000 | -3000 | 9000 | -16000
Cum Delta ag. Forecast |  |  |  | -58600 | -98409 | -55800 | -97073 | -7000 | -900 | 0 | -71850 | -91408 | -27800 | -100750 | -5450 | -41000 | -86800
w635 | 2006-08-28 | Mon |  | 4000 |  | 3700 |  |  |  |  | 5000 |  | 5100 |  |  | 25000
| 2006-08-29 | Tue |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-08-30 | Wen |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-08-31 | Thu | 16000 | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-01 | Fri |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-02 | Sat |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-03 | Sun |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| Total |  |  | 29800 | 0 | 25900 | 0 | 0 | 0 |  | 35000 | 0 | 35700 | 0 |  | 25000 | 0
Delta ag. Forecast |  |  |  | 13800 | -16000 | 9900 | -16000 | -4300 | 0 | 0 | 19000 | -16000 | 19700 | -16000 | -5000 | 9000 | -16000
Cum Delta ag. Forecast |  |  |  | -44800 | -114409 | -45900 | -113073 | -11300 | -900 | 0 | -52850 | -107408 | -8100 | -116750 | -10450 | -32000 | -102800
w636 | 2006-09-04 | Mon |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100 |  |  | 16000
| 2006-09-05 | Tue |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-06 | Wen |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-07 | Thu | 16000 | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-08 | Fri |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-09 | Sat |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-10 | Sun |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| Total |  |  | 30100 | 0 | 25900 | 0 | 0 | 0 |  | 35000 | 0 | 35700 | 0 |  | 16000 | 0
Delta ag. Forecast |  |  |  | 14100 | -16000 | 9900 | -16000 | -4300 | 0 | 0 | 19000 | -16000 | 19700 | -16000 | -5000 | 0 | -16000
Cum Delta ag. Forecast |  |  |  | -30700 | -130409 | -36000 | -129073 | -15600 | -900 | 0 | -33850 | -123408 | 11600 | -132750 | -15450 | -32000 | -118800
w637 | 2006-09-11 | Mon |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100 |  |  | 16000
| 2006-09-12 | Tue |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-13 | Wen |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-14 | Thu | 16000 | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-15 | Fri |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-16 | Sat |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-17 | Sun |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| Total |  |  | 30100 | 0 | 25900 | 0 | 0 | 0 |  | 35000 | 0 | 35700 | 0 |  | 16000 | 0
Delta ag. Forecast |  |  |  | 14100 | -16000 | 9900 | -16000 | -4300 | 0 | 0 | 19000 | -16000 | 19700 | -16000 | -5000 | 0 | -16000
Cum Delta ag. Forecast |  |  |  | -16600 | -146409 | -26100 | -145073 | -19900 | -900 | 0 | -14850 | -139408 | 31300 | -148750 | -20450 | -32000 | -134800
w638 | 2006-09-18 | Mon |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100 |  |  | 16000
| 2006-09-19 | Tue |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-20 | Wen |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-21 | Thu | 20000 | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-22 | Fri |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-23 | Sat |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-24 | Sun |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| Total |  |  | 30100 | 0 | 25900 | 0 | 0 | 0 |  | 35000 | 0 | 35700 | 0 |  | 16000 | 0
Delta ag. Forecast |  |  |  | 10100 | -20000 | 5900 | -20000 | -4300 | 0 | 0 | 15000 | -20000 | 15700 | -20000 | -5000 | -4000 | -20000
Cum Delta ag. Forecast |  |  |  | -6500 | -166409 | -20200 | -165073 | -24200 | -900 | 0 | 150 | -159408 | 47000 | -168750 | -25450 | -36000 | -154800
w639 | 2006-09-25 | Mon |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100 |  |  | 16000
| 2006-09-26 | Tue |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-27 | Wen |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-28 | Thu | 20000 | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-29 | Fri |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-09-30 | Sat |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| 2006-10-01 | Sun |  | 4300 |  | 3700 |  |  |  |  | 5000 |  | 5100
| Total |  |  | 30100 | 0 | 25900 | 0 | 0 | 0 |  | 35000 | 0 | 35700 | 0 |  | 16000 | 0
Note on F22: alprini: 400 arriving in KLF with hand carry on Sunday night, the rest with TNT on Monday morning
Note on G35: TNT Tracking number 120432675 451 instead of 193 pcs
Note on G43: TNT 120582932
Note on G45: TNT 120686333
Note on G46: TNT 120727235
Note on I22: alprini: 400 arriving in KLF with hand carry on Sunday night, the rest with TNT on Monday morning
Note on J35: TNT Tracking number 120432675
Note on J43: TNT 120582932
Note on J45: TNT 120686333
Note on J46: TNT 120727235
Note on P35: TNT Tracking number 120432675
Note on P43: TNT 120582932
Note on P45: TNT 120686333
Note on P46: TNT 120727235
Note on S32: TNT 789208771
Note on S43: TNT 789208992
Note on S46: TNT 789209131
Note on W35: TNT 789208842
Time schedule based on no modification of snap function light guide
Volymes in italics not confirmed right now due to more color versions.