## Slide 1: Philippe “Elegant Performance“ OPC Status Report at DS
Claus Dalmose
Technical Project Management
16th May 2006
TPM: Claus Dalmose
TPM BA: Hubertus Schlausch
CPM: Claudia Weidner
CPM BA: Markus Aicher

## Slide 2: Quality Gate Rating Philippe DS Status
CONTRACT
Cost vs. Target
BOM deviation 15% Current: 86,31€ vs. M1 target 75,13€ Reasons: new FX rate (about 3,8€ at S25 ) and volume reduction.
Time-to-market
24. May 2006 (current) vs 29. May 2006 (M1 target) (SW version 38)
Possible earlier deliveries to RUS, UKR of ~13k on 19. May 2006 to be decided (SW version 37)
SCM
Allocation
No major issues
Production Technology
Gap between front cover and uppercase for the first 25k: CPM clarifies if this is acceptable

## Slide 3: Quality Gate Rating Philippe DS Status
R&D
Software
SW 38 still has to be tested in production
Hardware/Radio
FCC certificate is not available until now
Mechanics
Preliminary parts will have additional 2% scrap rate (approximately 60k)
Compliance and Approvals
FCC certificate is not available until now
Orange approvals expected May 19th 06 (SW38)
Country approvals on SW37 for Ramp up available
(Turkey, CZR, Croatia, Russia, AZB)
QM
Overall Prod. Quality / System Test
Current Return Rate estimation is not yet available (availability until 19. May 2006). NCCPI is ?? (inline with NCCPI targets
GCF test results not available yet, but planning is inline with customer requirements
Project Quality
Signatures from EA, SW, LCM1, LCM3, SD QM, ST, QM (BA, CPM) not yet available. Signatures are expected till 24. May 2006

## Slide 4: Product House Costs – Philippe Status at DS

## Slide 5: Required management support
OPC
accepts the milestone declaration
rejects the milestone declaration

## Slide 6: Backup

## Slide 7: Points to be closed until DS
SW SVN38 SW | Available since 15.05.06
FCC approval EA | All tests passed. All formalities in place. Grant expected 16.05.06 (maybe +1 day due to time difference US/EU)
GCF approval ST-MO | Pass verified on test SW (SVN38) Formal test to be done at 7Layers with official SW SVN38 Approval expexted until 22.05.06
Java certificate ST-SW / QM-SW | Pass confirmed on test SW (SVN38) Pass to be verified on official SW release (Self-certification). Pass confirmed 16.05.06 (DS okay for ST-SW). Listing on SUN WEB page/Certificate expected until 24.05 (not finally confirmed) QM-SW blocks for DS w/o certificate
SMS-On-Exit test QM-SW | For Return rate estimation.Testing in 5 days for RR estimation + 2 days for reporting Expected to be finished until 24.05.06 (test results 22.05.06) Current status for SVN37 is 6,0% - 6,5% (based on Minos)
BT qualification ST-MO | Fail on BT test case with SW SVN38. Potentially test failure. Under clarification No violation of lega requirements Blocking from ST-MO side
R&TTE approval (BABT) ST-MO | Granted 16.05.06

## Slide 8: SW SVN37 DS blockers
P7500108512 | Two "lastModified()" related tests failed in JSR75 FC TCK run.
P7500105684 | GCF SAT TC27.22.4.13.3 SET UP CALL (display of icons) is failed. Wrong Terminal Response is sent from ME to SIM
P7500105703 | GCF SAT TC 27.22.7.4.1 LOCATION STATUS EVENT is failed due to wrong ENVELOP send from ME to SIM
P7500111914 | Philippe JSR82 TCK : Test case api/javax/bluetooth/ServiceRecord/setDeviceServiceClassesTest failed