## Slide 1: Status Hawk #1/2
B2 samples grey/black:
- Plan @ M1: available in regions cw29 (21.7.06)
- Actual: available in cw30 (deliveries on July 21st and 24th – done)
Standard target for B2: 3 weeks before DS; DS planned on 11.8. (cw32) -> Depending on
arrival in regions only slight delay
Blue/white variant:
- Plan @ M1: only intention to deliver 2nd color variant
- Team target: available in regions cw30; volume production 4 weeks after DS (cw36)
Actual: assembly B2 in cw32; available in regions cw33
> Hence 3 weeks delay
- MMC tray delivery critical; first volume end cw35 in case that color match is OK
Measures to secure samples:
Nolato to check if and how acceleration of IMD window und camera lid from Nissha is
possible (driver SCM QM)
In case MMC trays are not available we should deliver w/o trays
Measures to secure volume production:
- Raw material for white PC-ABS and blue TPE already ordered for 50K devices;
available at Nolato on 11.8. (cw32)
- Availability of keypads not confirmed yet for cw35; SP is in charge to get confirmation

## Slide 2: Status Hawk #2/2
Ramp Up Volume:
- Plan Milestone PS: 3.8.2006 (cw31)
- Nolato deliveries are until end of week
Hence cw31 and cw32 are most critical
Nolato still has problems with damage of tooling during molding
From todays view DS at Aug. 11th still possible, but with reduced volume (appr. 8K)
Measures:
- Daily TelCo with Nolato driven by SCM QM
SCM QM is asked to check at Nolato onside how to solve the problem with tooling and if there is a general issue with the tooling concept.
 | cw29 | cw30 | cw31 | cw32 | cw33
Forecast | 3,5K | 12K | 21K | 20K | 18K
Pilot volume |  | 1,5K |  |  | 
Production volume |  |  | 7,7K | 12,5K | 14K
delivery from Nolato |  | 2,7K | 18K | 20K | 20K