## EMC_Ant
Department load from : HW EMC/AntAal AAL; HW EMC/Ant ATL; HW EMC/AntBEJ BEJ; HW EMC/AntKLF KLF; HW EMC/AntMch Mch; HW EMC/Ant SAN; HW EMC/AntUlm Ulm
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 504
Sum in MM | 48 | 54 | 54 | 60 | 68 | 80 | 93 | 106 | 108 | 105 | 98 | 104 | 979
Sum in Hr. | 6775 | 7698 | 7660 | 8369 | 9385 | 10869 | 12494 | 14166 | 14386 | 13877 | 12734 | 13450 | 131863
Delta in MM | -6 | -12 | -12 | -18 | -26 | -38 | -51 | -64 | -66 | -63 | -56 | -62 | -475
Delta in Hr. | -861 | -1784 | -1746 | -2455 | -3471 | -4955 | -6580 | -8252 | -8472 | -7963 | -6820 | -7536 | -60895
Consultant (Eur) | 218700 | 228400 | 265700 | 265700 | 283700 | 274700 | 271200 | 253200 | 253200 | 202000 | 176500 | 176500 | 2869500
Material (Eur) | 0 | 2200 | 0 | 4800 | 100 | 2300 | 100 | 300 | 100 | 250 | 50 | 200 | 10400
Miscellaenous (Eur) | 79863 | 114254 | 63639 | 82062 | 126788 | 182908 | 111108 | 112963 | 61523 | 118886 | 127137 | 101590 | 1282721
Travel (Eur) | 19863 | 33954 | 26639 | 38062 | 33788 | 36908 | 44508 | 39963 | 47523 | 48886 | 39137 | 41590 | 450821
NRE (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
License (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Certification (Eur) | 60000 | 80300 | 37000 | 44000 | 93000 | 146000 | 66600 | 73000 | 14000 | 70000 | 88000 | 60000 | 831900
Others (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ST
Department load from : ST HW-ST/Appr AAL; ST HW-ST/Appr ATL; ST HW-ST/Appr BEJ; ST HW-ST/Appr KLF; ST HW-ST/Appr Mch; ST HW-ST/Appr SAN; ST HW-ST/Appr Ulm
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 156 | 159.5 | 165.5 | 169.5 | 173.5 | 173.5 | 173.5 | 173.5 | 173.5 | 175 | 175 | 175 | 2043
Sum in MM | 169 | 173 | 175 | 184 | 203 | 209 | 229 | 241 | 230 | 240 | 244 | 253 | 2551
Sum in Hr. | 24071 | 24721 | 25198 | 26805 | 29661 | 30522 | 33376 | 34905 | 33056 | 34389 | 34945 | 36077 | 367726
Delta in MM | -13 | -14 | -10 | -15 | -29 | -35 | -55 | -67 | -57 | -65 | -69 | -78 | -508
Delta in Hr. | -1459 | -1541 | -1016 | -1955 | -4143 | -5004 | -7858 | -9387 | -7538 | -8676 | -9232 | -10364 | -68169
Consultant (Eur) | 440950 | 459280 | 477920 | 506960 | 562550 | 683360 | 731170 | 762680 | 759920 | 612950 | 691285 | 777935 | 7466960
Material (Eur) | 147200 | 145050 | 127550 | 91360 | 94800 | 169250 | 185550 | 195160 | 163850 | 122250 | 143050 | 194850 | 1779920
Miscellaenous (Eur) | 622659 | 675402 | 628492 | 729442 | 290967 | 834667 | 1251567 | 743567 | 601867 | 1084367 | 1327017 | 874317 | 9664331
Travel (Eur) | 70601 | 78898 | 87092 | 86492 | 97867 | 116217 | 108517 | 109517 | 71817 | 52117 | 64517 | 60317 | 1003969
NRE (Eur) | 100000 | 126000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426000
License (Eur) | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
Certification (Eur) | 407558 | 426704 | 475000 | 384000 | 175000 | 699000 | 1125000 | 612000 | 516500 | 1012900 | 1246500 | 783500 | 7863662
Others (Eur) | 44500 | 43800 | 46400 | 38950 | 18100 | 19450 | 18050 | 22050 | 13550 | 19350 | 16000 | 30500 | 330700
Department load from : ST SW-ST AAL; ST SW-ST ATL; ST SW-ST BEJ; ST SW-ST KLF; ST SW-ST Mch; ST SW-ST SAN; ST SW-ST Ulm
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 130 | 135 | 145 | 144 | 152 | 152 | 152 | 152 | 153 | 153 | 154 | 154 | 1776
Sum in MM | 140 | 147 | 162 | 159 | 181 | 191 | 208 | 231 | 224 | 234 | 252 | 288 | 2417
Sum in Hr. | 20688 | 22106 | 24429 | 24153 | 27833 | 29173 | 32107 | 35759 | 34291 | 35553 | 37843 | 42906 | 366841
Delta in MM | -10 | -12 | -17 | -15 | -29 | -39 | -56 | -79 | -71 | -81 | -98 | -134 | -641
Delta in Hr. | -1206 | -1713 | -2326 | -2217 | -4561 | -5901 | -8835 | -12487 | -10888 | -12150 | -14313 | -19376 | -95973
Consultant (Eur) | 1618150 | 1587890 | 1428100 | 1230300 | 1342100 | 1451375 | 1590200 | 1944000 | 2375100 | 2599100 | 2826600 | 3319500 | 23312415
Material (Eur) | 20850 | 22230 | 23690 | 26500 | 30150 | 30850 | 34350 | 30200 | 28650 | 31165 | 31074 | 33542 | 343251
Miscellaenous (Eur) | 118188 | 129338 | 115038 | 147413 | 208213 | 151513 | 170363 | 257413 | 225413 | 389418 | 186718 | 269918 | 2368946
Travel (Eur) | 77488 | 79188 | 70838 | 103313 | 149213 | 115013 | 125613 | 145363 | 147863 | 138063 | 123163 | 151263 | 1426381
NRE (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000
License (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Certification (Eur) | 10000 | 21000 | 0 | 15000 | 24500 | 2500 | 10000 | 75000 | 45000 | 20000 | 27000 | 75000 | 325000
Others (Eur) | 30700 | 29150 | 44200 | 29100 | 34500 | 34000 | 34750 | 37050 | 32550 | 31355 | 36555 | 43655 | 417565

## SW
Department load from : SW Engines AAL; SW open OS AAL; SW PC SW AAL; SW Engines ATL; SW open OS ATL; SW PC SW ATL; SW UI&App. ATL; SW Engines BEJ; SW PC SW BEJ; SW UI&App. KLF; SW Appl Mch; SW Engines Mch; SW PC SW Mch; SW UImch Mch; SW UI&App. SAN; SW UI&App. Ulm
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 203.3 | 206.9 | 213.9 | 222.9 | 227.9 | 228.9 | 228.9 | 229 | 229 | 229 | 229 | 229 | 2677.7
Sum in MM | 227 | 232 | 234 | 239 | 273 | 308 | 329 | 366 | 378 | 397 | 398 | 389 | 3768
Sum in Hr. | 32456 | 33206 | 33616 | 34252 | 38705 | 43129 | 45755 | 50485 | 51974 | 54397 | 54412 | 53170 | 525557
Delta in MM | -23 | -25 | -20 | -16 | -45 | -79 | -100 | -137 | -149 | -168 | -169 | -160 | -1091
Delta in Hr. | -3525 | -3698 | -2985 | -2118 | -5736 | -10029 | -12655 | -17372 | -18861 | -21284 | -21299 | -20057 | -139617
Consultant (Eur) | 3062045 | 3815445 | 4370715 | 4591921 | 5144340 | 6053090 | 5567160 | 6060035 | 6512105 | 6341390 | 6444860 | 6521060 | 64484166
Material (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Miscellaenous (Eur) | 193770 | 711689 | 118632 | 718657 | 312688 | 540763 | 181688 | 477063 | 336769 | 592425 | 141775 | 436525 | 4762444
Travel (Eur) | 95270 | 121489 | 107432 | 119957 | 113788 | 122263 | 115688 | 138563 | 119269 | 126725 | 123875 | 115925 | 1420244
NRE (Eur) | 0 | 50000 | 0 | 200000 | 150000 | 100000 | 0 | 0 | 180000 | 100000 | 0 | 0 | 780000
License (Eur) | 52800 | 505300 | 5300 | 352800 | 12000 | 310300 | 47800 | 310300 | 28300 | 346800 | 9000 | 311700 | 2292400
Certification (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others (Eur) | 45700 | 34900 | 5900 | 45900 | 36900 | 8200 | 18200 | 28200 | 9200 | 18900 | 8900 | 8900 | 269800
Department load from : SW Layer1 AAL; SW PL1 AAL; SW PL2 AAL; UMTS 3G PL All; UMTS 3G SW PL1 All; SW Layer1 ATL; SW PL1 ATL; SW PL2 ATL; SW Layer1 BEJ; SW PL1 BEJ; SW PL2 BEJ; SW Prod Var BEJ; SW Layer1 KLF; SW PL1 KLF; SW PL2 KLF; SW Layer1 Mch; SW PL1 Mch; SW PL2 Mch; SW PL1 SAN; SW Layer1 Ulm; SW PL1 Ulm; SW PL2 Ulm
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 294.5 | 305.5 | 315.5 | 320.5 | 331.5 | 335.5 | 339.5 | 341.5 | 342.5 | 341.5 | 341.5 | 341.5 | 3951
Sum in MM | 289 | 298 | 305 | 316 | 343 | 363 | 373 | 385 | 413 | 426 | 444 | 452 | 4407
Sum in Hr. | 42623 | 43869 | 45012 | 46871 | 51120 | 54263 | 56034 | 57824 | 61613 | 63805 | 66432 | 67579 | 657045
Delta in MM | 5 | 8 | 10 | 5 | -11 | -28 | -33 | -44 | -70 | -84 | -102 | -110 | -456
Delta in Hr. | 743 | 1334 | 1797 | 925 | -1854 | -4433 | -5640 | -7136 | -10758 | -13085 | -15712 | -16859 | -70676
Consultant (Eur) | 3137145 | 3358465 | 3427977 | 3687392 | 3894369 | 4013329 | 3847629 | 3786734 | 3925244 | 3956871 | 3654999 | 3640119 | 44330273
Material (Eur) | 6600 | 22100 | 17600 | 13600 | 14600 | 14600 | 12100 | 9100 | 8600 | 17000 | 8000 | 8000 | 151900
Miscellaenous (Eur) | 790092 | 256434 | 497026 | 454736 | 445092 | 465292 | 393142 | 479842 | 666467 | 429295 | 397495 | 349795 | 5624708
Travel (Eur) | 153104 | 199484 | 199230 | 212936 | 209792 | 268992 | 210542 | 287542 | 232167 | 222495 | 209495 | 232995 | 2638774
NRE (Eur) | 574038 | 0 | 191346 | 170000 | 170000 | 0 | 0 | 170000 | 1000 | 1000 | 1000 | 1000 | 1279384
License (Eur) | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000 | 150000 | 150000 | 0 | 900000
Certification (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others (Eur) | 62950 | 56950 | 106450 | 71800 | 65300 | 46300 | 32600 | 22300 | 133300 | 55800 | 37000 | 115800 | 806550

## MD
Department load from : MD MDDevl AAL; MD MDDevl ATL; MD MDDevl BEJ; MD MDDevl KLF; MD MDDevl Mch; MD MDDevl SAN; MD MDDevl Ulm
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 136 | 135 | 136 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 1649
Sum in MM | 135 | 159 | 171 | 183 | 195 | 197 | 210 | 201 | 198 | 209 | 210 | 197 | 2266
Sum in Hr. | 19240 | 22698 | 24494 | 25943 | 27302 | 27228 | 28531 | 27251 | 26566 | 27812 | 27787 | 25938 | 310790
Delta in MM | 1 | -24 | -35 | -45 | -57 | -59 | -72 | -63 | -60 | -71 | -72 | -59 | -617
Delta in Hr. | 318 | -3307 | -4936 | -6051 | -7410 | -7336 | -8639 | -7359 | -6674 | -7920 | -7895 | -6046 | -73255
Consultant (Eur) | 230000 | 323000 | 351500 | 285000 | 300000 | 300000 | 265000 | 245000 | 225000 | 225000 | 185000 | 170000 | 3104500
Material (Eur) | 138500 | 181000 | 198800 | 236800 | 262500 | 250000 | 215000 | 228900 | 228600 | 437600 | 272600 | 252100 | 2902400
Miscellaenous (Eur) | 257200 | 232400 | 225200 | 230300 | 248000 | 247000 | 242100 | 227800 | 233500 | 238100 | 238200 | 219700 | 2839500
Travel (Eur) | 202200 | 226000 | 220800 | 227300 | 245000 | 244000 | 240100 | 226800 | 232500 | 237100 | 237200 | 218700 | 2757700
NRE (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
License (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Certification (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others (Eur) | 55000 | 6400 | 4400 | 3000 | 3000 | 3000 | 2000 | 1000 | 1000 | 1000 | 1000 | 1000 | 81800

## HW
Department load from : HW BB AAL; HW EMC/AntAal AAL; HW LPD AAL; HW RFAal AAL; HW SP AAL; HW BB ATL; HW EMC/Ant ATL; HW HW PL ATL; HW LPD ATL; HW RF ATL; HW SP ATL; HW BB BEJ; HW EMC/AntBEJ BEJ; HW LPD BEJ; HW RFBEJ BEJ; HW BB KLF; HW EMC/AntKLF KLF; HW HW PL KLF; HW LPD KLF; HW RFKLF KLF; HW SP KLF; HW BB Mch; HW EMC/AntMch Mch; HW HW PL Mch; HW LPD Mch; HW RFMch Mch; HW SP Mch; HW EMC/Ant SAN; HW BB Ulm; HW EMC/AntUlm Ulm; HW HW PL Ulm; HW LPD Ulm; HW RFULM Ulm; HW SP Ulm
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 350 | 352 | 353 | 353 | 353 | 350 | 349 | 349 | 349 | 349 | 349 | 350 | 4206
Sum in MM | 365 | 386 | 399 | 416 | 435 | 450 | 488 | 534 | 533 | 519 | 498 | 513 | 5538
Sum in Hr. | 50070 | 53176 | 54677 | 56707 | 58844 | 60602 | 65247 | 70901 | 70083 | 68048 | 64746 | 66412 | 739513
Delta in MM | -15 | -34 | -46 | -63 | -82 | -100 | -139 | -185 | -184 | -170 | -149 | -163 | -1332
Delta in Hr. | -2254 | -5026 | -6392 | -8422 | -10559 | -12818 | -17584 | -23238 | -22420 | -20385 | -17083 | -18622 | -164803
Consultant (Eur) | 1071260 | 2628683 | 1335610 | 2976175 | 1306850 | 3064405 | 930250 | 3130905 | 1022930 | 2265460 | 1029270 | 1912266 | 22674064
Material (Eur) | 50000 | 37200 | 180000 | 47800 | 32100 | 63300 | 140100 | 40300 | 30100 | 120300 | 30100 | 40200 | 811500
Miscellaenous (Eur) | 695738 | 704419 | 799864 | 1028717 | 376023 | 611813 | 804663 | 694008 | 530993 | 454356 | 696717 | 286510 | 7683821
Travel (Eur) | 157488 | 166269 | 164114 | 185167 | 180973 | 187763 | 190013 | 189958 | 192243 | 199706 | 180267 | 190760 | 2184721
NRE (Eur) | 30000 | 362000 | 355000 | 675000 | 60000 | 135000 | 510000 | 220000 | 264000 | 100000 | 250000 | 0 | 2961000
License (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Certification (Eur) | 60000 | 80300 | 37000 | 44000 | 93000 | 146000 | 66600 | 73000 | 14000 | 120000 | 116000 | 60000 | 909900
Others (Eur) | 448250 | 95850 | 243750 | 124550 | 42050 | 143050 | 38050 | 211050 | 60750 | 34650 | 150450 | 35750 | 1628200

## PL
Department load from : PG PL-T GSM AAL; PG PL-T GSM ATL; PG PL-T GSM BEJ; PG PL-T GSM KLF; PG PL-T UMTS KLF; PG PL-T GSM Mch; PG PL-T UMTS Mch
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 21 | 22 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 283
Sum in MM | 24 | 24 | 34 | 40 | 42 | 48 | 51 | 53 | 52 | 53 | 52 | 50 | 525
Sum in Hr. | 3314 | 3431 | 4725 | 5385 | 5720 | 6448 | 6810 | 7014 | 6934 | 7054 | 6774 | 6537 | 70146
Delta in MM | -3 | -2 | -10 | -16 | -18 | -24 | -27 | -29 | -28 | -29 | -28 | -26 | -242
Delta in Hr. | -359 | -313 | -1313 | -1973 | -2308 | -3036 | -3398 | -3602 | -3522 | -3642 | -3362 | -3125 | -29953
Consultant (Eur) | 13000 | 13000 | 23000 | 26000 | 26000 | 26000 | 26000 | 26000 | 26000 | 25000 | 13000 | 13000 | 256000
Material (Eur) | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 5500
Miscellaenous (Eur) | 23550 | 25550 | 39350 | 43575 | 44625 | 50375 | 55000 | 55500 | 55050 | 55500 | 56000 | 56000 | 560075
Travel (Eur) | 23550 | 25550 | 39350 | 43575 | 44625 | 50375 | 55000 | 55500 | 55050 | 55500 | 56000 | 56000 | 560075
NRE (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
License (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Certification (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Total
Total R&D
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 1290.8 | 1315.9 | 1352.9 | 1371.9 | 1399.9 | 1401.9 | 1404.9 | 1407 | 1409 | 1409.5 | 1410.5 | 1411.5 | 16585.7
Sum in MM | 1349 | 1419 | 1480 | 1537 | 1672 | 1766 | 1888 | 2011 | 2028 | 2078 | 2098 | 2142 | 21472
Sum in Hr. | 192462 | 203207 | 212151 | 220116 | 239185 | 251365 | 267860 | 284139 | 284517 | 291058 | 292939 | 298619 | 3037618
Delta in MM | -58 | -103 | -128 | -165 | -271 | -364 | -482 | -604 | -619 | -668 | -687 | -730 | -4887
Delta in Hr. | -7742 | -14264 | -17171 | -21811 | -36571 | -48557 | -64609 | -80581 | -80661 | -87142 | -88896 | -94449 | -642446
Consultant (Eur) | 9572550 | 12185763 | 11414822 | 13303748 | 12576209 | 15591559 | 12957409 | 15955354 | 14846299 | 16025771 | 14845014 | 16353880 | 165628378
Material (Eur) | 363150 | 408080 | 548140 | 416560 | 434650 | 528500 | 587600 | 504160 | 460300 | 728815 | 485324 | 529192 | 5994471
Miscellaenous (Eur) | 2701197 | 2735232 | 2423602 | 3352840 | 1925608 | 2901423 | 3098523 | 2935193 | 2650059 | 3243461 | 3043922 | 2492765 | 33503825
Travel (Eur) | 779701 | 896878 | 888856 | 978740 | 1041258 | 1104623 | 1045473 | 1153243 | 1050909 | 1031706 | 994517 | 1025960 | 11991864
NRE (Eur) | 704038 | 538000 | 546346 | 1245000 | 380000 | 235000 | 510000 | 390000 | 445000 | 401000 | 251000 | 1000 | 5646384
License (Eur) | 52800 | 505300 | 25300 | 372800 | 12000 | 460300 | 197800 | 310300 | 328300 | 496800 | 159000 | 311700 | 3232400
Certification (Eur) | 477558 | 528004 | 512000 | 443000 | 292500 | 847500 | 1201600 | 760000 | 575500 | 1152900 | 1389500 | 918500 | 9098562
Others (Eur) | 687100 | 267050 | 451100 | 313300 | 199850 | 254000 | 143650 | 321650 | 250350 | 161055 | 249905 | 235605 | 3534615

## Rest
Department load from : PD OS AAL; TS TS AAL; BA BA Mch; CTO NG Mch; IPR IPR Mch; IT IT Mch; PD OS Mch
Display from : | fromMonth=10 |  | until :
| Oct 2004 | 2004-11-01 | Dec 2004 | 2005-01-01 | 2005-02-01 | Mar 2005 | 2005-04-01 | May 2005 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | Sum
Own Capacity (MM) | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 114
Sum in MM | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 114
Sum in Hr. | 1208 | 1208 | 1208 | 1208 | 1208 | 1208 | 1208 | 1208 | 1208 | 1208 | 1208 | 1208 | 14496
Delta in MM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta in Hr. | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -18
Consultant (Eur) | 989464 | 980464 | 991364 | 981364 | 981364 | 991364 | 976614 | 971864 | 981864 | 971864 | 971868 | 989892 | 11779350
Material (Eur) | 0 | 0 | 4000 | 10000 | 10000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 33000
Miscellaenous (Eur) | 77933 | 23033 | 22483 | 63433 | 22433 | 22183 | 51933 | 100933 | 22683 | 21933 | 22433 | 22687 | 474100
Travel (Eur) | 14200 | 19300 | 18500 | 18700 | 18700 | 18200 | 18200 | 17200 | 18700 | 18200 | 18700 | 18700 | 217300
NRE (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
License (Eur) | 60000 | 0 | 0 | 30000 | 0 | 0 | 30000 | 80000 | 0 | 0 | 0 | 0 | 200000
Certification (Eur) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others (Eur) | 3733 | 3733 | 3983 | 14733 | 3733 | 3983 | 3733 | 3733 | 3983 | 3733 | 3733 | 3987 | 56800