## Slide 1: SG2 platform – reporting – 75 generation
Platform timeline
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
M0 30.06.2004
M0 SW 20.08.2004
S0 HW 27.08.2004
M1 30.11.2004
S15 03.12.2004
S2 02.03.2005
S25 24.06.2005
WM AS (TA) 27.06.2005
AS 01.07.2005
S3 HW 01.07.2005
PS (1st) 05.08.2005
MKA 5.08.2005
S3 26.08.2005
DS (1st) 15.09.2005
WM S4 HW 30.09.2005
S4 01/2006
M3 02/2006
Timeline
Technical aspects
Major threats
milestones, timeline, primavera planning (base M1 schedule):
+ S2 maturity reached with miner restrictions
- S25 highly endangered, DS under investigation, SW re-planning ongoing
  finalized planning will be available 10/03/2005
o PV planning under investigation, resource overload in some areas
technical aspects, next steps
o support of B1+ production
  ATI Sample delivery to be secured for B1+
  SW support available but not tested on new ATI samples
  secure SW deliveries for production
major threats
- CR buffer (CA + DL activities) exceeded for some components
  agreement with PD management to set CRs related to those components on hold
- no CR buffer left regarding ST1 activities
- CR budget (consultant) is currently not secured for e.g. CR438 Infusio ca. 200K Euro
  budget is considered in the last PD planning
  SWC PO status unknown, AI TBD
- Consultant PO ordering (SWC) was again fully stopped in CW7/8
  2nd time since mid of Jan., delay in S25 expected
  install PO monitoring in SWC, SWP, AI TBD
- POC 75 (MMB 1.5) is currently not secured due to resource conflicts at Comneon (changed prios and new tasks at Comneon)
  proposal from SWP to hire PSE resources, status PO unknown, impact to project schedule open, AI TBD
- additional budget savings at SWC required (2 Mio Euro)
  impact to Sg2 rel1 TBC, AI TBD
Notes: <number>
<footer>
<header>
<date/time>

## Slide 2: SG2 products – Minos
Minos
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
milestones, timeline, primavera planning (base M1 schedule):
+ S2 declared on time
- S25/DS under investigation, refer to platform status
+ Primavera planning on track, investigation regarding resource overload started
technical aspects, next steps
o Evaluation of new ATI chip ongoing (at ATI Toronto)
+ HW to SW requirements agreed for SIP6.
o B1+ prototype shop:
=> planned: start B1+ first shot 07.03.05, B1+ Main run 14.03.05
=> preparing of test line ongoing (base pre-SIP6-SW)
major threats
- SW schedule re-planning (CA) ongoing => high risk for shifting the S25 and DS
- Delivery date of new ATI (A21) samples delayed (best case just in time for B1+)
=> SW support of new ATI A21 not testable
=> Late ATI SW-delivery is root cause for shifting SIP6 SW-delivery by 2 weeks
=> High risk for planned timeline B1+ run due to missing test and stabilization phase
in prototype shop (originally planned 2 weeks)
Additional delay for B1+ SW delivery due to tooling problems (delivery CDB to IDB interrupted)
=> start B1+ delayed by at least 3 days

## Slide 3: SG2 products – Hydra
Hydra
milestones, timeline, primavera planning (base M1 schedule):
+ S2 declared on time
S25/DS under investigation, refer to platform status
+ Primavera planning on track
technical aspects, next steps
+ B1+ TO
o B1+ population start 9.3.05. B1+ Main run 15.3.05. Timeline on risk.
o Assembly Lumberg start 7.3.05
o Securing 2nd source 768Mbit memory from AMD (3 die)
+ HW to SW requirements agreed for SIP6.
major threats
- PI Engineering – Re-new contracts possible?
Lumberg has got financial difficulties
SW schedule re-planning (CA) ongoing => potential risk for S25 and DS
- Late delivery of ATI chip A21 samples critical (best case just in time for B1+) => SW support of new ATI A21 not testable => Late ATI SW-delivery is root cause for shifting SIP6 SW-delivery by 2 weeks => High risk for planned timeline B1+ run due to missing test and stabilisation phase in prototype shop (originally planned 2 weeks)
PD-team status [Karsten Roar Sørensen, PL-T]

## Slide 4: Backup

## Slide 5: X75 SG2 platform - Highlights
software platform
+ S2 of SW and SP declared 02.03.2005 on schedule; 90% of QA mandatory requirements fulfilled
+ Only 5 C15 declarations open, which are still on track
- Budget Impacts: more detailed update of plan expected from CA until 09.03.05 latest
- Preparing B1+ production SW (SIP6) ongoing; still on risk;
- Workload cannot be covered by PL-SW-Variant and one Co-PL (4 additional colleagues were planned until approval start). Timeline highly endangered! "
+[ST1] S2 signed & delivered for platform, Hydra, Minos
-[ST1] from now, there is no CR buffer available
-[ST1] Delay CQ<->Continuous Integration under clarification
-[ST1] consequences of the late component C3 milestones under clarification
(due to new delivery agreement with CA is the risk reduced)
- [ST1] not all requirement/specification are available to finalize test specification
eg. BT multipoint 50 % missing, i-mode
- [ST1] edge tests in real network not clarified, SD can’t support
- [ST2] R&TTE mandated EDGE RF test cases without validation on test systems
- [ST2] Resulting a workshop regarding OPWV Messaging/Browser between SW-CA and
ST confidence to reach GCF certification as planned
system test
platform

## Slide 6
X75 SG2 platform - Highlights
EGPRS
modem
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
S-GOLD 2
hardware platform
+ S2 can be signed with restrictions (some requirements to SW TBC)
+ Malpha.4 tape out done. Board assembling started. Finalization planned until cw10.
o Step up converter concept discussion (NSC vs. Fairchild solution) ongoing. Platform recommendation is the Fairchild solution. Product measurements are ongoing and should be finalized until end of cw10.
Requirements to SW’ list review ongoing. Finalization scheduled for 2005-03-03.
- First ATI W2182 (A21) samples delayed. No impact to product B1+ runs. Only Malpha.4 assembling effected. Risk: No option for pre-testing of new SW.
+ S2 granted
o characterization activities ongoing
o enhanced ball material (solder4) is too late for X75 products. Earliest for Sep.05
- Problems with AFC for Edge popped up – work started at IFX/CN
+ PA 9026 cut 5.5 samples received: first measurements show good results, additional cut 5.7 (improved complex termination) will be delivered in time for B1+ main run
Tests on FTA tester: still blocked by test case problem (fix expected for Monday)
+ Debugging process Comneon interface / Comneon / COM firmware / IFX firmware: IFX interface under discussion
- Severe Edge AFC problem detected, solution leads to significant efforts @ Infineon and Comneon, financial discussion ongoing
+ Approval for S2 given with minor restrictions
- Problems to get SW for IOT Nokia next week
Notes: <number>
<footer>
<header>
<date/time>