## Slide 1: SG2 platform – reporting – 85 generation
roadmap planning
Platform Timeline
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
status
milestones, timeline, primavera planning
- target M0 31.03.2005 looks today not feasible from SW platform point of view (refer to major threats)
o later milestones are not yet verified
o primavera planning in platform projects HW/ST1 started
development aspects
+ Feature discussion for rel2 finished
  SW top level requirements frozen
  HW feature list frozen
+ M@4 tape out done covering latest 85 product requirements
o collection of HW to SW requirements started
major threats
- SW top level requirements are not assigned to component projects
  transfer requirements to SW feature list, AI CTO TS CW10
  start C0/CS0 investigation in DL/CA CW11
- SW resources are currently not sufficient
  under clarification: several (co) PL SW, primavera support, AI SWP CW10
  under clarification: architects, support from component projects, AI SWC CW10
- SW planning not yet started
  start of primavera planning depending on support, AI refer to above
  SIP planning to be started on HW to SW requirements, CW12
- SW feature set does (partly) not fit to product stories, key OP feature missing
  no CR buffer/budget available to add or change SW feature, AI TBD?
- pre development SW solution w/o Gimmick chip is not closed yet
  multimedia feature open for Swift, Ibis..
  as fallback ATI Gimmick chip to be considered in stack up concepts (-> BCs endangered!)
M0 (rel2) target 03/2005
DS (rel2) target 02/2006
Notes: <number>
<footer>
<header>
<date/time>

## Slide 2: SG2 products – Polaris
Polaris
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
milestones, timeline, PrimaVera planning
M0 03/05 ( HW reached M0 status 28.02.05)
S0 04/05
M1 05/05
M0 PV Planning done (except SW)
technical aspects, next steps
M0 HW/MD status reached
A1 TO scheduled 31.03.05
major threats
- Platform SW M0 03/05 seems not to be feasible -> DS 02/06 on risk

## Slide 3: SG2 products - Swift/ Ibis
Swift/
Ibis
milestones, timeline, PrimaVera planning
Swift and Ibis rough hardware project timeline worked out >> DS targets reachable
Initial Swift Primavera Workshop 07.03.2005
technical aspects, next steps
No decision on Swift and Ibis stack-up yet because of ongoing battery selection process
Swift DS delay > 2weeks if no decision until tomorrow and if other solution than 1 or 3
  1) housing 90/46/17, Sanyo customized >> too expensive, former working basis
  2) housing 94/46/17, Panasonic standard >> too big
  3) housing 90/46/16, Sanyo standard >> mechanical compromises, Ibis stack-up?
  4) housing ?92/48/17?, Panasonic alternative >> evaluation ongoing, first output today
ATI Chipset decision pending
  Swift and/or Ibis with or without ATI2282 >> decision needed until 18.03.2005
  Output of CTO investigation on 09.03.2005
  ATI population option will increase length of Swift and Ibis by ~0.7 mm
major threats
Swift BOM target >> cannot be met right now
  ~70€ over life cycle needed to reach 7,5% Ebit
  first BOM calculation of 04.03.2005 indicate 95€ at launch time
Platform SW timeline missing >> overall project planning not possible
  SW milestone planning and SW prototype shop support needed

## Slide 4: SG2 products - Baya/Macaw
Baya/
Macaw
milestones, timeline, PrimaVera planning
Schedule in process – target is 10.03.05 for the first draft of the mechanical (main) schedule.
Foreseeable that the M0 date (31.03.05) is endangered.
technical aspects, next steps
Mechanical concept in process.
PCB placement in process.
PD team is announced.
major threats
Battery not selected – big impact to mechanical concept.
Display definition not finalized.
One or two speaker concept not decided – impact to design.
Feature set close to Swift but selling price target for Baya 20,-€ below Swift.
No designer in the team.
Macaw unclear – where will it be done, is a team announced ...