## Slide 1: SGL products Adonis
Schedule/PV/Milestones:
M0: 22.10.04 ( 25.10.05)  S2: 29.03.05  DS: 11.07.05
S0: 29.10.04 ( 01.11.05)  S25: 27.04.05  S4: 11.07.05
M1: 10.12.04 ( 23.12.05)  S3: 30.05.05  M3: 08.08.05
DS deviation of current PV plan is 3 days
Major threats
Further delay of B1+ tape out => potential delay of DS
HW
B1+ tape out delayed by 2 days from 09.03.05 to 11.03.05 because root cause for high power consumption in talk and idle and countermeasures for self-interference and for low frequency emissions via headset have not found been found.
SW
Due to special CeBit SW preparation all bug fixes have to be copied from the stabilization branch to the normal CDB – additional unplanned effort but no effect on timeline
Mechanics
Hard tool parts planned to be used in B1+ were already used for B1.2 – first tests indicated good quality
Prototyping:
See HW/Major threats