## Slide 1: SGL products M65 Rescue Edition
Schedule/PV/Milestones:
M0: 15.11.04 ( 15.11.05)
S4: 28.02.05 ( 28.02.05)
DS: 04.03.05 ( 04.03.05) Ready for CeBit
Major threats
Project finalized, no further activities planned except for normal sustain engineering.
HW
Main PCB and MMI board in “status 20”, - released for production.
SW
Special “Rescue” software SVN44 released. No further versions planned.
Mechanics
Red plastics, keypad and metal clamp unlimited released for production.
Production
1500 phones planned for CeBit in CW09 ( Done)
500 phones planned for CW10 ( Done)
No more phones planned in production.
Ole Byrdal COM MD PD PGG AAL / 11. March 2005