## Slide 1: SGL Platform
Schedule/PV/Milestones:
M0: 01.03.05 ( 10.06.04)  S2: N/A  DS: N/A
S0: N/A  S25: 18.03.05  S4: 01.04.2006
M1: 01.03.05 ( 22.10.04)  S3: 15.12.05  M3: 01.06.2006
SGL Platform planning title has been opened and is currently under planning
Equivalent PV account needs to be opened
Major threats
Introduction of lead-free soldering – new problems appeared in Phoenix/Sirius B1+ boards
Stabilization period between SW S25 and first DS only 9 weeks
HW
First risk release of SGL with G15 mask done.
B6E RF-solution implemented in Adonis – high power consumption in talk mode under investigation.
Use of SGL G15 and Mozart+/Twigo+ not possible for all products due to huge stocks from R65 generation
SW
Phase II SW team installed lead by A. Betting for remaining R65 projects
Z-IDB4 will be set up on 18.04.05 and will be used for X75 products Phoenix, Sirius, Adonis & Aries
ASP solution has been found and major activities finished. Investigations on certain PTT applications ongoing.
S25 SW is very stable (see Phoenix/Sirius)
Improved PTT User Interface for Vodafone still can not be committed – investigations ongoing