## Slide 1: SGL products SP65
Schedule/PV/Milestones:
M1: 10.12.04 ( 10.12.04) DS: 23.03.05 (-)
S25: 20.01.05 ( 25.01.05 ) S4: 22.04.05 (-)
S3: 25.02.05 ( 28.02.05) M3: 20.05.05 (-)
Major threats
FCC type approval time line is tight. DS risk is less than 1week.
HW
No open issues.
SW
SVN47 available for DS. New release required to fulfil TMO requirements and to declare S4.
Mechanics
No open issues.
Production
Pilot series successfully completed.
Production start 17.03.05
Claus Dalmose COM MD PD PGG AAL / 11. March 2005