## Slide 1
EGOLDlite
Timeline
I0 09.04.2004  I3 30.10.2004
I1 08.06.2004  I4 30.12.2004
I2 13.08.2004 
- I3 delayed because of product SW stability (LL). Target for I3 E11/04. I4 not impacted.
SW test with LIBRA B6E A1 is ongoing.
Software platform
Hardware platform
EGOLDlite
Audio part integration is ongoing
Power saving concept is implemented and optimisation is ongoing
All of implementation for measurement is done and debugging is ongoing
call to tester and emergency call to BS is working
 X75 HW platform does not include HW which is explicitly used in EGOLDlite products. Such components (e.g. B/W display DORADO, slim 130 x 130 TFT display  FLAMINGO, …) are tracked in the related EGL product projects.
E-GOLDlite baseband chipset qualification is almost done, including:
The TEAKlite DSP qualification is done and optimisation is ongoing
For MCU, all the drivers are available now. The test cases coding is ongoing
MCU part qualification is planned to be done E12/04
EGOLDlite is an cost optimized baseband processor and based on a shrinked EGOLD V3 and SGOLDlite DSP targeting low tier products.
The development of the EGOLDlite is carried out in a pre-development project which covers EGL HW, SW and FW. The purpose of the predevelopment is to verify and test EGL for the secure application in product products. Lead product projects are LIBRA/DORADO with M3 05/05.
Notes: <number>
<footer>
<header>
<date/time>

## Slide 2: X75 product project highlights
Pegasus
M0 23.07.04  S15 15.11.04 S3 25.04.05
S0 17.08.04  S2 14.01.05 DS 30.05.05 (GCF)
M1 28.09.04  S25 02.03.05 S4 09.06.05
A1 SD2 sample run ongoing. B1 B6E TO done.
HW design related conflict between IRDA & Connectivity. High efforts for HW and SW will be needed for IRDA implementation, HW solution has to be fixed ASAP  B1+!!!
- Only one prototype line available in SHA. Suboptimal preparation for sample shop of different projects and efficiency in sample shop leads to delays of lower prioritized projects.
Dorado
M0 14.07.04  S2 19.01.05 S4 26.05.05
S0 30.07.04  S25 25.02.05 DS 19.05.05
M1 28.09.04  S3 14.04.05 M3 30.06.05
S15 24.11.04 PS 28.04.05
A1 evaluation is done. RF & BB performance quite good.
DORADO SW code size critical regarding 32Mbit. Optimisation of SW code size w/o feature change ongoing.
Libra
M0 14.07.04  S2 06.01.05 S4 20.05.05
S0 30.07.04  S25 22.02.05 DS 06.05.05
M1 17.09.04  S3 01.04.05 M3 30.06.05
S15 12.11.04  PS 15.04.05
Call in real network incl. voice done.
S15 declared.
B1 B6E sample run scheduled for CW49.

## Slide 3: 85 product project highlights
Flamingo
Malpha 03.11.04  S15 28.03.05 S4 05.12.05
M0 23.12.04 S2 30.0605 M3 30.12.05
S0 18.01.05 S25 06.10.05 M1 17.02.05 S3 24.10.05 MKA1 19.12.05 (105k, VKL)
- Malpha declared on 03.11.04.
First rough schedule does not reach MKA 11/05. Improvement ongoing.
- Request under investigation to declare M0 at Dec. 10 and S0 at Dec. 23 to use X-mas time (Dec. 27 to Jan. 8) for MD construction after design freeze.
Albatross
Malpha 03.11.04  S15 14.03.05 S4 19.10.05 M0 23.12.04 S2 26.05.05
S0 17.01.05 S25 03.08.05 M1 17.02.05 S3 02.09.05 MKA1 09.11.05 (115k, VKL)
- Malpha declared on 03.11.04
First rough schedule does not reach MKA 10/05. Improvement ongoing.
Request under investigation to declare M0 at Dec. 10 and S0 at Dec. 23 to use X-mas time (Dec. 27 to Jan. 8) for MD construction after design freeze.