## Slide 1
Platform SGL Highlights
Software platform
Hardware platform
S-GOLDLite
 Resource conflicts with X75 SG2 Platform (mainly bug fixing and CR handling)
 Delay in Audio features for the X75 generation has no impact on the overall timeline but SW schedule needs to be modified.
CR situation is critical (too many). Implementation of all “must” CRs in Phoenix and Sirius, including I-mode/Doja, is only possible in a 2nd SW-release, three weeks later.
Phase II SW team installed lead by A. Betting
Z-IDB4 will be set up on 18.04.05 and will be used for Phoenix, Sirius, Adonis & Aries
ASP
 CR to ”Voiceband over SGL” raised. This CR can be agreed for the platform but can not be implemented in all products. Test PCB based on Phoenix available.
 CR regarding use of Mozart+/Twigo+ raised. This CR can be agreed for the platform but can not be implemented in all products.
 Due to a huge stock of SGLite G12 mask material, switching back to G12 in Phoenix, Sirius, Adonis and Aries was requested. A respective CR for Phoenix and Sirius has been agreed. Adonis shall be the lead product for the G15 mask but its SW has to able to support both masks
A CR to reduce the communicated operation time of the new R65 products is planned
 Solution for ASP including the PaT solution is agreed for the R65 products. For the X75 Generation the PaT solution still needs to be agreed – no other solution is currently seen for the X75 generation.
Several signal tones are now louder (e.g. predialling tone) which are marked as idle tones and therefore have an upper limit of 130dB – this is not critical. However, adaptations will be made by creating a table showing new limits for all tones in different states (idle, call). Target is until 21.01.2005
Notes: <number>
<footer>
<header>
<date/time>

## Slide 2: Product Project Highlights – 65 Generation
CX65 Family
C65 Family
S65 Family
SK65
 M3 declared for CX65 and M65 on 14.01.2005
 SW R13 (SVN43) available on 28.01.2005, for CX65, CX70, and M65.
 ST & SW resources for finalizing CX70 secured. Extra ST available for I-Mode testing.
 CR to change of PCB material to halogen-free for M65 is still under evaluation; leads to BOM increase of 0.085 Euro
 First M65 Rescue prototype shop samples available. Bad SAR & antenna performance due to wrong mounted camera flex cable shielding - production will be informed!
 SW R13 (SVN44) for Rescue available on 31.01.05. Test of FFS and Mapfile in CW05
 CT66: There might be a business potential with Comcel in Columbia
 C66/C71 going for S4 by end of January, only for LAM market.
 C70 DS planned for 1st March; C70 S4 planned for 2nd March.
 Hera outdoor + Hera VGA rejected by the board because of bad business case.
 SP65: S25 declared - going for S3 25.02.05
 SP65: Samples of new rear cover and IMD foil received – quality is good. Rear cover is released by SPM. IMD foil release expected on 02.02.05
 SP65: Running change to lead free technology under discussion – request from lead free team
 HW S4 declared on 21.01.2005
 SW S4 was planned on 21.01.05 but has been significantly delayed due to missing overall SW-quality (timeline under clarification). It will be declared together with the other phase II projects for both the standard and the Blackberry variant. Impact on Z- IDB-4 to be checked.
 New Blackberry version 4.0 still not decided. Waiting for MP-Board decision.

## Slide 3: Product Project Highlights – Late Followers
Phoenix
Sirius
Aries
 Delay of Adonis B1 prototype shop due to delayed arrival of test fixtures in SSMC. First boards delivered on time using offline testing. B1-run finalized 3 days after schedule; no impact on B1+ tape out and project schedule.
 Principal Design Decision for Adonis done. Due to wrong hinge concept, agreed design will be reworked . M0 is planned on 04.03.2005.
Baya kick-off (Adonis II, TFT, MPix) done. Realization will be done on SGL platform with same PCB as Adonis. Due to wrong design assumptions, the Principal Design Decision was delayed by two weeks to 09.02.05 and the M0 to 18.03.2005.
Adonis
Family
 S2 declaration planned for 26.01.05. S2 maturity reached on time but due to an inconsistency in the SW-plan, CCQ suspended the S2 declaration until 04.02.05.
New SW-schedule available shows delayed S25 and S3 SW milestones with no effect on the DS milestone.
 Some “must”-CRs can probably not be available for DS (PoC GUI, I-mode/Doja)
Delay of flash memory delivery may lead to insufficient B1+ quantities at the agreed dates – still under clarification with the memory supplier.
M0 declared on 21.01.2005; S0 declaration, B1-TO and 80% mechanical data achieved on 28.01.2005
 Less than 7 months between S0 and DS is challenging and very risky
 SW-planning is z-IDB4 for Aries DS-SW - Risks: Stability, Phoenix/Sirius/Adonis delay
Plover
 SGL platform has been decided. Kick-off done on 21.01.05
 PD-team not fully staffed – main problem is missing nomination of RF and EA PPLs.
Principal Design Decision planned on 17.02.2005 and M0 planned on 01.04.05
 One stack-up sent to designers based on dimensions of 104x46x17.5mm. Additional stack up concepts still under investigation.