## Slide 1: Robin UMTS 1. Project Summary
Product description
6250 platform, Wolf4 follower project. Bar phone design, cost optimized feature set.
Excellent audio device, outstanding design and supporting music related NOP services
Project Management
PL-T: Klaus-Peter Bräuherr SPM: Jörg Hantschel PM: tbd BA: Wolfgang Steiner
Milestones:
M0 22 Apr 05 S15 15 Jul 05 S3 24 Feb 06 M3 tbd
S0 20 May 05 S2 16 Sep 05 DS 10 Mar 06
M1 17 Jun 05 S25 2 Dec 05 S4 7 Apr 06
Prototype builds overview
A1 25 May 05 B1 10 Aug 05 B1+ 26 Oct 05 B2 10 Jan 06
Costs
Total project development costs: 18,3 Mio € Development costs FY 04/05: 9,3 Mio €
BOM target: 100 € BOM actual: 110 €
Time to market summary
First bottom up planning done, strong dependency on in-time Wolf5 SW deliverables

## Slide 2: Robin UMTS 2. Major Progress and Achievments
Team/Resources/Skills
PPLs assigned, regular PD Team meetings installed
Partner and Contract Management
Regular Robin Telco with QCT installed
SW-Development (Platform, Drivers, Tools, UI)
Draft Feature List available
Mechanics
StackUp concept review done
Industrial design and stackup concepts are matching
Platform Components
Reuse of Wolf5 battery, Wolf4 stereo speaker, Wolf4 display,
General Project Management, Quality, Costs etc.
First BOM calculation based on Wolf4 done
Draft time scheduling done
HW Aal handover ongoing

## Slide 3: Robin UMTS 3. Risks, Problems and Corrective Actions
Partner and Contract Management
Risk: Insufficient Qualcomm support for Robin feasibility study (SW workshop, SW documentation, Robin feature set)
Severity: medium Possible impact: delay of feasibility studies and M0
Actions taken: First telco with SD done, get agreement on relevant next steps
SW-Development (Platform, Drivers, Tools, UI)
Risk: Strong dependency on Wolf5 deliverables from Qualcomm
Severity: medium Possible impact: no support of key features
Actions taken: strengthen information flow between W5 and Robin project teams