## Slide 1: Wolf 4 UMTS 1. Project Summary
Product description
First generation Siemens UMTS mobile phone based on Qualcomm´s MSM6250 chipset. Premium semi-automatic slider design, high quality finishing Tri-band GSM/GPRS, 176 x 220 pixels 2” display, 256k colours, BT interface, video telephony with dedicated CIF camera, 1.3 megapixel camera, RS MultiMediaCard slot, MP3 player, Push and Talk
Project Management
PL-T: Hans Beckers SPM: Jörn Watzke PM: Denis Jeanson BA: Sebastian Kuritke
Milestones:
M0 20.12.04  S15 18.03.05 S3 22.09.05 M3 23.12.05
S0 26.01.05  S2 13.05.05 DS 04.11.05
M1 18.02.05  S25 22.07.05 S4 16.12.05
Prototype builds overview
A1 23.12.04  B1 24.03.04 B1+ 03.06.05 B2 19.08.05
Costs
Total project development costs: €37.7M (direct 26.6M) Development costs FY 04/05:
BOM target: €125 (€117) BOM actual: €124
Time to market summary
No delays. Project schedule is very tight and dependent on software deliveries from Qualcomm.

## Slide 2: Wolf 4 UMTS 2. Major Progress and Achievements
HW-Development (BB, RF, EMC/Antenne)
A1 evaluation gave valuable feedback (UMTS receive sensitivity and 1.6Mhz spurious)
Platform Components
Received first displays, batteries, speaker modules
General Project Management, Quality, Costs etc.
Project schedule is on track and committed by all project leads
Development - and product cost optimized (target for M1: business case improved)
Product is well received by our operators (pre-selected for product hero @ Vodafone)
A1 PCB made first calls on 900, 1800 GSM bands and 2100 UMTS band.
First Wolf 4 B1 phone samples will be available within 2 weeks

## Slide 3: Wolf 4 UMTS 3. Risks, Problems and Corrective Actions
HW-Development (BB, RF, EMC/Antenna)
Risk: EMC concept of the MMI flex
Severity: high Possible impact: self-interference and possibly a time-to-market delay
Actions taken: several (7) test flex´s defined based on different shielding concepts / different MMI Flex stack up concepts and different materials (Ag paste versus mesh Ra-Cu). Test flex´s ordered from different suppliers (Nitto, Ichia & Career)
SW-Development (Platform, Drivers, Tools, UI)
Risk: dependency on Wolf 5 software deliveries from Qualcomm
Severity: high Possible impact: feature decrease and possibly a time-to-market delay
Actions taken: Wolf 4 and Wolf 5 teams working closely together with Qualcomm to track the situation and define corrective measures.
  Remark: Project team is staffed but keeps changing (i.e. All baseband development transferred before M1 from Roke Manor Research to München). New project leads for BB (twice), ST1, ST2, CCQ QM-HW, CCQ-Service and AD.