## Slide 1: Wolf 5 UMTS 1. Project Summary
Product description
Lead project 6250, first in-house UMTS phone. Key features: Full-featured GPS navigation, Brillant 2,2 inch QVGA display, 2MPix camera, 2nd video telephony camera, RS-MultiMediaCard, Bluetooth, RDS-Radio
Project Management
PL-T: Thomas Engelhardt SPM: Jörn Watzke PM: Ralf Plitzner BA: Sebastian Kuritke
Milestones:
M0 02.07.04  S15 27.01.05  S3 27.07.05 M3 11.11.05
S0 19.08.04  S2 08.03.05 (22.3.05) DS 23.09.05
M1 22.10.04  S25 17.05.05 S4 27.10.05
Prototype builds overview
A1 23.07.04  A1+ 17.11.04  B1 10.01.05  B1+ 23.03.05 B2 31.05.05
Costs
Total project development costs: 49‘ € Development costs FY 04/05: 39‘ €
BOM target: 129€ BOM actual: 134,57€
Time to market summary
Original DS is still feasible. Intensive risk mitigation activities are required on 2 main areas of concern:
1. SW development on QCT side: QCT late in feature implementation, de-featurization likely
2. HW optimization on RMR side: Slow progress, support by MD necessary, intermediate layout cycles may be needed.

## Slide 2: Wolf 5 UMTS 2. Major Progress and Achievements
HW-Development (BB, RF, EMC/Antenne)
Support by PD (MCH and KLF) substancially improved the development status of RMR and our confidence level (RF, EA).
SW-Development (Platform, Drivers, Tools, UI)
Cebit software build available in time.
Enables stable video telephony, streaming, video playback and navigation demonstration.
Mechanics
First (B1) plastics available, mechanics on time
B1+ phones will be manufactured in time, i.e. by 21.03.05

## Slide 3: Wolf 5 UMTS 3. Risks, Problems and Corrective Actions
SW-Development (Platform, Drivers, Tools, UI)
Risk: QCT: SW implementation behind schedule. QCT unable to accelerate further
Severity: high Possible impact: DS delay or de-featurisation
Actions taken: 1) Regular review of SW implementation status on-site at QCT San Diego
2) Regular meetings to identify acceptable de-featurisation potentials (CRs)
3) Implementation of integration mgr. temporarily in SD for daily status controlling
4) Steering commitee: Negotiations on „must have“ features, in turn commitment from QCT on „implementation complete milestone“ by 30.04. to keep DS.
Team/Resources/Skills
Risk: RMR: Limited experience & missing skills delay HW evaluation progress
Severity: medium Possible impact: Additional HW spins, schedule impact
Actions taken: 1) Increased PD support, also on-site: EA, RF.
2) RMR has sub-contracted Perlos for SAR.
3) RMR internal team size increase (RF)
4) Add. prj.mgmt. coach put in place: Improvement in prj.mgmt. skills