## Slide 1: KOALA Product Status: DS Assessment at planned S0
Presentation and content by Mario Topel
BMG PHE TPM2
09.01.2006
TPM: Detlef Wiesing
CPM: Jörg Hantschel

## Slide 2: Executive Summary Current assessment at planned S0 does not allow project commitment for planned DS
KOALA project cannot be committed by TPM based on planned feature set and schedule
Resource situation in Q1/07 very critical and requires clear prioritization
Platform transfer to PHA is highly endangered due to resource situation which might directly impact Merlin and Cesar
Staffing of initial ONYX SW-resources leads to delays of S0/M1 milestones
Stabilization of Kestrel launch date requires additional resources
Support of 6275 chipset by Qualcomm ends in Q2/2006 which highly endangers GCF-compliance
Immediate decision for further procedure regarding KOALA and BenQs 3G-roadmap needed based on different options

## Slide 3: Options To Keep KOALA as product Basically three options have been worked out to continue KOALA-development
Keep Koala with exactly same design as planned
6275 porting incl. EDGE / HSDPA
Application suite is Kestrel based
No landscape mode
No Rel 2 Features and additional Operator Features
no valid GCF version, Qualcomm support ends with GCF 3.20 in Q1/2006
platform transfer PHE highly endangered (impact on Merlin and Cesar expected)
Onyx team staffing not ensured
Option 1:
DS: 2006-09-29

## Slide 4: Options To Keep KOALA as product Basically three options have been worked out to continue KOALA-development
Keep Koala with exactly same design as planned
6275 porting incl. EDGE / HSDPA
Landscape mode in significant applications
Rel 2 features and additional operator features possible
platform transfer Taipei significantly ensured
Onyx team staffing ensured
Delay KOALA by 3 month
No state of the art chip set in Q1 /07
Bad cost position in Q1/07 compared to competition and on chipset level (vs. 6280)
No re-use for future products due to old chipset
No valid GCF version, Qualcomm support ends with GCF 3.20 in Q2/2006, Operator listing endangered
Option 2:
DS: 2007-01-12

## Slide 5: Options To Keep KOALA as product Basically three options have been worked out to continue KOALA-development
Keep Koala concept (Swivel, landscape story)
Evaluate stack up optimization in terms of length/thickness & design
Base KOALA on new chipset 6280 (similar to 6275), same as in Ruby/Amethyst
20% higher CPU performance
New RF-CMOS solution (same solution as in Ruby/Mallow/Gecko/Amethyst)
Cost saving on component level >3€, PCB space saving >= 100mm²
Full HSDPA support with 3.6 MBit
Full landscape support and Rel 2 + additional operator Features
valid GCF certification due to continued Qualcomm support
Easier migration to 6255/60 for Mallow/Gecko
platform transfer PHE ensured
Onyx team staffing ensured
Reduced support of parallel platforms 6250/6280/6255 instead of 6250/6275/6280/6255, one RF solution less
Delay KOALA by 5 month
Option 3:
DS: 2007-02-23
Recommended by TPM

## Slide 6: Timeline
Q2
CY 2006
Q4
Q1
Q3
CY 2006
Q1
Q2
Q3
Q4
GCF3.19
GCF3.20
GCF3.21
GCF3.22
GCF3.23
6280
6255A
6275
ES 6280
CS 6280
ES RFCMOS
CS RFCMOS
ES 6255A
CS 6255A
Rel. 2.0
Rel. 3.1
Rel. 3.2
Rel. 1.0
Rel. 3.0
Rel. 3.3
Rel. 1.0
Rel. 2.0
Rel. 3.0
Koala
(ES 6280 65nm)
Rel. 4.0
Rel. 4.0
Kestrel
Cesar
Merlin
Discontinuation of 6275
Onyx

## Slide 7: Timeline cont´d
Q2
CY 2007
Q4
Q1
Q3
CY 2006
Q1
Q2
Q3
Q4
GCF3.19
GCF3.20
GCF3.21
GCF3.22
GCF3.23
6280
6255A
Rel. 3.0
Amethyst
Mallow
Ruby
Gecko
Tbd.
Rel. 4.3
Tbd.

## Slide 8: Main Problems identified during S0-assessment Resource ramp up for QCT-program and maturity from W5-development not sufficient
70 % of most experienced ICT / CPE architects and IMs left BenQ at the End of 2005
3 month delay of W5 Rel 1.4 (base for Kestrel) causes additional resources on Kestrel
Extended Kestrel support due to first main operator approval for Qualcomm products
Qualcomm working model change, BenQ is since W5 DS responsible for bug fixing
WRO Koala team not enough experienced yet, technical coaching by line management and experienced developers needed
Munich resource ramp up delayed due to Minos/Hydra DS shift
Very high implementation effort for Landscape mode as a result of the S0 feasibility studies
Qualcomm AMSS 6275 Rel. 4.0 was canceled on 12.12.05, no valid GCF version support
Issues
Resources

## Slide 9
STAY YOUNG – KEEP EXPLORING