## Slide 1
R&D, MEP 7 adaptation to newly introduced product/project classes I-IV
%
  Common R&D HR resource collection and planning
  Aligned cost structure and calculation model
  Development milestone mapping
  Unified organization presentation
  Aligned reporting concept
Lead:
U. Schmitz
Status:
Kick off
Achievements:
Objectives:
  Pragmatic adaptation of MEP 7 R&D parts to project classes I-IV
  Provide leaner MEP for leaner project-classes
  Eliminate obsolete check-items
  Combine and/or drop milestones for ‘simple projects’ (if applicable!).
  Adapt standard durations to project classes
Critical issues / Open topics to be solved:
Key KPIs:
Critical issues / Open topics to be solved:
Next steps:
Activity
Responsible
Date
Status
Deadlines and results on track
Deadlines and results at risk
Deadlines and results highly at risk
  Get ‘GO’ from R&D board. Adapt team U. Schmitz cw 2
  Inform team U. Schmitz cw 2
  Agreement with I/F partners U. Schmitz cw 2
  First WS with Team U. Schmitz cw 2
  New MEP (R&D parts) available E/March 2006
  Existing MEP checkpoints aligned to project classes I-IV
  Milestones combined and/or dropped for ‘simple projects’ (not yet decided, must be evaluated in the coarse of the project)
  Standard phase-durations for project classes defined
Team: J. Bauregger (HW), T. Hagemann (SW), O. Schrage (MD), C. Friedl (ST), A. Betting (TPM), H.P. Hoeckenreiner (Planning)
Interface: Th. Masselink (Over all MEP), U. Mielkau (CTM), A. Eising (QM), t.b.d.(SCM), t.b.d (RD VAS)
Sponsor/Steering:
S. Bocionek, W. Klebsch, J. Schmitz
  Team availability must be ensured
  Agreement and availability of I/F partners
Procedure and timeline
  Based on project class definition results of PD energize project. Re-use results/material developed there
  Team regularly meets in WS (apprx. 4x), no add. status meeting
  1st WS: Analyze solution in depth and agreement. 2nd+3rd: intermediate results. 4th prepare final version
  Present intermediate results to sponsor/steering (1-2x)
  Kick-Off: 10.Jan., Interm.res. :3.Feb + 3.Mar, Final version 31.Mar.
  Rough effort estimation: ~40h/month for each team member. ~100h/month for project lead.
t.b.c
  Project proposal (= base for R&D board ‘GO’) available

## Slide 2: Appendix

## Slide 3: Project Organisation

## Slide 4: Areas of work / open issues
1. General:
• Define if each check point gets a ‘relevant for product class X’ indication
• Define if milestones need to be merged for certain class X products (e.g. S15/S2 for class1) If so: Enhance each of the tables in the entire document.
• Check,/decide if milestones can be dropped for certain classes
2. Adapt duration of phases to mapping to project classes
• Enhance duration list
• Combine/drop milestones(?)
3. Adapt checklist responsible (Due to org change)
• Each checklist at each milestone should show definition responsible
Optional:
3. Eliminate mix department/project
• Provide clear matrix org statement and picture
4. BenQ mobile Org
• Add missing functions in “4. Overview of declarations” (e.g. Ma: no entry, but approx 35 checkpoints).
• What does CTM/TPM cover? (Process discussion!!!!!)
• Grouping of functions (e.g. R&D)
• Unbind from changing org
• Use generic terms (as partially already in)
• Provide one-pager as mapping to current org struct
• Adapt to new department structure
• Unique wording throughout the doc
• Provide generic org struct which shows all MEP-players
5. Metrics
• Overview how many checkpoints for which MS/function
6. Check use of platform
• Assumption for MEP 7.x platform process goes alive

## Slide 5: Definition of PD project classes The project cost and the project duration are depending on the development effort. This is described by the PD classes
Source: Collected data from PL-P & PL-T
PD project class | I | II | III | IV
Description | New ID only, same PCB, same SW | New housing, new PCB, slight SW modifications, reuse of available HW and SW components | New form factor (concept) SW and/or HW evolution | Lead product incl. platform and component cost  Everything new
Cost range (direct cost) | 2’8 (Condor) - 5’0 (Phillipe) | 4’0 (Finch) - 7’7 (Obsidian) | 15’8 (Onyx) - 20’(Kestrel) | >30’ (Swan, Koala…)
Typical cost | 3’0 | 6’5 | 17’5 | 40’
Typical project duration (M0 till DS) | 25 weeks (driven by mechanics) Condor: 21 weeks | 33 weeks (driven by mechanics) | 45 weeks (driven by SW) | 75 weeks (driven by SW)
Prerequisites for timeline | Design must be available and aligned with Mechanics, other features identical to technical predecessor. | Design must be available and aligned with Mechanics, all features must be defined in terms of “as already available for…” | SW feature list must be finalized and agreed. Architecture to be derived from predecessor projects/platform | SW feature list must be finalized and agreed (top level), Architecture must be available from TPS, key HW features/components are defined.
Risk | low | low-mid | mid | high
Notes: Themes are defining the „center of gravity“ of a phone‘s positioning, not it‘s exclusive functionality
-> e.g., an Imaging phone might also support Music / MP 3, even though it‘s not on the „Music“ Theme roadmap