## Slide 1: Product House Europe PD-Status TPM1 QualComm based products
Mario Topel
BenQ Mobile
06. March 2006

## Slide 2: PHE TPM1 Highlights/Lowlights 20.02.2006
Product Development
+
EF81: Further support incl. April 06 agreed with Qualcomm
Onyx: M1-HW declared on Feb 24th / M1-SW planned on March 17th Antenna performance increased by 1.5dBm to 15.5dBm
Ruby M0 declared on March 3rd by Project Team / 6280-SLA signed by BenQ/QCT - Koala project restarted, TPM assigned
Mallow project started, TPM assigned
-
SXG75: volumes still only 56k over LC. Scrap risk 6’7€. SFR deal cancelled!
EF81: Still increasing overall number of defects (esp. from operator tests). Netto bug fix rate of 100 per week not reached  DS delayed to March 29th.
Still significantly component shortage (e.g. KHVatec) / additional quality problems with mechanics and earpiece
General Tasks
-
Team staffing Koala
Team staffing Mallow
Comparison Kestrel vs. Macross C1 in terms of project setup / costs etc. as best practice sharing

## Slide 3: PHE TPM1 Kestrel nCCPi-Statistic 06.03.2006

## Slide 4: PHE TPM1 Kestrel nCCPi-Statistic 06.03.2006

## Slide 5: PHE TPM1 Defect Rate 06.03.2006

## Slide 6: PHE TPM1 Defect Rate 06.03.2006

## Slide 7: PHE TPM1 Current defects vs. commitments 06.03.2006

## Slide 8: New Roadmap as of 10.02.2006 3G dominates new portfolio
%
Q1
Q2
CY2007
Q3
Q4
Explore
Performance
H
M
Explore
Image/Status
H
M
L
M
L
Affordable
Quality
Explore
Passion
H
M
3G
2G
Goldstone-PHA
Pearl (Moonstone)
Morgonite (Lolite)
Zircon
Low cost ownership
Alumen-PHA
Multimedia for the masses
Crystal - PHA
Mysterious sensation
Ruby-PHE
Diamond
Platinum-PHA
Quartz (Marten)
04/07
02/07
Kaolin
Intensively Feminine
03/07
02/07
02/07
Luxury style statement
Garnet - PHA
05/07
The sculpture
Koala-PHE
04/07
07/07
10/07
08/07
01/07
04/07
03/07
Sunstone
07/07
Mangania-PHA
02/07
Silverstone
09/07
Mica-PHE
04/07
Galena
08/07
Titanium - PHE
Kunzite
Mallow-PHE
04/07
Style expression
Fun expression
09/07
06/07
Under discussion
Need a repositioning
3G/EDGE
Low end
Onyx II
OLED
Multimedia
Diamond II
GPS
Landscape
3G/EDGE/HSDPA & VT
SWIFT 3G ultra-slim
Waterproof
camcorder
Quail with Camera
Jasper II
ROBUST GPS & VT
Poppy 3
Amber II
Flamingo with Camera

## Slide 9: New Roadmap as of 10.02.2006 – Updated acc. CTO 3G dominates new portfolio
%