## Slide 1: PLM Excellence Program
Dr. S. Bocionek/ Dr. J. Eickholt
BenQ Mobile PHE BMG RD
Munich, March 20, 2006

## Slide 2: Project „Quo Vadis PHE PD ?“: Bocionek
Goals
  Communication Campaign in PD
  Increase confidence in mgmt
  Increase knowledge & skills
  Facilitate cross-dept interaction
  Increase enjoyment
Measures of Succes
  Employee opinion survey after 6 months (and annually after that)
  Initial target: „66% positive“
Responsibilities
  Program Manager: Bocionek
  Contributions: mgmt team, all
Reporting & Review
  Bi-monthly all hands R&D meetings
  Employee opinion survey in summer 2006
Project Schedule
  Mgmt kick-off workshop: mid Jan 06
  1st all hands R&D meeting: 27. Jan. 06
  Breakfast Club 5-Apr-06 (topic: Customer Orientation and Process Discipline: Harmony or Contradiction?)
Project Status Summary: 20-Mar-06
achievements
  concept „Quo Vadis R&D“ defined
  accepted by mgmt team
  successful 1st all hands meeting on 31. Jan
issues
  n/a
support/decisions needed
  n/a
next steps
  All hands R&D meeting on 31-Mar-06
  Breakfast Club 5-Apr-06
  include PHA R&D in combined product house (May 06)

## Slide 3: Project „High-Performing Culture“: Bocionek
Goals
  Establish commitment-driven behavior
    Goal orientation
    Realistic but agressive plans
    Clear action setting
    Reliable delivery schedules
    Accountability culture across teams
    Service orientation towards internal customer satisfaction
  Skill optimization of mgmt & staff
Measures of Succes
  75% of all KPI‘s reached in year 1
  Work satisfaction > 66%
Responsibilities
  Program Manager: Bocionek/Klebsch
  Mgmt coaching: Bocionek / Klebsch
  Performance Controlling: Wingens
Reporting & Review
  Mgmt summary: monthly by SB & WK
  Ongoing KPI and „internal customer sat“ metrics
Project Schedule
  KPI‘s complete, and mgmt objectives finalized: end Jan 06
  Mgmt kick-off workshop & first training: mid Jan 06
  1st task for all mgrs: work out PLM excellence projects: end Jan. 06
  Performance monitoring: starts March 06
  Satisfaction questionnaire: Sept 06
  LQA / SMR: 1Q06
  Balanced Score Cards moved to April
Project Status Summary: 20-Mar-06 :
achievements
  KPIs defined and signed in Feb 06; KPI scoreboard set up by K. Wingens
  commitment culture implemented in U2, Fit4Apoxi Workshop, etc. Mgmt team accepts this approach
  LQA at PHE R&D accepted by mgmt team (prototyped within BMG)
issues
support/decisions needed
next steps
  LQA starts in 2nd half of March
  Make BSC from KPI scoreboard (April)
  Opinion Poll offered earlier than 3Q06 (tbd in 2Q06)

## Slide 4: Project „Platform & Portfolio“: Bocionek/Eickholt
Goals
  Establish BenQ Mobile Portfolio, Roadmap Platform as unifying planning tools for whole organization
    Cross-organizational workgoups
    QA‘ed documentation with approval and change request process of all stakeholders involved
  Derive concise strategies for re-use, make-or buy decisions, partner selection and sales programs
  Start with CM & PHE in 1H06; then involve PHA
Measures of Succes
  Formal documentation and change mgmt in place: Feb 06 not before April
  „Re-use factor“ increased by 33% in year 1
  R&D costs reduced by: tbd
Responsibilities
  Coach: Eickholt / Lepold
  Program Manager: Bocionek - Mulholland
Reporting & Review
  Mgmt report in OPC council
  Quarterly presentation of updated roadmap and portfolio
Project Schedule
  Alignment with CM, PHE: Eickholt & Lepold, Jan 06
  1st portfolio ready for approval: Sydon, Jan 06
  Uddated roadmap: Feb. 06 became March
  Re-use strategy doc: Feb 06 will be April
Project Status Summary: 20-Jan-06 :
achievements
  first „real“ portfolio/roammap and R&D budget alignment discussion on March 13
  replanning based on prioritized roadmap (by CM) on March 20th
  project back on track
issues
  CM needs more systematic approach; should be possible in new organization
support/decisions needed
next steps
  finalize roadmap – budget alignment (March)
  agree on regular update process, every second month (April)

## Slide 5: Project “Real V-Model: Introduce process culture and discipline“
Goals
  Establish true V-Model for PLM, across whole organization, and for all parts, e.g. HW, SW, MD, …)
    Set up „complete“ horizontal layers of responsibility in the „V“
    Define and agree on clear roles and responsibilities across all Org‘s
    Establish measurable process discipline
    Foster culture of internal customer satisfaction
  Improve TTM, Quality and cost position
Measures of Success
  Process maturity: > tbd
  QA deviations: < tbd
  Internal customer sat > 66%
Responsibilities
  Coach: Bocionek
  Project Manager: Assan
  Monitoring and measuring: Schwab/tbd
Reporting & Review
  Mgmt summary: monthly by SB & WK
  Ongoing KPI and „internal customer sat“ metrics
Project Schedule
  Name project lead (Feb. 06)  done
  Project Plan (Mar 06)  started
  Information Kick-off (Mar 06)  moved
  Education starts (Mar 06)  started
  Internal customer satisfaction metrics set (Mar 06)
  Cont. Improvement Process targets set (Apr. 06)
  Process adaptations completed (Jun 06)
  CMMI baseline available (Sep 06)

## Slide 6: Project „From Proto-Agile to Full Agile“: U. Schmitz
Goals
  Establish „Agile with Scrum“ as standard software development process
    Product backlog
    Scrum teams
    Sprint-based release plans
    TDD (test-driven development)
  Prototype Agile in Ruby and Gemstone
  Adjust organization as needed
  Adjust QMS as needed
Measures of Succes
  Kick-off for selected projects (01/06)
  Broad Introduction of Methodology (02/06)
  Start Ruby project on Agile (02/06)
  Setup transition team (02/06)
  Mentoring by OM starts (03/06)
  Create prioritized transition backlog and transition plan (03/06)
  Start Gemstone project on Agile (03/06)
  Scrum teams and sprint planning of pilots established (05/06)
  Pilot teams trained for TDD and agile principles (06/06)
  New R&D process for Agile development released (09/06) – proposal in 07/06
  Start full transition program (09/06)
  Organization prepared for full agile transition (12/06)
Responsibilities
  Coach: Bocionek
  Program Manager: U. Schmitz
  Project lead: Rudolph, Fässler
  Project lead QA/QMS: Fillers/Grein
Reporting & Review
  Pilot-Agile within regular project reviews in the OPC
  Pilots/Full transition: monthly mgmt report
Project Schedule
  Start: Jan 06 End: Dec 06; continue from there
  See Measures of success
Add Project Status Summary:
achievements
  Initial transition backlog created
  Product Owner for transition defined (S. Bocionek)
  Agile Overview and Q&A sessions held in MCH 250, KLF220, WRO 120
  Consulting plan with Object Mentors defined and started
  Ruby project started on Agile
issues
support/decisions needed
  OM consulting order release needed
next steps
  Prioritize and start processing transition backlog
  Start decomposing architecture of Ruby with OM onsite
  Involve Agile in ‚Fit 4 Apoxi‘

## Slide 7: Project „U2“: Rudolph, Fässler
Goals
  Secure TTM of Polaris, Swift, Swan, Kestrel
  Work packages as key metrics
  Commitment driven
  Open status communication
  Fast reaction on issues
  No compromise on quality
  TEAMWORK
Measures of Succes
  Establish weekly reporting of commitment and fulfillment (01/2006)
  Utilize reporting charts as project/PL control methods (02/2006)
  Enable team spirit and competition from reported results (03/2006)
  Establish U2 as practice in all relevant projects (04/06)
Responsibilities
  Work packackage table: PD (Fässler, Rudolph)
  Wallcharts: TPM (Asmussen, Topel)
  Test Trends: PD (Wacker)
  Program Manager U2: (Fässler, Rudolph)
Reporting & Review
  Wallchart review: 60min every Wed (all involved PL SW and SW/ST managers)
  PHE board: JE + SB/WK + TPM
Project Schedule
  Start: Jan 06 End: Mar 06; continue from there
  See Measures of success
Add Project Status Summary:
achievements
  meetings regularly held
  additional metrics added
issues
  none
support/decisions needed
  none
next steps
  continue with practice

## Slide 8: Project „proto-Agile Gemstone/Apoxi“: Fässler
Goals
  Prototype Agile with SCRUM in the Swan/Apoxi project
  Prepare organization for Agile
Measures of Success
  TTM reached with less than 2 weeks deviation from plan
  Broad Introduction of Methodology (02/06)
  Start Gemstone project on Agile (03/06)
  Setup transition team (02/06)
  Mentoring by OM starts (03/06)
  Create prioritized transition backlog and transition plan (03/06)
  Scrum teams and sprint planning of pilots established (05/06)
  Pilot teams trained for TDD and agile principles (06/06)
  New R&D process for Agile development released (09/06) – proposal in 07/06
  Start full transition program (09/06)
Responsibilities
  Program mgr: Dr. Georg Fässler
Reporting & Review
  Every 2nd month
Project Schedule
  Project launch Feb. 06
Project Status Summary:
achievements
  Broad Introduction of Methodology (02/06)
  Start Gemstone project on Agile (03/06)
  Setup transition team (02/06)
  Mentoring by OM starts (03/06)
issues
  none
support/decisions needed
  support of CPM not available (Robert Butz)
next steps
  Create prioritized transition backlog and transition plan (03/06)

## Slide 9: Project „ cleanApoxi“: Fässler
Goals
  Establish clear platform concept, including
    Clean definition
    Clean architecture
    Clean release strategy
    Clean toolkit usage concept
Measures of Success
  Definitions in place (2/06)
  Sub workgroup formed (2/06)
  Kick-off working groups (3/06)
  Re-use of platform 7/07
  APOXI cost below Native cost
Responsibilities
  Program mgr: Georg Fässler
Reporting & Review
  Reporting and review every 2nd month
Project Schedule
Project Status Summary:
achievements
  - significant part of the work done during the FIT 4 APOXI workshop
issues
  none
support/decisions needed
  none
next steps
  Finalize FIT 4 APOXI workshop

## Slide 10
Project „ Fit 4 Apoxi“: Fässler (step 1: Analysis Project)
Charter for the team
- Re-define „platform“ in its totality adressing people, process and product needs. Derive an optimal supplier co-operation model based on a platform as R&D productivity tool, and having in mind a maximized re-use factor of all invested efforts (specs, designs, code/features, base products).
- Future-safety and R&D productivity will come from key informatics principles like abstraction, componentization, and backward-compatible design.
- The trade-offs between „good platform“ and „market pressure“ will be analyzed for a concrete product, e.g. Diamond, and described in at least two scenarios.
- Potential white spots in the functionality of Apoxi to allow for a first product will be identified (incl. an estimate of the time to completion)
- A decision will be possible at the end of the analysis phase what the first product on Apoxi will be, and when we can deliver.
Objectives for the „platform“
Clean architecture (incl. 3rd party components)
Clean release concept
Clean requirements & CR process
Clean project management process (incl. 3rd parties)
Clean development process (agile)
Clean training and education concept
Measures of Success
  Abstraction layer requirements in place (3/06)
  Agreed upon rationale for APOXI cost lower native cost (4/06)
  White spots in Apoxi known; IFX comittment to close (4/06)
  Apoxi product decisions possible for Q1-Q3 2007 (3/06)
  Project plan for next 6 – 12 months ready and agreed (4/06)
Responsibilities
  Program mgr: Georg Fässler / Uli Geiger
  PL: Patric Houben - Chief architect : Norbert Haiduk
  Team members: nominated
  Steering board: SB, Sydon, Mucke, Björk
Reporting & Review (until end of March)
  Reporting and review every week
Project Schedule
  Architecture :
    Group members identified; committed <01.03.06
    Workshop abstraction layer : 6.03.06 < T < 31.03.06
      including all development parties :IFX-Comneon, Aplix, PSE, Teleca
  Project Management :
    Release strategy < 10.03.06
    Requirement platform management < 31.03.06
    Process rollout < 31.03.06
Project Status Summary:
achievements
  FIT 4 APOXI workshop currently ongoing
next steps
  see above

## Slide 11: Project „Invent the Future“: Bauregger
Goals
Strengthen IP portfolio of BenQ Mobile.
Make invention disclosures part of routine PLM work.
Stimulate fun to invent.
Measures of Success
Start: Jan 06 End: Aug 06
Agree on invention disclosure targets (Feb 06).
Investigate status and potential measures (Feb.06).
Start invention initiative (Mar 06).
Implement incentive proposal (Mar 06).
Implement organisational changes (Apr.06).
90 invention disclosures filed (Jul 06).
180 invention disclosures filed (Dec 06).
Reporting & Review
Management summary monthly to RD board
Project Schedule
See Measures of success
Responsibilities
Coach: Dr. Bocionek & Dr. Schneider-Hufschmidt
Program Manager: Bauregger, Hartmann
Add Project Status Summary:
achievements:
  Invention disclosure targets agreed.
  Status and potential measures available.
  Organizational change decided.
issues - none
support/decisions needed - none
next steps
  Alignment with ISR for invention initiative.
  Execute organizational change.

## Slide 12: Project „Thin Client Phone“: Bauregger
Goals
Realization of a WLAN VoIP Phone Prototype.
Design like Apple’s iPOD Nano.
Priority thin package.
Skype client must be used.
802.11b/g implementation.
Measures of Success
Start: Jan 06 End: Aug 06
Start Feature definitions (Jan 06)
Interdisciplinary team starts (Feb 06)
Draft Predevelopment Project Plan (Feb.06)
Final Predevelopment Project Plan (Mar.06)
System Supplier selection HW and SW (Mar.06)
System deliverables agreed with supplier (Apr. 06)
Component definition done (e.g. Display, etc.) (Apr.06)
Start PCB and Mechanical Design (Apr.06)
Prototype running (Jul 06)
Documentation (Aug.06)
Product decision (Aug 06)
Reporting & Review
Management summary monthly to RD board
Project Schedule
See Measures of success
Responsibilities
Coach: Dr. Bocionek
Program Manager: Bauregger
Project Leader: V. Otto
Add Project Status Summary:
achievements:
  “Short List” for supplier selection ready.
  Draft project plan ready.
  First stack up concept done.
  PMC planning implemented.
issues - none
support/decisions needed - none
next steps
  Account opening.
  Start detailed feature definition with CTM
  Fix final project plan (March).
  Select system supplier (March).

## Slide 13: Project MD Q-Improvement ( status 17.3.06 )
Goals
  Prevent defects and high return rates
  Detect and correct potential problems as early as possible
  Focus on PLM – SCM collaboration
    Parts
    Tools
    Suppliers
Measures of Success
  < 2% field return rate
Responsibilities
  Coach: Bocionek
  Program Manager: Thonhauser
Reporting & Review
  Monthly
Project Schedule
  Project start: Feb 06
  root cause/ levers : March 06
  - Start implementation : April 06
Add Project Status Summary:
achievements :
  3 sub projectteams installed ( MD performance, Integrator supplier, MD / SQA interface )
  interdisciplinary teams nominated ( MD, SCM and SP )
  root cause and levers defined ( aligned between all parties )
  lead products : Onyx and Obsidian
  Interface MD –SQA fixed and agreed
next steps - implementation plan ( March 06 )

## Slide 14: Project „Best in Test“: Wacker
Goals
  Create 5 significant metrics for performance measurement of ST , e.g.
    Test coverage, pass rate
    Code coverage
    Defect injection analysis
    Bug handling cycle time
    Field return rate
  Minimize number of new bugs detected after S4
  Provide test cases for TDD for acceptance test on time
  Provide measurement for changed lines of code after C3 milestone for component
  Provide measurement for 1st pass yield (pass rate during first test run)
  Improve ST performance based on metrics above
  Rollout of Testdirector
Measures of Success
  A) First metric setup 1.2.06, done 27.1.06 B) Complete metric setup 1.5.06
  Metric set up 1.5.06 incl. first roll out
  Availability of required test cases for TDD in pilot scrum team in time.
  Metric set up by 01.05. incl. first roll out
  Metric set up by 01.05. incl. first roll out
  Improvement targets for ST based on metrics above defined by 15.05.
  Buy decision 15.4.05, pilot run 30.7.
Responsibilities
  Coach: Bocionek
  Program Manager: Wacker
Reporting & Review
  Management summary monthly to RD board
Project Schedule
  See Measures of success
Add Project Status Summary:
achievements:
  kickoff with line managers and project leaders done
  all teams are named, and tasks are in progress as planned.
  data collection for all metrics started
  average EXIT/day metric introduced, data available
  principle workflow for TDD agreed with RD SW
issues - none
support/decisions needed – budget for Testdirector
next steps
  detailed data collection
  further alignment with QM

## Slide 16: BACKUP

## Slide 17: Project „Model-V“ & PM@PD: TBD
Goals
  Establish true V-Model for PLM, across whole organization, and for all parts, e.g. HW, SW, MD, …)
    Set up „complete“ horizontal layers of responsibility in the „V“
    Define and agree on clear roles and responsibilities across all Org‘s
    Establish measurable process discipline
    Foster culture of internal customer satisfaction
  Improve TTM, Quality and cost position
Measures of Succes
  Process maturity: > tbd
  QA deviations: < tbd
  Internal customer sat > 66%
Responsibilities
  Coach: Bocionek
  Program Manager: SB/WK - tbd
  Process def & CR: QP/QA org
  Monitoring and measuring: Schwab/tbd
  Quality Gates Checking: Mgmt team
Reporting & Review
  Mgmt summary: monthly by SB & WK
  Ongoing KPI and „internal customer sat“ metrics
Project Schedule
  Find program mgr: SB, Jan 06
  Alignment with QM/QP, CM, TPM, SCM, SP, PD: SB, Jan 06
  Information Kick-off: SB Jan 06
  KPI‘s complete, and mgmt objectives finalized: end Jan 06
  Start program: Feb. 06