## Slide 1
Uwe Schmitz, Karsten Rudolph
Munich, March 20, 2006
Status „PLM Excellence“
U2
From Proto-Agile to Full Agile

## Slide 2: Project „From Proto-Agile to Full Agile“: U. Schmitz
Goals
  Establish „Agile with Scrum“ as standard software development process
    Product backlog
    Scrum teams
    Sprint-based release plans
    TDD (test-driven development)
  Prototype Agile in Ruby and Gemstone
  Adjust organization as needed
  Adjust QMS as needed
Measures of Succes
  Kick-off for selected projects (01/06)
  Broad Introduction of Methodology (02/06)
  Start Ruby project on Agile (02/06)
  Setup transition team (02/06)
  Mentoring by OM starts (03/06)
  Create prioritized transition backlog and transition plan (03/06)
  Start Gemstone project on Agile (03/06)
  Scrum teams and sprint planning of pilots established (05/06)
  Pilot teams trained for TDD and agile principles (06/06)
  New R&D process for Agile development released (09/06) – proposal in 07/06
  Start full transition program (09/06)
  Organization prepared for full agile transition (12/06)
Responsibilities
  Coach: Bocionek
  Program Manager: U. Schmitz
  Project lead: Rudolph, Fässler
  Project lead QA/QMS: Fillers/Grein
Reporting & Review
  Pilot-Agile within regular project reviews in the OPC
  Pilots/Full transition: monthly mgmt report
Project Schedule
  Start: Jan 06 End: Dec 06; continue from there
  See Measures of success
Add Project Status Summary:
achievements
  Transition backlog reviewd, prioritization ongoing
  Consulting contract, team and schedule and with Object Mentors agreed
  Ruby project:: first 4 Scrum teams in WRO finished their sprint with excellent results (high motivation, good achievements, positive experience and results with TDD by Unit testing)
  Apoxi: first Scrum teams started in WRO
issues: none
support/decisions needed: none
next steps
  Finish prioritization of transition backlog and Sprint planning
  Decompose architecture of Ruby with OM onsite
  Define and implement Scrum based requirements handling
  Define detailed training schedule and content with OM
  Setup Scrum teams in MCH and increase number in WRO

## Slide 3: Project „U2“: Rudolph, Fässler
Goals
  Secure TTM of Polaris, Swift, Swan, Kestrel
  Work packages as key metrics
  Commitment driven
  Open status communication
  Fast reaction on issues
  No compromise on quality
  TEAMWORK
Measures of Succes
  Establish weekly reporting of commitment and fulfillment (01/2006)
  Utilize reporting charts as project/PL control methods (02/2006)
  Enable team spirit and competition from reported results (03/2006)
  Establish U2 as practice in all projects (04/06)
Responsibilities
  Work packackage table: PD (Fässler, Rudolph)
  Wallcharts: TPM (Asmussen, Topel)
  Test Trends: PD (Wacker)
  Program Manager U2: (Fässler, Rudolph)
Reporting & Review
  Wallchart review: 60min every Wed (all involved PL SW and SW/ST managers)
  PHE board: JE + SB/WK + TPM
Project Schedule
  Start: Jan 06 End: Mar 06; continue from there
  See Measures of success
Add Project Status Summary:
achievements
  Wallchart quality improved by additional metrics
  U2 Meetings regularly held
  Team competition fostered by presenting U2 wallcharts and Shopping lists in team floors in WRO and MCH and KLF
  Dedicated U2 project control room established in MCH (E3.Rotunde 2nd floor)
issues
  none
support/decisions needed
  none
next steps
  continue with practice
  Establish comparable ranking between teams of different platforms (Bundesligatabelle)