## Slide 1: PLM Excellence Program
Dr. S. Bocionek
BMG PH RD
Munich, May 08, 2006

## Slide 2: Status Summary
PLM - Excellence

## Slide 3: People
PLM - Excellence

## Slide 4
Done
Done
Project, P-Leader | Project Plans & Milestones | Status xxMay06 | Next Steps
Uniform Communication in R&D; Bocionek | Start: Jan 06 ongoing 1. Establish regular all hands communication (Jan 06) 2. Engage in breakfast meetings and other activities (start Feb 06) 3. Include PHA R&D in those activities after the PHE/PHA merge (start May 06) |  | - 2nd all hands R&D meeting on 31. March 06 - breakfast club in Apr 06 - next all hands R&D meeting (world wide) May 06 Take off from PLM exc. June
High-performing culture & commitment-driven behavior; Bocionek | Start: Jan 06 End: Dec 06; repeat every year 1. KPI metrics (Jan 06) 2. Mgmt Objectives aligned and signed (Feb 06) 3. Balanced Score cards (Feb. 06; moved to April) 4. LQA analysis (R&D only: May 06; moved to March) 4b. opinion poll possible in 2Q06 5. Peer Rating in Mgmt (R&D only; Sept 06) 6. 10 Basic Aspects (Oct 06) 7. Feedback rounds, EFA (Nov/Dec 06) | Done Done Done Done | LQA March 06 Evaluation discussion in mgmt team mid May
Real Model-V: Introduce process culture and discipline; Assan | Start: Jan 06 End: Sep 06 1. Name project lead (Feb. 06) – M. Assan 2. Project Plan (Mar 06) 3. Education starts (Mar 06) 4. Internal customer satisfaction metrics set (Mar 06) 5. CIP targets set (Apr. 06) 6. Process adaptations completed (Jun 06) 7. CMMI baseline available (Sep 06) | Done | Work packages moved due to launch of Processes N’Synch Role definitions will be handled within Processes N’Synch

## Slide 5
Project, P-Leader | Project Plans & Milestones | Status xxMay06 | Next Steps
Done
Best in Requirement Engineering; Sarzio | Start: May 06 End: Sep 06 1. Name project lead (Apr. 06) – J. Sarzio 2. Project Plan (May 06) 3. xxx |  | Accept work plan: May 06
Done
Done
Done
Done
Done
Done
Done
Going Agile; U. Schmitz, Faessler, Rudolph | Start: Jan 06 End: Dec 06; continue from there 1. Kick-off for selected projects (01/06) 2. Broad Introduction of Methodology (02/06) 3. Start Ruby project on Agile (02/06) 4. Setup transition team (02/06) 5. Mentoring by OM starts (03/06) 6. Create prioritized transition backlog and transition plan (03/06) 7. Start Gemstone project on Agile (03/06) 8. Scrum teams and sprint planning of pilots established (05/06) 9. Pilot teams trained for TDD and agile principles (06/06) 10. New R&D process for Agile development released (09/06) – proposal in 07/06 11. Start full transition program (09/06) 12. Organization prepared for full agile transition (12/06) |  | Continue to implement Scrum based team structure and requirements handling Continue requirements->use cases->architecture support for projects Broad training coverage for acceptance testing, agile C, C++, test-driven development Improve information to teams about agile transition achievements

## Slide 6
Project, P-Leader | Project Plans & Milestones | Status xxMay06 | Next Steps
Done
Done
Best-in-Test: Wacker | Start: Jan 06 End: Jun 06; continue measuring All teams named, tasks are in progress 1.1 First metric setup (Feb 06) 1.2 – 1.5 complete metrics set up (e.g. defect injection analysis) (May 06) 2. Roll out “new bugs after S4” metric (May 06) 3. Test cases for TDD in scrum team in time (May 06) 4. Roll out “changed LOC” metric after C3 (May 06) 5. Roll out “first pass yield” metric (May 06) 6. KPI targets ST based on metrics data (June) |  | Ongoing data collection Scrum teams with TDD (started) alignment with ST Asia deeper alignment with RD SW for CLOC
Best-in-SW Tools Mario Topel Wolfgang Hettich | Start: May 06 End: Jun 07 1. Project Plan (May 06) 2. Tool / Workflow assessment (Jun 06) 2. Consolidate all teams for PLM (July 06) 3. Start centralizing support infra-structure (July 06) 4. Increase automation of tool chain (Sep 06) |  | Project re-start Project plan to be worked out in detail (May 2006) Best practice sharing /w SIE MED (17./18.05) Tool / workflow assessment Beijing/Taipei till June 06

## Slide 7
Project, P-Leader | Project Plans & Milestones | Status xxMay06 | Next Steps
Done
Done
Platform & Portfolio; SB + JE | Start: Jan 06 End: Jun 06 1. Define alignment & change mgmt process (Feb 06), 2. clarify platform responsibilities/activities (Feb 06) 2b. portfolio – budget alignment (Mar 06) 3. define re-use strategy (Mar 06) is ongoing 4. PH wide portfolio and plan (June 06) |  | Portfolio / Roadmap vs R&D budget alignment underway in March 06 Process well established PH wide plan next (June 06)
Done
Done
Invent the future; Bauregger, Hartmann | Start: Jan 06 End: Jun 06 1. Agree on invention disclosure targets (Feb 06) 2. Investigate status and potential measures (Feb.06) 3. Start invention initiative (Mar 06) 4. Implement incentive proposal (Mar 06) 5. Implement organizational changes (Apr.06) 6. 90 invention disclosures filed (Jul 06) 7. 180 invention disclosures filed (Dec 06) |  | Alignment with ISR for invention initiative. Execute organizational change.
Done
cleanApoxi platform; Faessler | Start: Jan 06 End: Dec 06 (perhaps earlier) 1. Align all parties incl. IFX, Teleca (Feb 06) 2. Analysis workshop (Mar 06) 3. Diamond decision (Mar 06) 4. Publish formal platform concept, incl. technical specification and usage model (Apr 06) 6. Start skills enhancement program (May 06) 7. Close gaps in Apoxi (tbd) 8. First Apoxi product (tbd; hopefully Apr 07) |  | Workshop (start 05-Mar-06), Diamond decision (latest EO March)

## Slide 8
Project, P-Leader | Project Plans & Milestones | Status xxMay06 | Next Steps
Done
Done
Done
Done
U2 projects; Faessler, Rudolph | Start: Jan 06 End: Mar 06; continue from there 1. Establish weekly reporting of commitment and fulfillment (01/2006) 2. Utilize reporting charts as project/PL control methods (02/2006) 3. Enable team spirit and competition from reported results (03/2006) 4. Establish U2 as practice in all projects (04/06) |  | New projects to be added ( Ruby, Falcon) continue with practice Establish comparable ranking between teams of different platforms (Bundesligatabelle)
Done
Done
Done
Quality Up of MD; Thonhauser | Start: Jan 06 End: Jun 06 1. PLM MD excellence program and KPI‘s (Jan06) 2. Interdisciplinary Project teams installed 3. MD SQA interface fixed and agreed 4. Visible results (Jul 06) |  | Track monthly KPI‘s
Done
Done
Done
Thin client phone; Bauregger | Start: Jan 06 End: Aug 06 1. Start Feature definitions (Jan 06) 2. Interdisciplinary team starts (Feb 06) 3. Draft Predevelopment Project Plan (Feb.06) 4. Final Predevelopment Project Plan (Mar.06) 5. System Supplier selection HW and SW (Mar.06) 6. System deliverables agreed with supplier (Apr. 06) 7. Component definition done (e.g. Display, etc.) (Apr.06) 8. Start PCB and Mechanical Design (Apr.06) 9. Prototype running (Jul 06) 10. Documentation (Aug.06) 11. Product decision (Aug 06) |  | Investigation of potential platform suppliers (HW/SW) ongoing. Detailed feature alignment with CTM. Develop Stack up concept. Fix final project plan (March). Select system supplier (March).

## Slide 9: Project „Quo Vadis PHE PD ?“: Bocionek
Goals
  Communication Campaign in PD
  Increase confidence in mgmt
  Increase knowledge & skills
  Facilitate cross-dept interaction
  Increase enjoyment
Measures of Success
  Employee opinion survey after 6 months (and annually after that)
  Initial target: „66% positive“
Responsibilities
  Program Manager: Bocionek
  Contributions: mgmt team, all
Reporting & Review
  Bi-monthly all hands R&D meetings
  Employee opinion survey in summer 2006
Project Schedule
  Mgmt kick-off workshop: mid Jan 06
  1st all hands R&D meeting: 27. Jan. 06
  Breakfast Club 5-Apr-06 (topic: Customer Orientation and Process Discipline: Harmony or Contradiction?)
  Concept established; Quo Vadis R&D will be ongoing activity; can be taken off the PLM-excellence program after May 06
Project Status Summary: 08-May-06
achievements
  concept „Quo Vadis R&D“ defined
  accepted by mgmt team
  successful 1st all hands meeting on 31. Mar
  successful breakfast club on 5.Apr. In MUC
  add‘l subsequent all hands meetings in KLF, BEJ, HSI, TAI
issues
  n/a
support/decisions needed
  n/a
next steps
  All hands R&D meeting in May 06 (world-wide, new RD organization)

## Slide 10: Project „High-Performing Culture“: Bocionek
Goals
  Establish commitment-driven behavior
    Goal orientation
    Realistic but aggressive plans
    Clear action setting
    Reliable delivery schedules
    Accountability culture across teams
    Service orientation towards internal customer satisfaction
  Skill optimization of mgmt & staff
Measures of Success
  75% of all KPI‘s reached in year 1
  Work satisfaction > 66%
Responsibilities
  Program Manager: Bocionek/Klebsch
  Mgmt coaching: Bocionek / Klebsch
  Performance Controlling: Wingens
Reporting & Review
  Mgmt summary: monthly by SB & WK
  Ongoing KPI and „internal customer sat“ metrics
Project Schedule
  KPI‘s complete, and mgmt objectives finalized: end Jan 06
  Mgmt kick-off workshop & first training: mid Jan 06
  1st task for all mgrs: work out PLM excellence projects: end Jan. 06
  Performance monitoring: starts March 06
  LQA / SMR: 1Q06
  Satisfaction questionnaire: Sept 06
Project Status Summary: 08-May-06 :
achievements
  KPIs defined and signed in Feb 06; KPI scoreboard set up by K. Wingens
  commitment culture implemented in U2, Fit4Apoxi Workshop, etc. Mgmt team accepts this approach
  LQA at PHE performed
issues
support/decisions needed
next steps
  LQA evaluation to be discussed with mgmt; follow ups needed (May, June)
  Opinion Poll offered earlier than 3Q06 (tbd in 2Q06)
  measure now true quantitative improvements (start May 06)

## Slide 11: Processes
PLM - Excellence

## Slide 12: Project “Real V-Model: Introduce process culture and discipline“
Goals
  Establish true V-Model for PLM, across whole organization, and for all parts, e.g. HW, SW, MD, …)
    Set up „complete“ horizontal layers of responsibility in the „V“
    Define and agree on clear roles and responsibilities across all Org‘s
    Establish measurable process discipline
    Foster culture of internal customer satisfaction
  Improve TTM, Quality and cost position
Measures of Success
  Process maturity: > tbd
  QA deviations: < tbd
  Internal customer sat > 66%
Responsibilities
  Coach: Bocionek
  Project Manager: Assan
  Monitoring and measuring: Schwab/tbd
Reporting & Review
  Mgmt summary: monthly by SB
  Ongoing KPI and „internal customer sat“ metrics
Project Schedule
  Name project lead (Feb. 06)  done
  Project Plan (Mar 06)  updated
  Information Kick-off (Mar 06)  moved
  Education starts (Mar 06)  started
  Internal customer satisfaction metrics set (Mar 06)  May 05
  Cont. Improvement Process targets set (Apr. 06)  May 05
  Process adaptations completed (Jun 06)
  CMMI baseline available (Sep 06)
   Work packages moved due to launch of Processes N’Synch
   Role definitions will be handled within Processes N’Synch

## Slide 13: Project „Requirement Engineering Excellence“
Goals
Define and establish formal requirements engineering practice in BMG („Best-in-Class“)
  Scope
    Product requirements
    Platform requirements
    All projects globally
  Improve on all levels of operation within CM and PD
    Process: Role and workflow clarity (incl. deliverables), trigger organizational adaptions where needed, speed through re-use,, support of Agile with Scrum, ensure formal review practices, increase transparency
    People: Skills, Training, Mentoring and Staffing
    Tools: Improve usability of Doors, increase also RE efficiency by adequate tool support (i.e. Doors, CR-Light)
    Communication: Improve, align and communicate activities
    (TBD) Projects: higher quality documents / requirements, „small but beautiful“
Measures of Success (to be finalised and agreed upon)
  Internal Customer satisfaction; positive Doors user feedback by opinion survey
  On-time delivery (OTD) of requirements docs at Mx milestones > 90% of plan (TBD)
  100% product requirements handled in Doors at end of CY 2006
Responsibilities
  Coach: Bocionek / Sydon
  Project Manager: Jörg Sarzio
Reporting & Review
  bi-weekly jourfix with coaches
  monthly management report
Project Schedule
  Start: Apr 06
  Analyze situation and identify improvement areas (04/06)
  Accompany pilot projects Ruby, Koala and Gemstone platform (start 04/06)
  Define project setup, targets and first rollout plan (05/06)
  Align and initiate “low hanging fruits” improvements within Doors, agree on Rollout Plan for “Phase 1”(05/06)
  Fix RE workstream / processes (in alignment with CM Implementation and PD setup / Agile ) (06/06 - tbd)
  Ensure adequate people skills and staffing (07/06)
  Based on agreed upon processes modify as required Doors, agree rollout plan for Phase 2 (start 07/06, duration tbd))
  Target Project End: Dec 06; continue from there
Add Project Status Summary (Status 26.4.06):
achievements
  >30 interviews with stakeholders of RE in CM and PD conducted
  more than 100 points with improvement potential identified and first clustering / prioritization done
  drafting of first work packages / measures for Process and Tool (Doors) improvements
issues: widely varying understanding; limited availability of resources
support/decisions needed: Kickoff with Coaches, fix project goals
next steps
  fix cross functional project setup, fix and rollout meeting and reporting structure
  fix and align first work packages within the areas of PROCESS, TOOLs and COMMUNICATION
DRAFT

## Slide 14: Project „Best in Test“: Wacker
Goals
  Create 5 significant metrics for performance measurement of ST , e.g.
    Test coverage, pass rate
    Code coverage
    Defect injection analysis
    Bug handling cycle time
    Field return rate
  Minimize number of new bugs detected after S4
  Provide test cases for TDD for acceptance test on time
  Provide measurement for changed lines of code after S25 milestone for project specific SW
  Provide measurement for 1st pass yield (pass rate during first test run)
  Improve ST performance based on metrics above
  Rollout of Testdirector
Measures of Success
  A) First metric setup 1.2.06, done 27.1.06 B) Complete metric setup 1.5.06: 80% done, 20% planned 1.6.06
  Metric set up 1.5.06 done incl. first roll out (partly done, to be completed 15.6.)
  Availability of required test cases for TDD in pilot scrum team in time (done in time)
  Metric set up by 01.05. incl. first roll out, good progress, but delayed due to resources
  Metric set up by 01.05 done. incl. first roll out (no project S25 yet)
  Improvement targets for ST based on metrics above defined by 15.05.
  Buy decision shifted 20.5.05 due to merge PH, pilot run 30.8
Responsibilities
  Coach: Bocionek
  Program Manager: Wacker
Reporting & Review
  Management summary monthly to RD board
Project Schedule
  See Measures of success
Add Project Status Summary:
achievements:
  all teams are named, and tasks are in progress as planned.
  ongoing data collection for all metrics
  scrum teams with TDD started
  all teams are in operation and report regularly
issues - none
support/decisions needed – budget for Testdirector
next steps
  further alignment with PHA
  deeper alignment with RS SW for CLOC

## Slide 15
Goals
  Establish integrated SW-Tool Chain to support SW-development, agile programming methods, iterative, time- boxed and test driven development
  Harmonization of SW-Tool landscape for BenQ Mobile
  Perform Best Practice Sharing and Benchmarking
Add Project Status Summary:
achievements:
  1st (draft) concept available
  new team setup available, Kick-Off planned in cw18
issues:
  only 2+1 team members instead of needed 8 (10)
  still no official communication to Taiwan released
Project Best in SW-Tools for BenQ Mobile Mario Topel (Status 26.04.06)
Measures of Success
  Established SW-Tool Chain including workflow documentation per product line till Q4/2006
  Harmonization level 1 (number of different SW-Tool used for same task) per product line in Q3/2006
  1 Best Practice Sharing/Benchmarking per half year
  Infrastructure costs reduced by 20%
  Positive user feedback >80%
Goals
  Coach: Dr. S. Bocionek
  Program Manager/Project Lead: M. Topel / W. Hettich
Tools & Tasks
  Requirements Engineering: Telelogic DOORS /
  Description Language: Telelogic TAU /
  Configuration Management: Telelogic SYNERGY / Rational Clearquest / Serena
  Defect Management: Rational CLEARQUEST / SERENA
  (Automated Test:) To be decided Mercury TESTDIRECTOR
Reporting & Review
  Team Meeting: Weekly (re-start cw18)
  Steering Board: Monthly (re-start cw20)
Project Schedule
  Restart: cw18 / Tool assessment 05/06
  Final project plan: cw22
Add Project Status Summary:
Support/decisions needed:
  resource clarification/budget release by R&D
  establishment of new setup incl. global communication needed by R&D
Next steps:
  Project plan to be worked out in detail (May 2006)
  Best practice sharing /w SIE MED (17./18.05)
  Tool / workflow assessment Beijing/Taipei till June 06

## Slide 16: Project „From Proto-Agile to Full Agile“: U. Schmitz
Goals
  Establish „Agile with Scrum“ as standard software development process
    Product backlog
    Scrum teams
    Sprint-based release plans
    TDD (test-driven development)
  Prototype Agile in Ruby and Gemstone
  Adjust organization as needed
  Adjust QMS as needed
Measures of Success
  Kick-off for selected projects (01/06)
  Broad Introduction of Methodology (02/06)
  Start Ruby project on Agile (02/06)
  Setup transition team (02/06)
  Mentoring by OM starts (03/06)
  Create prioritized transition backlog and transition plan (03/06)
  Start Gemstone project on Agile (03/06)
  Scrum teams and sprint planning of pilots established (05/06)
  Pilot teams trained for TDD and agile principles (06/06)
  New R&D process for Agile development released (09/06) – proposal in 07/06
  Start full transition program (09/06)
  Organization prepared for full agile transition (12/06)
Responsibilities
  Coach: Bocionek
  Program Manager: U. Schmitz
  Project lead: Rudolph, Fässler
  Project lead QA/QMS: Fillers/Grein
Reporting & Review
  Pilot-Agile within regular project reviews in the OPC
  Pilots/Full transition: monthly mgmt report
Project Schedule
  Start: Jan 06 End: Dec 06; continue from there
  See Measures of success
Project Status Summary:
achievements
  Trainings done in MCH, KLF, WRO (Scrum Master, Agile C development). High trainee satisfaction.
  Various definitions done (Product owner team, Req to use cases, Acceptance tests,..)=>several work products available
  Communication into projects and R&D improved (bi-weekly newsletter, presentation of agile definition results in prj-meetings)
  Started prototype for automated simulation and in-target testing
  Gemstone project started on Agile
  >20 scrum teams running
issues
  Duration of Qualcomm-SW build to long for TDD
  Significant improvement of Q-simulation needed in Qualcomm
support/decisions needed: none
next steps
  Continue requirements->use cases->architecture support for projects
  Broad training coverage for acceptance testing, agile C, C++, test-driven development
  Improve information to teams about agile transition achievements

## Slide 17: Project „proto-Agile Gemstone/Apoxi“: Fässler
Goals
  Prototype Agile with SCRUM in the Swan/Apoxi project
  Prepare organization for Agile
Measures of Success
  TTM reached with less than 2 weeks deviation from plan
  Broad Introduction of Methodology (02/06)
  Start Gemstone project on Agile (03/06)
  Setup transition team (02/06)
  Mentoring by OM starts (03/06)
  Create prioritized transition backlog (03/06)
  Scrum teams and sprint planning of pilots established (05/06)
  Pilot teams trained for TDD and agile principles (06/06)
  New R&D process for Agile development released (09/06) – proposal in 07/06
  Start full transition program (09/06)
Responsibilities
  Program mgr: Dr. Georg Fässler
Reporting & Review
  Every 2nd month
Project Schedule
  Project launch Feb. 06
Project Status Summary:
achievements
  Broad Introduction of Methodology (02/06)
  Start Gemstone project on Agile (03/06)
  Setup transition team (02/06)
  Mentoring by OM starts (03/06)
issues
  none
support/decisions needed
  none
next steps
  Scrum teams and sprint planning of pilots to be established at PSE and BenQ Poland

## Slide 18: Project „U2“: Rudolph, Fässler
Goals
  Secure TTM of Polaris, Swift, Swan, Kestrel
  Work packages as key metrics
  Commitment driven
  Open status communication
  Fast reaction on issues
  No compromise on quality
  TEAMWORK
Measures of Success
  Establish weekly reporting of commitment and fulfillment (01/2006)
  Utilize reporting charts as project/PL control methods (02/2006)
  Enable team spirit and competition from reported results (03/2006)
  Establish U2 as practice in all relevant projects (04/06)
Responsibilities
  Work packackage table: PD (Fässler, Rudolph)
  Wallcharts: TPM (Asmussen, Topel)
  Test Trends: PD (Wacker)
  Program Manager U2: (Fässler, Rudolph)
Reporting & Review
  Wall chart review: 60min every Wed (all involved PL SW and SW/ST managers)
  PHE board: JE + SB/WK + TPM
Project Schedule
  Start: Jan 06 End: Mar 06; continue from there
  See Measures of success
Add Project Status Summary:
achievements
  meetings regularly held
  additional metrics added
  Wall chart quality improved by additional metrics
  Team competition fostered by presenting U2 wall charts and Shopping lists in team floors in WRO and MCH and KLF
  additional projects added: Philippe, Hawk & Obsidian, Onyx
issues
  none
support/decisions needed
  none
next steps
  further projects to be added ( Ruby, Falcon)
  continue with practice
  Establish comparable ranking between teams of different platforms (Bundesligatabelle)

## Slide 19: Project „Proto-Agile Ruby/QCT“: K. Rudolph
Goals
  Develop and test „Agile with Scrum“ as software development process within BenQ
    Product backlog
    Scrum teams
    Sprint-based release plans
    TDD (test-driven development)
  Prototype Agile with SCRUM in Ruby and QCT platform
  Prepare organization for Agile processes
Measures of Success
  Kick-off for Ruby (01/06)
  Broad Introduction of Methodology (02/06)
  Start Ruby project on Agile (02/06)
  Setup transition team (02/06)
  Mentoring by OM starts (03/06)
  Create prioritized transition backlog (03/06)
  Scrum teams and sprint planning of Ruby pilot established (05/06)
  Ruby teams trained for TDD and agile principles (06/06)
  New R&D process for Agile development proposal in 07/06 defined for Ruby
  New R&D process for Agile development released (09/06)
  Start full transition program (09/06)
  TTM of Ruby reached with less than 2 weeks deviation from plan
Responsibilities
  Coach: S. Bocionek
  Program Manager full transition: U. Schmitz
  Project lead Ruby transition: K. Rudolph
Reporting & Review
  Within regular project reviews in the OPC and every months in PLM excellence reports
Project Schedule
  Start: Jan 06 End: Dec 06; continue from there
  See Measures of success
Add Project Status Summary:
achievements
  Architecture preparation completed, Requirements structure definition ongoing
  First 4 Scrum teams in WRO finished their first sprint with excellent results (high motivation, good achievements, positive experience and first results with TDD)
  Further 17 Scrum teams in WRO and MCH started for next sprint
  Scrum Master training for WRO and MCH completed, TDD trainings started and ongoing
issues: none
support/decisions needed: none
next steps
  Finish prioritization of requirements structure, complete backlog and Sprint planning
  Decompose fully the architecture of Ruby, complete further sprint planning and setup of all remaining Scrum teams
  Finish TDD and Agile trainings for all involved teams (SW+ST)
  Improve Build process and testing environment

## Slide 20: Products
PLM - Excellence

## Slide 21: Project „Platform & Portfolio“: Bocionek/Eickholt
Goals
  Establish BenQ Mobile Portfolio, Roadmap Platform as unifying planning tools for whole organization
    Cross-organizational workgroups
    QA‘ed documentation with approval and change request process of all stakeholders involved
  Derive concise strategies for re-use, make-or buy decisions, partner selection and sales programs
  Start with CM & PHE in 1H06; then involve PHA
Measures of Succes
  Formal documentation and change mgmt in place: Feb 06 not before April
  „Re-use factor“ increased by 33% in year 1
  R&D costs reduced by: tbd
Responsibilities
  Coach: Eickholt / Lepold
  Program Manager: Bocionek - Mulholland
Reporting & Review
  Mgmt report in OPC council
  Quarterly presentation of updated roadmap and portfolio
Project Schedule
  Alignment with CM, PHE: Eickholt & Lepold, Jan 06
  1st portfolio ready for approval: Sydon, Jan 06
  Uddated roadmap: Feb. 06 became March
  Re-use strategy doc: Feb 06 will be April
  Planning for 2008 portfolio: 3Q06
Project Status Summary: 08-May-06 :
achievements
  first „real“ portfolio/roammap and R&D budget alignment discussion on March 13
  replanning based on prioritized roadmap (by CM) on March 20th
  project back on track
  change process established
issues
support/decisions needed
next steps
  finetune portfolio along whole new product house
  continue working on re-use strategy and improved platform concepts
  consider colocation of Mulholland and Bocionek

## Slide 22: Project „Invent the Future“: Bauregger
Goals
Strengthen IP portfolio of BenQ Mobile.
Make invention disclosures part of routine PLM work.
Stimulate fun to invent.
Measures of Success
Start: Jan 06 End: Aug 06
Agree on invention disclosure targets (Feb 06).
Investigate status and potential measures (Feb.06).
Start invention initiative (Mar 06).
Implement incentive proposal (Mar 06).
Implement organizational changes (Apr.06).
90 invention disclosures filed (Jul 06).
180 invention disclosures filed (Dec 06).
Reporting & Review
Management summary monthly to RD board
Project Schedule
See Measures of success
Responsibilities
Coach: Dr. Bocionek & Dr. Schneider-Hufschmidt
Program Manager: Bauregger, Hartmann
Add Project Status Summary:
achievements:
  Alignment with ISR for invention initiative.
  Inventor Training presentation prepared by ISR.
  Organizational change done.
issues - none
support/decisions needed - none
next steps
  Inventor training to be started top down in RD board.

## Slide 23: Project „Thin Client Phone“: Bauregger
Goals
Realization of a WLAN VoIP Phone Prototype.
Design like Apple’s iPOD Nano.
Priority thin package.
Skype client must be used.
802.11b/g implementation.
Measures of Success and project schedule
Start: Jan 06 End: Aug 06
Start Feature definitions (Jan 06)
Interdisciplinary team starts (Feb 06)
Draft Predevelopment Project Plan (Feb.06)
Final Predevelopment Project Plan (Mar.06)
System Supplier selection HW and SW (Mar.06)
System deliverables agreed with supplier (Apr. 06)
Component definition done (e.g. Display, etc.) (Apr.06)
Start PCB and Mechanical Design (Apr.06)
Prototype running (Jul 06)
Documentation (Aug.06)
Product decision (Aug 06)
Reporting & Review
Management summary monthly to RD board
Responsibilities
Coach: Dr. Bocionek
Program Manager: Bauregger
Project Leader: V. Otto
Add Project Status Summary:
achievements:
  Account opening done.
  Detailed feature definition with CTM started.
  Final project plan fixed (prototype).
  System supplier selected (Marvell).
  Design proposal for prototype and product available.
issues
  Skype support for SW realization needed.
  Project can only be continued as product project.
support/decisions needed
  Skype requests BenQ presentation (incl. BenQ Mobile company presentation, product story, business case).
  Decision for product development needed.
next steps
  Agree system deliverables with supplier (April).
  Complete component definition (April).
  Start PCB and Mechanical Design (April).
  Presentation at Skype (ASAP).
  Decision for product (ASAP).

## Slide 24: Project „cleanApoxi“: Fässler
Goals
  Establish clear platform concept, including
    Clean definition
    Clean architecture
    Clean release strategy
    Clean toolkit usage concept
Measures of Success
  Definitions in place (2/06)
  Sub workgroup formed (2/06)
  Kick-off working groups (3/06)
  Re-use of platform 7/07
  APOXI cost below Native cost
Responsibilities
  Program mgr: Georg Fässler
Reporting & Review
  Reporting and review every 2nd month
Project Schedule
Project Status Summary:
achievements
  - significant part of the work done during the FIT 4 APOXI workshop
issues
  none
support/decisions needed
  none
next steps
  Review of the documentation outlining the results of the FIT 4 APOXI workshop

## Slide 25
Project „ Fit 4 Apoxi“: Fässler (step 1: Analysis Project)
Charter for the team
- Re-define „platform“ in its totality adressing people, process and product needs. Derive an optimal supplier co-operation model based on a platform as R&D productivity tool, and having in mind a maximized re-use factor of all invested efforts (specs, designs, code/features, base products).
- Future-safety and R&D productivity will come from key informatics principles like abstraction, componentization, and backward-compatible design.
- The trade-offs between „good platform“ and „market pressure“ will be analyzed for a concrete product, e.g. Diamond, and described in at least two scenarios.
- Potential white spots in the functionality of Apoxi to allow for a first product will be identified (incl. an estimate of the time to completion)
- A decision will be possible at the end of the analysis phase what the first product on Apoxi will be, and when we can deliver.
Objectives for the „platform“
Clean architecture (incl. 3rd party components)
Clean release concept
Clean requirements & CR process
Clean project management process (incl. 3rd parties)
Clean development process (agile)
Clean training and education concept
Measures of Success
  Abstraction layer requirements in place (3/06)
  Agreed upon rationale for APOXI cost lower native cost (4/06)
  White spots in Apoxi known; IFX commitment to close (4/06)
  Apoxi product decisions possible for Q1-Q3 2007 (3/06)
  Project plan for next 6 – 12 months ready and agreed (4/06)
Responsibilities
  Program mgr: Georg Fässler / Uli Geiger
  PL: Patric Houben - Chief architect : Norbert Haiduk
  Team members: nominated
  Steering board: SB, Sydon, Mucke, Björk
Reporting & Review (until end of March)
  Reporting and review every week
Project Schedule
  Architecture :
    Group members identified; committed <01.03.06
    Workshop abstraction layer : 6.03.06 < T < 31.03.06
      including all development parties :IFX-Comneon, Aplix, PSE, Teleca
  Project Management :
    Release strategy < 10.03.06
    Requirement platform management < 31.03.06
    Process rollout < 31.03.06
Project Status Summary:
achievements
  FIT 4 APOXI workshop finished
next steps
  Review of the documentation outlining the results of the FIT 4 APOXI workshop

## Slide 26: Project MD Q-Improvement ( status 26.04.06 )
Goals
  Prevent defects and high return rates
  Detect and correct potential problems as early as possible
  Focus on PLM – SCM collaboration
    Parts
    Tools
    Suppliers
Measures of Success
  < 2% field return rate
Responsibilities
  Coach: Bocionek
  Program Manager: Thonhauser
Reporting & Review
  Monthly
Project Schedule
  Project start: Feb 06
  root cause/ levers : March 06
  - Start implementation : April 06
Add Project Status Summary:
achievements :
  3 sub project teams installed ( MD performance, Integrator supplier, MD / SQA interface )
  interdisciplinary teams nominated ( MD, SCM and SP )
  root cause and levers defined ( aligned between all parties )
  lead products : Onyx and Obsidian
  R&D MD restructuring done ( negative: 5 from 6 Ulm people left after 3 month )
  Interface to SCM SQA fixed and agreed between R&D and SCM
next steps: detailed project plan for improved integrator supplier concept ( May 06 )

## Slide 28: BACKUP