## Slide 1: Platinum TTM
Josef Bauregger
BMG PHE RD BOS
2006/05/22

## Slide 2: Platinum CM request
Status
  Platinum is one of 10 core projects
  Platinum DS 06.07 planned (according SWM DS is for retail version)
  DS 07.07 possible for operators acc. SWM (as Koala is here lead, if no Koala lead then 08.07)
CM request
  Platinum DS 05.07 for operators

## Slide 3: Platinum most critical features
SI voice recognition
  feasibility investigation started
  some features identified as risk already (e.g. voice control inside navigation)
GPS/A-GPS
  First implementation of new HW and SW (RFR6275 not working on EVB so far, no SW implementation available today)

## Slide 4: Platinum TTM
Critical line is SWM
Investigation was done how to come to an earlier DS for operators

## Slide 5: SWM: Scenario Platinum DS in 04/2007 (= 1st operator approval in 06/2007!)
1) Immediate start with Platinum specific features not possible due to:
  Voice Control and A-GPS solution still not clarified nor system concept defined, nor ISVs selected  no imediate start possible as required for early IOTs and DS in 04/2007 = high risk and potential delay of DS
  Resources for Voice Control and A-GPS (Munich experts) involved in Kestrel and DSP handover from AAL during June 2006
   High risk for DS in 04/2007
   Koala had to get a timeout of 2 months leading to DS in 06/2007
2) Risk reduction (especially for IOT) possible if fully A-GPS enabled HW is available early (Dec 2006)
3) Overall SW load situation very similar as with Koala due to identical operator requirements of Koala and Platinum (still a req. reduction needed due to overload)
4) Koala touch screen and landscape application mode already very well prepared for immediate start
5) Biggest challenge for whole platform is huge operator requirements (many big changes) and so expected long approval cycles with operators
 DS Retail in 04/2007 leads to a first operator approval in 06/2007 (Koala or Platinum)