## Agenda
Minutes of Meeting
CONFIDENTIAL
|  |  | Moderation by |  | Tel.:
|  |  | Dr. Thai Lai Pham |  | 35910
|  |  | Minutes written by |  | Tel.: | Dial-In No. (VC/TC)
|  |  | Dr. Thai Lai Pham |  | 35910 | 0049 89 20 60 35 70 / Conf. ID: 0815#
At (Day) |  | Date |  | from - till Time |  | Location/Building/Room
Monday |  | 2006-01-16 |  | 9:00 - 12:00 |  | BenQ, Grillparzerstr, 03.225
PHE R&D Board Meeting
Participants: |  |  |  |  | Absent:
Dr. Wolfgang Klebsch | Josef Bauregger |  |  |  | Dr. Dirk Didascalou
Hermann Thonhauser | Karsten Rudolph |  |  |  | Dr. Siegfried Bocionek
Dr. Thai-Lai Pham | Dr. Georg Fässler |  |  |  | Jürgen Riesmeyer
Jürgen Schmitz | Dr. Klaus Wacker |  |  |  | Mario Topel
Holger Asmussen | Olaf Dicker
Klaus Wingens | Christof Schwab
Ralf Scholz
Meeting Summary | [5 empty] | Who |  | Time
Agenda
I. | Management Update |  |  |  |  | Boccionek / Klebsch |  | 45 min
Jerry, Hawk, Wolf 5 New
| AI Tracking from last R&D Board Meeting |  |  |  |  | Pham |  | 15 min
II. | Overview activities (Tops, Flops, Issues) Program Management KLF |  |  |  |  | Asmussen |  | 30 min
| Overview activities (Tops, Flops, Issues) Program Management MCH |  |  |  |  | Topel |  | 30 min
III. | CoC's Topics
| Apoxi |  |  |  |  | Christof
| Trainings für MA |  |  |  |  | Karsten
Meeting Minutes
I. Management Information
II. Update from Program Management
A. Program Management KLF:
B. Program Management MUC:
III. CoC Topics

## Issue List
Priority: high, medium, low
R&D Board Action Items |  |  |  | Status: open, overdue, closed
ID | Priority | Status | Issue | Initiator | Date opened | Due Date | Responsible | Remark
1 | low | closed | SCM Reporting Format versenden | Pham | 2005-11-07 | 2005-11-07 | Pham
2 | medium | closed | Projekt zur Vereinheitlichung Meilensteine, Prozesse | Schmitz | 2005-11-07 |  | Schmitz | Gespräch mit KK; Weitere Infos nach dem Steering Board am 18.11 und Vorgehensweise, 19.12.: Kommunikationsmodell der Meilensteine zwischen PHE / PHA. Abgleich der wichtigsten Meilensteine noch nicht entschieden. Lead Masselink, Schmitz U. R&D Vertreter; Next Step: Alignment Klesch/Schmitz
3 | high | closed | Align with PHE and CTM how to ensure alignment between PHE R&D and CTM regarding to CTO issues and roadmap | Klebsch | 2005-11-14 |  | Klebsch | Ende Januar: CTM stellt Roadmap zur Verfügung. Freigabe Prozess verabredet
4 | high | closed | Adjust MEP v 7 to match new cycle time as defined with the 4 product categories | Asmussen | 2005-11-14 |  | Schmitz / Fillers | MEP v8 Projekt Team aufgesetzt: Betting (TPM), Schmitz (R&D), Fillers (QM);
5 | medium | closed | Provide template for reporting of restructuring projects within each R&D location | Klebsch | 2005-11-14 | 2005-11-17 | Thonhauser / Pham
6 | high | closed | Organise telco to discuss AT / FK candidate list | Klebsch | 2005-11-14 | 2005-11-17 | Pham
7 | high | closed | Escalation to IT management and ensure availability of R&D IT tools and infrastructure | Asmussen | 2005-11-14 | 2005-11-15 | Schmitz
8 | medium | closed | Ensure order of Musterbau as defined (1300 devices for R&D; above to be ordered by PM itself) | Asmussen | 2005-11-14 |  | Asmussen | WS mit CPM für 21.12.05 geplant: Keine Akzeptanz bei CPM Musterbau zu verändern.
9 | medium | closed | Provide communication package for communication within organisation | Bauregger | 2005-11-14 |  | Klebsch / Pham
10 | medium | closed | Align with PHE head how to book services for PHA (e.g. acceptance test or training request) | Wacker | 2005-11-14 | 2005-11-18 | Klebsch / Wingens | Budget für PHA und PHE geplant. Verwaltung der Beauftragung in der BA.
11 | high | closed | Escalate dial in solution (e.g. Corina) in BenQ corporate environment to first Theis and then Joos, Eickholt | Asmussen | 2005-12-19 | 2005-12-23 | Bocionek | IT Is currently working CORA as global solution
12 | high | closed | Introduce 1 sheet service order from PHA and establish a monthly R&D order status report | Bocionek | 2005-12-19 | 2006-01-09 | Wingens | ongoing process. Request from PHA to KWi. KWi will approved for planning for PMC planning. Differentiation of products necessary.
13 | high | closed | Align with Dirk Didascalou regarding to BEJ support obligation for SGL. To be escalate to Eickholt if no clarification | Asmussen | 2005-12-19 | 2005-12-21 | Klebsch | SGL maintenance is committed by PHA BEJ R&D.
14 | medium | closed | Provide MEP v 7 Delta project decription on 1 sheet with target and project measure | Bocionek | 2005-12-19 | 2005-12-23 | Schmitz
15 | high | closed | Provide feedback to Katrin Braun regarding to Jerry resource request | Asmussen | 2005-12-19 | 2005-12-21 | Klebsch / Bocionek | AAL until M1, then transfer to BEJ
16 | high | closed | Provide Apoxi cost situation overview to Bocionek and Klebsch as preparation for further esclation to Eickholt | Wingens | 2005-12-19 | 2005-12-19 | Höckenreiner
17 | high | closed | Clarify HC recruiting by using print media, e.g. VDI | Thonhauser | 2005-12-19 | 2005-12-23 | Bocionek | Ad is plan for VDI on 06.01.06
18 | high | closed | Prioritization of backlog features for Koala | Bocionek | 2005-12-19 | 2006-01-16 | Rudolph | Will be done for Ruby
19 | high | closed | Planning of HC phase 2a and phase 2b in planning database (PMC) | Thonhauser | 2005-12-19 | 2005-12-23 | All CoC
20 | medium | closed | Bi-weekly HC ramp up report | Thonhauser | 2005-12-19 |  | All CoC
21 | medium | closed | Identify number of ST resources required for MAO | Klebsch | 2005-12-19 | 2005-12-23 | Wacker | MAO headcount: proposal given to Klaus Wingens for agreement, no answer yet
22 | medium | open | Complete product class definition with Musterbaumengen per product class | Asmussen | 2006-01-10 | 2006-01-16 | Schwab | Provided by Lutterbeck on 13.01.06. Feedback from CoC open.
23 | medium | closed | CR: Momintate staff for modifiying CR process | Asmussen | 2006-01-10 |  | Thonhauser / Pham | SW: Dietzen; HW: Beba
24 | medium | closed | CR: Provide feedback on accounting of CR of foreign services in SAP SK | Asmussen | 2006-01-10 |  | Faessler | SWAN: Mid 02/06: 75G/85G End 02/06
25 | high | closed | Provide intial feedback on SW status of Jerry: Scope, Key issues and possible levers to meet TTM | Asmussen | 2006-01-10 | 2006-01-11 | Faessler
26 | high | closed | Clarify decision on Jerry and Hawk in Taipei with JE | Asmussen | 2006-01-10 | 2006-01-13 | Klebsch / Bocionek
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
| high | open | Provide updated skill mix | Klebsch |  | 2006-01-17 | CoC
| high | open | Please check accounting of staff. Klaus Wingens will send out latest overview | Wingens | 2006-01-16 | 2006-01-20 | CoC
2005-04-21

## Zeitkonto
| Total | 2005-08-29 | 2005-10-05 | 2005-11-07 | 2005-11-14 | 2005-12-19
Asmussen | 0:00
Bauregger | 0:00 |  |  |  | 0:00
Didascalou | 0:00 | 0:00
Fässler | 0:00
Klebsch | 0:00 |  | 0:00
Pham | 0:00
Riesmeyer | 0:00 |  |  |  | 0:00
Rudolph | 0:00
Schmitz | 0:00
Schwab | 0:00 | 0:00
Thonhauser | 0:00
Topel | 0:00 | 0:00
Wacker | 0:00
Wingens | 0:00