## Agenda
Minutes of Meeting
CONFIDENTIAL
|  |  | Moderation by |  | Tel.:
|  |  | Dr. W. Klebsch |  | 35910
|  |  | Minutes written by |  | Tel.: | Dial-In No. (VC/TC)
|  |  | Ch. Schwab |  | 35910 | 0049 89 20 60 35 70 / Conf. ID: 0815#
At (Day) |  | Date |  | from - till Time |  | Location/Building/Room
Monday |  | 2006-02-13 |  | 9:00 - 12:00 |  | BenQ, Grillparzerstr, 03.225
PHE R&D Board Meeting
Participants: |  |  |  |  | Absent:
Dr. Wolfgang Klebsch | Josef Bauregger | Dr. Siegfried Bocionek
Hermann Thonhauser | Karsten Rudolph | Jürgen Riesmeyer
Dr. Thai-Lai Pham | Dr. Georg Fässler | Mario Topel
Jürgen Schmitz | Dr. Klaus Wacker
Holger Asmussen | Olaf Dicker
Klaus Wingens | Christof Schwab
Ralf Scholz | Dr. Dirk Didascalou
Meeting Summary | [5 empty] | Who |  | Time
Agenda
I. | General Issues
II. | Update of Project Status Swift, Polaris, Kestrel, … (for Functional Review) |  |  |  |  | Topel / Asmussen
Prototype apmles
Kestrel refresh
Classification product classes
III. | Presentation of R&D KPI's to be agreed on | [6 empty] | 60 min
Functional Objectives
Swan Apoxi
Roadmap outlook
Maintenance SUN
Planning assumptions
SP Apoxi; Qualcomm
Requests Beijing
Accoustic shock E-Gold Radio
IV. | [5 empty] | Thonhauser / Wacker / Dicker / Rudolph
Meeting Minutes
I. Management Information
Apoxi Straetegy ajustment | [5 empty] | Asmussen
Absolutly no communication within the organization
Swan, Diamond on native
Apoxi delay to be detailled
No partner communication; before go by Bocionek
Roadmap | [5 empty] | Asmussen
Performance products not feasible based on SG2 native
Emerald shift to 3G
Sandpiper, Jade repriotization; very low prio
Lapislazuli also very low prio
KLF = Swan, Diamond, Lolite
Moonstone based on EGR
First Apoxi phone will be Lolite; SG2/ SG3 not yet decided; UMTS Apoxi not yet decided
3G late = low end UMTS; platform not yet decided; potential Apoxi UMTS phone
Apoxi replanning/saving will initiated ; target latest next wedensday
3G roadmap presentation | [5 empty] | Topel
Ruby (02/07) and Koala (04/07) based on QCT 6280
Goldstone under evaluation (07 /07or 08/07); if feasible Goldstone will be realized instead of Mallow
Goldstone would be based on a dualcore QCT 7200 platform
Interaction with Taiwan regarding the handover of projects works perfectly; all other statments are rumors
Apoxi replanning/saving will initiated next week
QCT replanning/saving will initiated ; target latest next wedensday
II. Update from Program Management
A. Program Management KLF:
B. Program Management MUC:
III. CoC Topics/others
Resource request Beijing; | [5 empty] | Didascalou
1 expert HW; 1 manager ST needed; requests placed
Acoustic shock EGR; Ralf Hartmann requested; IFX not able to provide actual the sufficent expertise

## Issue List
Priority: high, medium, low
R&D Board Action Items |  |  |  | Status: open, overdue, closed
ID | Priority | Status | Issue | Initiator | Date opened | Due Date | Responsible | Remark
1 | low | closed | SCM Reporting Format versenden | Pham | 2005-11-07 | 2005-11-07 | Pham
2 | medium | closed | Projekt zur Vereinheitlichung Meilensteine, Prozesse | Schmitz | 2005-11-07 |  | Schmitz | Gespräch mit KK; Weitere Infos nach dem Steering Board am 18.11 und Vorgehensweise, 19.12.: Kommunikationsmodell der Meilensteine zwischen PHE / PHA. Abgleich der wichtigsten Meilensteine noch nicht entschieden. Lead Masselink, Schmitz U. R&D Vertreter; Next Step: Alignment Klesch/Schmitz
3 | high | closed | Align with PHE and CTM how to ensure alignment between PHE R&D and CTM regarding to CTO issues and roadmap | Klebsch | 2005-11-14 |  | Klebsch | Ende Januar: CTM stellt Roadmap zur Verfügung. Freigabe Prozess verabredet
4 | high | closed | Adjust MEP v 7 to match new cycle time as defined with the 4 product categories | Asmussen | 2005-11-14 |  | Schmitz / Fillers | MEP v8 Projekt Team aufgesetzt: Betting (TPM), Schmitz (R&D), Fillers (QM);
5 | medium | closed | Provide template for reporting of restructuring projects within each R&D location | Klebsch | 2005-11-14 | 2005-11-17 | Thonhauser / Pham
6 | high | closed | Organise telco to discuss AT / FK candidate list | Klebsch | 2005-11-14 | 2005-11-17 | Pham
7 | high | closed | Escalation to IT management and ensure availability of R&D IT tools and infrastructure | Asmussen | 2005-11-14 | 2005-11-15 | Schmitz
8 | medium | closed | Ensure order of Musterbau as defined (1300 devices for R&D; above to be ordered by PM itself) | Asmussen | 2005-11-14 |  | Asmussen | WS mit CPM für 21.12.05 geplant: Keine Akzeptanz bei CPM Musterbau zu verändern.
9 | medium | closed | Provide communication package for communication within organisation | Bauregger | 2005-11-14 |  | Klebsch / Pham
10 | medium | closed | Align with PHE head how to book services for PHA (e.g. acceptance test or training request) | Wacker | 2005-11-14 | 2005-11-18 | Klebsch / Wingens | Budget für PHA und PHE geplant. Verwaltung der Beauftragung in der BA.
11 | high | closed | Escalate dial in solution (e.g. Corina) in BenQ corporate environment to first Theis and then Joos, Eickholt | Asmussen | 2005-12-19 | 2005-12-23 | Bocionek | IT Is currently working CORA as global solution
12 | high | closed | Introduce 1 sheet service order from PHA and establish a monthly R&D order status report | Bocionek | 2005-12-19 | 2006-01-09 | Wingens | ongoing process. Request from PHA to KWi. KWi will approved for planning for PMC planning. Differentiation of products necessary.
13 | high | closed | Align with Dirk Didascalou regarding to BEJ support obligation for SGL. To be escalate to Eickholt if no clarification | Asmussen | 2005-12-19 | 2005-12-21 | Klebsch | SGL maintenance is committed by PHA BEJ R&D.
14 | medium | closed | Provide MEP v 7 Delta project decription on 1 sheet with target and project measure | Bocionek | 2005-12-19 | 2005-12-23 | Schmitz
15 | high | closed | Provide feedback to Katrin Braun regarding to Jerry resource request | Asmussen | 2005-12-19 | 2005-12-21 | Klebsch / Bocionek | AAL until M1, then transfer to BEJ
16 | high | closed | Provide Apoxi cost situation overview to Bocionek and Klebsch as preparation for further esclation to Eickholt | Wingens | 2005-12-19 | 2005-12-19 | Höckenreiner
17 | high | closed | Clarify HC recruiting by using print media, e.g. VDI | Thonhauser | 2005-12-19 | 2005-12-23 | Bocionek | Ad is plan for VDI on 06.01.06
18 | high | closed | Prioritization of backlog features for Koala | Bocionek | 2005-12-19 | 2006-01-16 | Rudolph | Will be done for Ruby
19 | high | closed | Planning of HC phase 2a and phase 2b in planning database (PMC) | Thonhauser | 2005-12-19 | 2005-12-23 | All CoC
20 | medium | closed | Bi-weekly HC ramp up report | Thonhauser | 2005-12-19 |  | All CoC
21 | medium | closed | Identify number of ST resources required for MAO | Klebsch | 2005-12-19 | 2005-12-23 | Wacker | MAO headcount: proposal given to Klaus Wingens for agreement, no answer yet
22 | medium | closed | Complete product class definition with Musterbaumengen per product class | Asmussen | 2006-01-10 | 2006-01-16 | Schwab | Provided by Lutterbeck on 13.01.06. Feedback from CoC open.
23 | medium | closed | CR: Momintate staff for modifiying CR process | Asmussen | 2006-01-10 |  | Thonhauser / Pham | SW: Dietzen; HW: Beba
24 | medium | closed | CR: Provide feedback on accounting of CR of foreign services in SAP SK | Asmussen | 2006-01-10 |  | Faessler | SWAN: Mid 02/06: 75G/85G End 02/06
25 | high | closed | Provide intial feedback on SW status of Jerry: Scope, Key issues and possible levers to meet TTM | Asmussen | 2006-01-10 | 2006-01-11 | Faessler
26 | high | closed | Clarify decision on Jerry and Hawk in Taipei with JE | Asmussen | 2006-01-10 | 2006-01-13 | Klebsch / Bocionek
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
| high | done | Provide updated skill mix | Klebsch |  | 2006-01-17 | CoC
| high | done | Please check accounting of staff. Klaus Wingens will send out latest overview | Wingens | 2006-01-16 | 2006-01-25 | CoC
|  |  | Doors is the one and only accepted Requirements input; start at once | Bocionek | 2006-01-23 | 2006-01-30 | Schmitz
| high | done | Clarification Class 4 prototype sample; | Schwab | 2006-01-23 | 2006-01-30 | Faessler
| high | done | MockUp, Fräsmuster and prototypes handling sale; instead of mockups "Fräsmuster" managed by MD; Lieferschein Lottner-Vorbeck | Thonhauser | 2006-01-23 |  | Wingens/Thonhauser
| high | done | Prototype concept (R&D, sales, …) | Asmussen | 2006-01-23 | 2006-02-06 | Thonhauser
| high | done | Iniative slides to be communicated (Value: heros Polaris, Swift, Kestrel, Pelicane; etc. ) | Asmussen | 2006-01-23 | 2006-01-30 | Bocionek; Klebsch
| high | done | Cost: Improve product cost position; Cost sensitivity; Workshop: targets, participants, … organized by J. Schwarplies | Asmussen | 2006-01-23 | 2006-01-25 | Schwarplies
| high | done | Cost saving CoC driven (10-12 targets); Prep. Saving workshop 26.1; | Asmussen | 2006-01-23 | 2006-01-26 | CoC heads
| mid | open | Act. TPM list will be distributed by TPM | Asmussen | 2006-01-23 | 2006-01-25 | Asmussen/Topel
| mid | open | HR; Arbeitserlaubnis in the states; visa problem possible; guideline for communication | Topel | 2006-01-23 | 2006-02-06 | Klebsch | Mrs. Cordes is taking care from HR side
| high | done | Secure clear interfaces Qualcomm; Friesen HW/Moser SW | Topel | 2006-01-23 | 2006-01-30 | CoC heads
| high | done | DVB-H transfer from Aal to Munich; timetable, .. | Topel | 2006-01-23 | 2006-02-06 | Rudolph
| high | open | Delta clarification | Topel | 2006-01-23 | 2006-02-13 | Wingens/Klebsch/Bocionek
| high | done | Single entry point requiremnets; R&D SPC | Bauregger | 2006-01-23 | 2006-01-23 | all
| high | done | Delta evaluation CY 06 | Schwab | 2006-01-23 | 2006-02-01 | Schwab/Wingens
| mid | done | Apoxi Roadmap Abklärung; 18- 19 Uhr; Donnerstag | Schwab | 2006-01-23 | 2006-01-26 | Asmussen
| high | done | Requested project capas to reviewed; TPM KPIs should be aligned with R&D KPIs; assumptions KLF 6 projects (Class 1: 2; Class 2: 2; Class3: 1; Class 4:1) ; assumptions MCH 4 projects (Class 1: 1; Class 2: 1; Class3: 1; Class 4:1) ; | Asmussen | 2006-01-23 | 2006-01-30 | all
| mid | done | MEP Presentation in PD Board | Bocionek | 2006-01-23 | 2006-01-30 | Schmitz Uwe
| mid | done | Slides all hands meeting to be reworked | Bocionek | 2006-01-30 | 2006-02-01 | Bocionek
| mid | open | actual vision and mission slides to be distributed; Communication guideline | Bocionek | 2006-01-30 | 2006-02-13 | Bocionek
| mid | done | Communication guideline next R&D board; Stuelpner to be invited | Schwab | 2006-01-30 | 2006-02-01 | Bocionek
| high | open | role based team analysis (see scrum team slide) | Bocionek | 2006-01-30 | 2006-02-13 | CoC | Template to be distributed
| high | open | PV roles split TPM-R&D to be agreed | Bocionek | 2006-01-30 | 2006-02-13 | Schmitz
| high | done | IFX SG2 solution to be found regarding switch from platform approach to reference design; benchmarking; contractual position to be clarified; time & cost impacts | Bocionek | 2006-01-30 | 2006-02-06 | Bauregger | FTA on reference board will be performed by IFX; Detailled system speciifaction will be performed bey IFX, BenQ will review the system specification
| high | open | Standard efforts for scenario tool to be provided to Robert Linder | Klebsch | 2006-01-30 | 2006-02-06 | Rudolph; Faesler
| high | open | Add. HC IT consolidated presentation; benchmark figures Med to be added | Klebsch | 2006-01-30 | 2006-02-06 | Schmitz | Info MED missing
| mid | open | MEP metrics benchmarking; target reduce complexity | Bocionek | 2006-01-30 |  | Schmitz | Due date tbc.
| mid | done | Support recruiting office at CeBit; every R&D board memeber half a day | Bocionek | 2006-01-30 | 2006-02-06 | Koch
| mid | open | Kick off to be started; Post mortem analysis to be peformed by project head; Minos team shall show lessons learnt | Bocionek | 2006-01-30 | 2006-02-06 | Klebsch | Kick off to be started wih Mions
| high | done | Transfer Kestrel knowledge to PHA | Eickholt | 2006-01-30 | 2006-02-06 | Topel
| high | done | Apoxi Gemstone cost analysis | Schwab | 2006-02-06 | 2006-02-13 | Schwab/Wingens | incl. CTO
| high | open | Functional performance to be defined and agreed | Klebsch | 2006-02-06 |  | all
| high | open | review and finialize Management objecties agreement | Bocionek/Klebsch | 2006-02-06 | 2006-02-08 | all | document on P:-Drive
| mid | open | check possibility to support Encyrption solution neccessary for HW and SW - PGP und Mail neccessary. | Rudokph | 2006-02-06 | 2006-02-17 | Schmitz/Rudolph
| high | open | KPI Feed Back latest until Thursday | Thonhauser | 2006-02-13 | 2006-02-15 | all CoGs
| high | open | Internal Apoxi meeting for pro/con different Apoxi scenarios | Schwab | 2006-02-13 | 2006-02-16 | Faessler
| high | open | ASP EGR feed back | Didascalou | 2006-02-13 | 2006-02-20 | Bauregger
| high | open | Prototype sample monitoring to be driven by TPM | Thonhauser | 2006-02-13 | 2006-02-20 | Asmussen/Topel
| high | open | Mallow-Goldstone decision to be made within the next 3 weeks; predevelopment decision to be reflected; | Schwab | 2006-02-13 | 2006-03-06 | Topel
| high | open | Qualcomm concepts to be clarified | Thonhauser | 2006-02-13 | 2006-02-27 | Topel/Rudolph/Schwab
2005-04-21

## Zeitkonto
| Total | 2005-08-29 | 2005-10-05 | 2005-11-07 | 2005-11-14 | 2005-12-19
Asmussen | 0:00
Bauregger | 0:00 |  |  |  | 0:00
Didascalou | 0:00 | 0:00
Fässler | 0:00
Klebsch | 0:00 |  | 0:00
Pham | 0:00
Riesmeyer | 0:00 |  |  |  | 0:00
Rudolph | 0:00
Schmitz | 0:00
Schwab | 0:00 | 0:00
Thonhauser | 0:00
Topel | 0:00 | 0:00
Wacker | 0:00
Wingens | 0:00