## Agenda
Minutes of Meeting
CONFIDENTIAL
|  |  | Moderation by |  | Tel.:
|  |  | Dr. S. Bocionek |  | 54600
|  |  | Minutes written by |  | Tel.: | Dial-In No. (VC/TC)
|  |  | Dr. W. Klebsch |  | 34430 | 0049 89 20 60 35 70 / Conf. ID: 2251#
At (Day) |  | Date |  | from - till Time |  | Location/Building/Room
Monday |  | 2006-03-13 |  | 14.00-16.00 |  | BenQ, Grillparzerstr, 03.225
PHE R&D Board Meeting
Participants: |  |  |  |  | Absent: | Tentative:
Dr. Siegfried Bocionek | Klaus Wingens |  | Holger Asmussen |  | Jürgen Riesmeyer
Dr. Wolfgang Klebsch | Ralf Scholz |  | Mario Topel |  | Jürgen Schmitz
Hermann Thonhauser |  |  |  |  | Dirk Didascalou
Josef Bauregger | Olaf Dicker
Karsten Rudolph | Mariano Julio
Dr. Georg Fässler | Dr. Dirk Didascalou
Dr. Klaus Wacker
Jürgen Riesmeyer
Meeting Summary | [5 empty] | Who |  | Time
Agenda
I. | BenQ Mobile Vision – Mission – Values – Corporate Messages |  |  |  |  | Marco Stülpner |  | 20 min.
II. | TTM goals in mgmt objectives |  |  |  |  | Siegfried Bocionek
III. | LQA / Leadership Quality Analysis |  |  |  |  | Siegfried Bocionek
IV. | Business Trip Regulations |  |  |  |  | Siegfried Bocionek
V. | Manaus - Budget Planning and Strategy |  |  |  |  | Mariano / K Rudolph
VI. | Additional support request from PHE for Beijing |  |  |  |  | Wacker / Bauregger
VII. | Process & Tools Management / Planning communication |  |  |  |  | Thonhauser
VIII: | TPM KLf |  |  |  |  | Asmussen
IX. | TPM Mch |  |  |  |  | Topel
X.
Meeting Minutes | [5 empty] | Who |  | Time
Ad I: Presentation see P:\RDM_Department\PD_Factory\PD_Board\2006\2006-03-13
Presentation by Marco Stülpner (S&C) about "BenQ Mobile Looking Ahead" with the following key messages:
- Turn around business in 3 Phases: Transition by E2006, Expansion by E2007, 3C Convergence by >2008
- Main objectives during the Transition phase: Drive Topline + Stabilize Market Share + Reduce Cost
Creating value with profitability before market share!
- Brand launch, 3GSM and CeBIT to increase the market recognition
Positive feedback even by financial analysts from Credit Suisse and Morgan Stanley.
- Asia is driving competition: The China Market growing with 13% pa, Asia with 10% pa.
Asia is Innovation Setter and most of the component manufacturers are in Asia
=> BenQ is well positioned
- BenQ's 3C competencies: Communication + Consumer Electronics + Computing
3C convergence will significantly increase the addressable market
Dual-mode WiFi Phones or DVB-H Phones are examples for Digital convergence technologies
Provide slide with a summary of all "valid" mission and vision statements | [5 empty] | Marco Stülpner |  | 22.03.
Ad II: TTM goals in mgmt objectives
accepted by all PHE R&D board members
Ad III: Leadership Quality Analysis: P:\RDM_Department\PD_Factory\PD_Board\2006\2006-03-13 by P. Gschwendtner / BMG HR
- LQA is a voluntary measure and does not need a BR approval
- LQA is planned as a part of the feedback-tools of PHE RD comprising:
Leadership Performance Feedback (LPF)
Leadership Quality Analysis (LQA)
Peer Feedback (planned)
[360° Feedback (not as a standard)]
- LQA: Managers shall assess managers about results, capabilities and suitability
Target Group: R&D Board Members plus 1 level below.
As an interim solution LQA will be performed on paper basis
in practise the LPF will show as the former Siemens Leadership Framework (SLF)
Leadership Results: Financials, Employees, Customers, Processes
Leadership Capability: Drive, Focus, Impact, Guide
SBo will generate assessment for board members (with support by WKl) | [5 empty] | Bocionek |  | t.b.d.
Ad IV: Business Trip Regulations: P:\RDM_Department\PD_Factory\PD_Board\2006\2006-03-13
Ad V: Manaus - Budget Planning and Strategy
- With current tasks (SW, ST) the internal and external resources in Manaus are far from being fully loaded.
The consultant company DBA's branch in Manaus, with 27 engineers assigned to BenQ, is in danger of close down due to underload.
Even the current tax obligation is not yet fully supported with development tasks
HTh and KWi to clarify budget and present during next R&D board meeting | [5 empty] | Thonhauser/Wingens |  | 20.03.
SBo, KWa, KRu, GFä to define strategy for MAO for next 2 years | [5 empty] | Bocionek |  | 20.03.
SBo to visit MAO in Beg 04/06 | [5 empty] | Bocionek
Ad VI: Additional support request from PHE for Beijing
- CM regarding Amber as a key product for the christmas business 2006
Beijing is not able to speed up development due inexperienced local engineers and DDi is now repeatedly asking for support from PHE.
Beijing is even questioning the Beijing contributions to Jerry.
WKl to analyse with DDi, KWi and JBau the request and to provide a solution | [5 empty] | Klebsch |  | 20.03.
Ad VII: Process & Tools Management / Planning communication
- Hermann Thonhauser will stand in for the new organization PTM (Process & Tools Management)
- Clearquest: Tool handling will be in the responsibility of ST (with Mr Ziegler in charge)
- CM Tools: No final solution yet for Clearcase vs Synergy Roland Betz from Syngo will be in Munich in cw13 for analysis of the situation
- HTh will take over the responsibility for PMC planning from CSch.
- SBo proposoal for the Budget Planning Process: Planning tool shall be open for Read-Write only 1x per year; after budget fixing access shall be read-only. Any changes necessitate CR's on budget, which are to approved by the R&D board.
HTh to provide the agreed regulations for CQ and to get a R&D board agreement | [5 empty] | Thonhauser |  | 20.03.
Any communication with Hans Höckenreiner about planning with Cc to HTh | [5 empty] | all |  | general
Ad VIII: Report from TPM KLf | [5 empty] | Asmussen
- After reviewing all running projects three projects have shown "bad" M1's.
Swift: at M1 a fully unrealistic BoM of 75€ was agreed. In reality 86€ provided to be feasible. As a consequence the profitability is deep red.
Minos: at M1 regarded a C-class now a S-class phone. Recalculation of BoM by B4/06
- IFX is under pressure w/r to EGRadio. IFX agreed to reduce the set price by 0.60€, as soon as the IFX ULC1 platform is selected for a product project, which, however is not on the roadmap yet!
Ad IIX: Report from TPM Mch | [5 empty] | Topel
- Kestrel: declaration of S3 was planned for today but was rejected by QM due to NCCPi too high. Expectation: 110.000 vs 144.000. SW freeze scheduled for 22.3. with NCCPi 110k to 120k

## Issue List
Priority: high, medium, low
R&D Board Action Items |  |  |  | Status: open, overdue, closed
ID | Priority | Status | Issue | Initiator | Date opened | Due Date | Responsible | Remark
1 | low | closed | SCM Reporting Format versenden | Pham | 2005-11-07 | 2005-11-07 | Pham
2 | medium | closed | Projekt zur Vereinheitlichung Meilensteine, Prozesse | Schmitz | 2005-11-07 |  | Schmitz | Gespräch mit KK; Weitere Infos nach dem Steering Board am 18.11 und Vorgehensweise, 19.12.: Kommunikationsmodell der Meilensteine zwischen PHE / PHA. Abgleich der wichtigsten Meilensteine noch nicht entschieden. Lead Masselink, Schmitz U. R&D Vertreter; Next Step: Alignment Klesch/Schmitz
3 | high | closed | Align with PHE and CTM how to ensure alignment between PHE R&D and CTM regarding to CTO issues and roadmap | Klebsch | 2005-11-14 |  | Klebsch | Ende Januar: CTM stellt Roadmap zur Verfügung. Freigabe Prozess verabredet
4 | high | closed | Adjust MEP v 7 to match new cycle time as defined with the 4 product categories | Asmussen | 2005-11-14 |  | Schmitz / Fillers | MEP v8 Projekt Team aufgesetzt: Betting (TPM), Schmitz (R&D), Fillers (QM);
5 | medium | closed | Provide template for reporting of restructuring projects within each R&D location | Klebsch | 2005-11-14 | 2005-11-17 | Thonhauser / Pham
6 | high | closed | Organise telco to discuss AT / FK candidate list | Klebsch | 2005-11-14 | 2005-11-17 | Pham
7 | high | closed | Escalation to IT management and ensure availability of R&D IT tools and infrastructure | Asmussen | 2005-11-14 | 2005-11-15 | Schmitz
8 | medium | closed | Ensure order of Musterbau as defined (1300 devices for R&D; above to be ordered by PM itself) | Asmussen | 2005-11-14 |  | Asmussen | WS mit CPM für 21.12.05 geplant: Keine Akzeptanz bei CPM Musterbau zu verändern.
9 | medium | closed | Provide communication package for communication within organisation | Bauregger | 2005-11-14 |  | Klebsch / Pham
10 | medium | closed | Align with PHE head how to book services for PHA (e.g. acceptance test or training request) | Wacker | 2005-11-14 | 2005-11-18 | Klebsch / Wingens | Budget für PHA und PHE geplant. Verwaltung der Beauftragung in der BA.
11 | high | closed | Escalate dial in solution (e.g. Corina) in BenQ corporate environment to first Theis and then Joos, Eickholt | Asmussen | 2005-12-19 | 2005-12-23 | Bocionek | IT Is currently working CORA as global solution
12 | high | closed | Introduce 1 sheet service order from PHA and establish a monthly R&D order status report | Bocionek | 2005-12-19 | 2006-01-09 | Wingens | ongoing process. Request from PHA to KWi. KWi will approved for planning for PMC planning. Differentiation of products necessary.
13 | high | closed | Align with Dirk Didascalou regarding to BEJ support obligation for SGL. To be escalate to Eickholt if no clarification | Asmussen | 2005-12-19 | 2005-12-21 | Klebsch | SGL maintenance is committed by PHA BEJ R&D.
14 | medium | closed | Provide MEP v 7 Delta project decription on 1 sheet with target and project measure | Bocionek | 2005-12-19 | 2005-12-23 | Schmitz
15 | high | closed | Provide feedback to Katrin Braun regarding to Jerry resource request | Asmussen | 2005-12-19 | 2005-12-21 | Klebsch / Bocionek | AAL until M1, then transfer to BEJ
16 | high | closed | Provide Apoxi cost situation overview to Bocionek and Klebsch as preparation for further esclation to Eickholt | Wingens | 2005-12-19 | 2005-12-19 | Höckenreiner
17 | high | closed | Clarify HC recruiting by using print media, e.g. VDI | Thonhauser | 2005-12-19 | 2005-12-23 | Bocionek | Ad is plan for VDI on 06.01.06
18 | high | closed | Prioritization of backlog features for Koala | Bocionek | 2005-12-19 | 2006-01-16 | Rudolph | Will be done for Ruby
19 | high | closed | Planning of HC phase 2a and phase 2b in planning database (PMC) | Thonhauser | 2005-12-19 | 2005-12-23 | All CoC
20 | medium | closed | Bi-weekly HC ramp up report | Thonhauser | 2005-12-19 |  | All CoC
21 | medium | closed | Identify number of ST resources required for MAO | Klebsch | 2005-12-19 | 2005-12-23 | Wacker | MAO headcount: proposal given to Klaus Wingens for agreement, no answer yet
22 | medium | closed | Complete product class definition with Musterbaumengen per product class | Asmussen | 2006-01-10 | 2006-01-16 | Schwab | Provided by Lutterbeck on 13.01.06. Feedback from CoC open.
23 | medium | closed | CR: Momintate staff for modifiying CR process | Asmussen | 2006-01-10 |  | Thonhauser / Pham | SW: Dietzen; HW: Beba
24 | medium | closed | CR: Provide feedback on accounting of CR of foreign services in SAP SK | Asmussen | 2006-01-10 |  | Faessler | SWAN: Mid 02/06: 75G/85G End 02/06
25 | high | closed | Provide intial feedback on SW status of Jerry: Scope, Key issues and possible levers to meet TTM | Asmussen | 2006-01-10 | 2006-01-11 | Faessler
26 | high | closed | Clarify decision on Jerry and Hawk in Taipei with JE | Asmussen | 2006-01-10 | 2006-01-13 | Klebsch / Bocionek
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
| high | done | Provide updated skill mix | Klebsch |  | 2006-01-17 | CoC
| high | done | Please check accounting of staff. Klaus Wingens will send out latest overview | Wingens | 2006-01-16 | 2006-01-25 | CoC
|  |  | Doors is the one and only accepted Requirements input; start at once | Bocionek | 2006-01-23 | 2006-01-30 | Schmitz
| high | done | Clarification Class 4 prototype sample; | Schwab | 2006-01-23 | 2006-01-30 | Faessler
| high | done | MockUp, Fräsmuster and prototypes handling sale; instead of mockups "Fräsmuster" managed by MD; Lieferschein Lottner-Vorbeck | Thonhauser | 2006-01-23 |  | Wingens/Thonhauser
| high | done | Prototype concept (R&D, sales, …) | Asmussen | 2006-01-23 | 2006-02-06 | Thonhauser
| high | done | Iniative slides to be communicated (Value: heros Polaris, Swift, Kestrel, Pelicane; etc. ) | Asmussen | 2006-01-23 | 2006-01-30 | Bocionek; Klebsch
| high | done | Cost: Improve product cost position; Cost sensitivity; Workshop: targets, participants, … organized by J. Schwarplies | Asmussen | 2006-01-23 | 2006-01-25 | Schwarplies
| high | done | Cost saving CoC driven (10-12 targets); Prep. Saving workshop 26.1; | Asmussen | 2006-01-23 | 2006-01-26 | CoC heads
| mid | open | Act. TPM list will be distributed by TPM | Asmussen | 2006-01-23 | 2006-01-25 | Asmussen/Topel
| mid | open | HR; Arbeitserlaubnis in the states; visa problem possible; guideline for communication | Topel | 2006-01-23 | 2006-02-06 | Klebsch | Mrs. Cordes is taking care from HR side
| high | done | Secure clear interfaces Qualcomm; Friesen HW/Moser SW | Topel | 2006-01-23 | 2006-01-30 | CoC heads
| high | done | DVB-H transfer from Aal to Munich; timetable, .. | Topel | 2006-01-23 | 2006-02-06 | Rudolph
| high | open | Delta clarification | Topel | 2006-01-23 | 2006-02-13 | Wingens/Klebsch/Bocionek
| high | done | Single entry point requiremnets; R&D SPC | Bauregger | 2006-01-23 | 2006-01-23 | all
| high | done | Delta evaluation CY 06 | Schwab | 2006-01-23 | 2006-02-01 | Schwab/Wingens
| mid | done | Apoxi Roadmap Abklärung; 18- 19 Uhr; Donnerstag | Schwab | 2006-01-23 | 2006-01-26 | Asmussen
| high | done | Requested project capas to reviewed; TPM KPIs should be aligned with R&D KPIs; assumptions KLF 6 projects (Class 1: 2; Class 2: 2; Class3: 1; Class 4:1) ; assumptions MCH 4 projects (Class 1: 1; Class 2: 1; Class3: 1; Class 4:1) ; | Asmussen | 2006-01-23 | 2006-01-30 | all
| mid | done | MEP Presentation in PD Board | Bocionek | 2006-01-23 | 2006-01-30 | Schmitz Uwe
| mid | done | Slides all hands meeting to be reworked | Bocionek | 2006-01-30 | 2006-02-01 | Bocionek
| mid | open | actual vision and mission slides to be distributed; Communication guideline | Bocionek | 2006-01-30 | 2006-02-13 | Bocionek
| mid | done | Communication guideline next R&D board; Stuelpner to be invited | Schwab | 2006-01-30 | 2006-02-01 | Bocionek
| high | open | role based team analysis (see scrum team slide) | Bocionek | 2006-01-30 | 2006-02-13 | CoC | Template to be distributed
| high | open | PV roles split TPM-R&D to be agreed | Bocionek | 2006-01-30 | 2006-02-13 | Schmitz
| high | done | IFX SG2 solution to be found regarding switch from platform approach to reference design; benchmarking; contractual position to be clarified; time & cost impacts | Bocionek | 2006-01-30 | 2006-02-06 | Bauregger | FTA on reference board will be performed by IFX; Detailled system speciifaction will be performed bey IFX, BenQ will review the system specification
| high | open | Standard efforts for scenario tool to be provided to Robert Linder | Klebsch | 2006-01-30 | 2006-02-06 | Rudolph; Faesler
| high | open | Add. HC IT consolidated presentation; benchmark figures Med to be added | Klebsch | 2006-01-30 | 2006-02-06 | Schmitz | Info MED missing
| mid | open | MEP metrics benchmarking; target reduce complexity | Bocionek | 2006-01-30 |  | Schmitz | Due date tbc.
| mid | done | Support recruiting office at CeBit; every R&D board memeber half a day | Bocionek | 2006-01-30 | 2006-02-06 | Koch
| mid | open | Kick off to be started; Post mortem analysis to be peformed by project head; Minos team shall show lessons learnt | Bocionek | 2006-01-30 | 2006-02-06 | Klebsch | Kick off to be started wih Mions
| high | done | Transfer Kestrel knowledge to PHA | Eickholt | 2006-01-30 | 2006-02-06 | Topel
| high | done | Apoxi Gemstone cost analysis | Schwab | 2006-02-06 | 2006-02-13 | Schwab/Wingens | incl. CTO
| high | open | Functional performance to be defined and agreed | Klebsch | 2006-02-06 |  | all
| high | open | review and finialize Management objecties agreement | Bocionek/Klebsch | 2006-02-06 | 2006-02-08 | all | document on P:-Drive
| mid | open | check possibility to support Encyrption solution neccessary for HW and SW - PGP und Mail neccessary. | Rudokph | 2006-02-06 | 2006-02-17 | Schmitz/Rudolph
| high | open | KPI Feed Back latest until Thursday | Thonhauser | 2006-02-13 | 2006-02-15 | all CoGs
| high | open | Internal Apoxi meeting for pro/con different Apoxi scenarios | Schwab | 2006-02-13 | 2006-02-16 | Faessler
| high | open | ASP EGR feed back | Didascalou | 2006-02-13 | 2006-02-20 | Bauregger
| high | open | Prototype sample monitoring to be driven by TPM | Thonhauser | 2006-02-13 | 2006-02-20 | Asmussen/Topel
| high | open | Mallow-Goldstone decision to be made within the next 3 weeks; predevelopment decision to be reflected; | Schwab | 2006-02-13 | 2006-03-06 | Topel
| high | open | Qualcomm concepts to be clarified | Thonhauser | 2006-02-13 | 2006-02-27 | Topel/Rudolph/Schwab
2005-04-21

## Zeitkonto
| Total | 2005-08-29 | 2005-10-05 | 2005-11-07 | 2005-11-14 | 2005-12-19
Asmussen | 0:00
Bauregger | 0:00 |  |  |  | 0:00
Didascalou | 0:00 | 0:00
Fässler | 0:00
Klebsch | 0:00 |  | 0:00
Pham | 0:00
Riesmeyer | 0:00 |  |  |  | 0:00
Rudolph | 0:00
Schmitz | 0:00
Schwab | 0:00 | 0:00
Thonhauser | 0:00
Topel | 0:00 | 0:00
Wacker | 0:00
Wingens | 0:00