Program & Project Plans: PLM-Excellence

Program Lead: Siegfried Bocionek

Program Start: Jan 06

Program End: Dec 06

Coach & Steering Board: Jochen Eickholt, tbd

| Project, P-Leader | Project Plans & Milestones | Status 20mar06 | Next Steps |
| --- | --- | --- | --- |
| Uniform Communication in R&D; Bocionek | Start: Jan 06 ongoing 1. Establish regular all hands communication (Jan 06) 2. Engange in breakfast meetings and other activities (start Feb 06) 3. Include PHA R&D in those activities after the PHE/PHA merge (start April 06) | Done | - 2nd all hands R&D meeting on 31. March 06 - First alignment meetings with PHA R&D 23/24 March - breakfast club in Apr 06 |
| High-performing culture & commitment-driven behavior; Bocionek | Start: Jan 06 End: Dec 06; repeat every year 1. KPI metrics (Jan 06) 2. Mgmt Objectives aligned and signed (Feb 06) 3. Balanced Score cards (Feb. 06; moved to April) 4. LQA analysis (R&D only: May 06; moved to March) 4b. opinion poll possible in 2Q06 5. Peer Rating in Mgmt (R&D only; Sept 06) 6. 10 Basic Aspects (Oct 06) 7. Feedback rounds, EFA (Nov/Dec 06) | Done Done | LQA March 06 |
| Real Model-V: Introduce process culture and discipline; Assan | Start: Jan 06 End: Sep 06 1. Name project lead (Feb. 06) – M. Assan 2. Project Plan (Mar 06) 3. Education starts (Mar 06) 4. Internal customer satisfaction metrics set (Mar 06) 5. CIP targets set (Apr. 06) 6. Process adaptations completed (Jun 06) 7. CMMI baseline available(Sep 06) | Done |  |
| Going Agile; U. Schmitz, Faessler, Rudolph | Start: Jan 06 End: Dec 06; continue from there 1. Kick-off for selected projects (01/06) 2. 2. Broad Introduction of Methodology (02/06) 3. Start Ruby project on Agile (02/06) 4. Setup transition team (02/06) 5. Mentoring by OM starts (03/06) 6. Create prioritized transition backlog and transition plan (03/06) 7. Start Gemstone project on Agile (03/06) 8. Scrum teams and sprint planning of pilots established (05/06) 9. Pilot teams trained for TDD and agile principles (06/06) 10. New R&D process for Agile development released (09/06) – proposal in 07/06 11. Start full transition program (09/06) 12. Organization prepared for full agile transition (12/06) | Done Done Done Done Done | - Finish prioritization of transition backlog and Sprint planning - Decompose architecture of Ruby with OM onsite - Define and implement Scrum based requirements handling - Define detailed training schedule and content with OM - Setup Scrum teams in MCH and increase number in WRO |
| Best-in-Test: Wacker | Start: Jan 06 End: Jun 06; continue measuring All teams named, tasks are in progress 1.1 First metric setup (Feb 06) 1.2 – 1.5 complete metrics set up (e.g. defect injection analysis) (May 06) 2. Roll out “new bugs after S4” metric (May 06) 3. Test cases for TDD in scrum team in time (May 06) 4. Roll out “changed LOC” metric after C3 (May 06) 5. Roll out “first pass yield” metric (May 06) 6. KPI targets ST based on metrics data (June) | Done Done | - Detailled data collection - Further alignment with QM |
| Best-in-IT tools; tbd | Start: Jan 06 End: Jun 07 1. Project Plan (Feb 06) 2. Consolidate all teams for PLM (Mar 06) 3. Start centralizing support infra-structure (Mar 06) 4. Increase automation of tool chain (Jul 06) |  | Project lead change to H. Thonhauser (acting); re-set |
| Platform & Portfolio; SB + JE | Start: Jan 06 End: Jun 06 1. Define alignment & change mgmt process (Feb 06), 2. clarify platform responsibilities/activities (Feb 06) 2b. portfolio – budget alignment (Mar 06) 3. define re-use strategy (Mar 06) will become Apr 06 |  | Portfolio / Roadmap vs R&D budget alignment underway in March 06 |
| Invent the future; Bauregger, Hartmann | Start: Jan 06 End: Jun 06 1. Agree on invention disclosure targets (Feb 06) 2. Investigate status and potential measures (Feb.06) 3. Start invention initiative (Mar 06) 4. Implement incentive proposal (Mar 06) 5. Implement organisational changes (Apr.06) 6. 90 invention disclosures filed (Jul 06) 7. 180 invention disclosures filed (Dec 06) | Done Done | Alignment with ISR for invention initiative. Execute organisational change. |
| cleanApoxi platform; Faessler | Start: Jan 06 End: Dec 06 (perhaps earlier) 1. Align all parties incl. IFX, Teleca (Feb 06) 2. Analysis workshop (Mar 06) 3. Diamond decision (Mar 06) 4. Publish formal platform concept, incl. technical specification and usage model (Apr 06) 6. Start skills enhancement program (May 06) 7. Close gaps in Apoxi (tbd) 8. First Apoxi product (tbd; hopefully Apr 07) | Done | Workshop (start 05-Mar-06), Diamond decision (latest EO March) |
| U2 projects; Faessler, Rudolph | Start: Jan 06 End: Mar 06; continue from there 1. Establish weekly reporting of commitment and fulfillment (01/2006) 2. Utilize reporting charts as project/PL control methods (02/2006) 3. Enable team spirit and competition from reported results (03/2006) 4. Establish U2 as practice in all projects (04/06) | Done Done | - continue with practice - Establish comparable ranking between teams of different platforms (Bundesligatabelle) |
| Quality Up of MD; Thonhauser | Start: Jan 06 End: Jun 06 1. PLM MD excellence program and KPI‘s (Jan06) 2. Interdisciplinary Project teams installed 3. MD SQA interface fixed and agreed 4. Visible results (Jul 06) | Done Done Done | Track monthly KPI‘s |
| Thin client phone; Bauregger | Start: Jan 06 End: Aug 06 1. Start Feature definitions (Jan 06) 2. Interdisciplinary team starts (Feb 06) 3. Draft Predevelopment Project Plan (Feb.06) 4. Final Predevelopment Project Plan (Mar.06) 5. System Supplier selection HW and SW (Mar.06) 6. System deliverables agreed with supplier (Apr. 06) 7. Component definition done (e.g. Display, etc.) (Apr.06) 8. Start PCB and Mechanical Design (Apr.06) 9. Prototype running (Jul 06) 10. Documentation (Aug.06) 11. Product decision (Aug 06) | Done Done Done | Investigation of potential platform suppliers (HW/SW) ongoing. Detailed feature alignment with CTM. Develop Stack up concept. Fix final project plan (March). Select system supplier (March). |