## Slide 1: Product Status Report Neo ”The premium messaging device for successful and demanding professionals”
Management Summary
Date: 24.10.2003
Milestone: S0 Information
S-PM: J. Schmitz
PM: H.-J.Frey, H-M. Mues-Hane
PL-T: M. Köhler, H. Bössl
PM-BA: Th. Keller
CM: S. Hirsch

## Slide 2
Product Status Neo ”The premium messaging device for successful and demanding professionals”
Applications
Timing/Market Introduction
Financials
Product
Accessories
Business case negative.
Actual S4 date end of August (2 month delay) due to SX1 impact (Blocking of internal and external software recourses).
Key features: QWERTY-Keyboard; A-GPS (?) ; 1.3 MPix Camera; Open OS
No RF Connector due to design constrains
Status and major changes (regarding last milestone)
always
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3
Positioning:
Business/Reference-Class: SX-class
Target Group: Cosmopolitan Networker
Male >> Female, 25-40 years, high income, professional & private usage
Differentiation to MP products:
Product / design concept (messaging device)
A-GPS variant (?)
MMC card slot
Open OS (Series 60)
MP3 Player (tbd)
Differentiation to Competition:
Product / design concept (messaging device)
MP3 Player (tbd)
A-GPS variant & W-LAN option
Business:
M3 09/04, LC x months
Volume over LC 1.5 Mio
EBIT p.u. Target xx%
Key end user benefits:
Innovative & elegant design combining functionality and esthetic in a surprisung way
Fast & easy text input
High quality photos
Key characteristics:
QWERTY Keypad
Open OS (Series 60)
1,3 mega pixel camera with attachable flash (accessory)
MP3 player (tbd)
External memory (MMC)
A-GPS variant (?)
Key characteristics:
Unique messaging device offering an innovative design merging phone & keypad
Key operator benefits:
Operator specific MMI & hardkey
Full range of messaging services (SMS, MMS, e-mail, IM, PTT)
Assisted GPS variant enabling location-based services
Product Profile Neo ”The premium messaging device for successful and demanding professionals”

## Slide 4
MTA Project Neo ”The premium messaging device for successful and demanding professionals”
time planning
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
Overall Project Status NEO
Software:
Software only partly progress (Predevelopment S60 V2.0). Only very little progress in other areas (System architecture, integration, planning, SWI, …)
Therefore S0-Status for SW not reachable during the next weeks due to resource allocation for SX1
Hardware:
S0 Status reached 1st of October. We now are facing the situation of upcoming investments for tooling and prototypes
Business Case:
Still negative and further negative impact due to TTM
Actions:
Investigation of different scenarios based on SX1 V1.2 Software are not sufficient for TTM and business case
Scenarios based on Penelope could lead to a sufficient solution – further investigation necessary. 1st estimation TTM -> launch end September

## Slide 6
Cost per device: BOM +Conv. Cost + Lic. Fee = HK (EURO)
Quantities (Mio)
Units over Lifecycle
Target
Actual
Major Change compared to last report
List price (EURO)
Launch Price
Phase out price
EBIT
% of turnover
M1
Actual
!
!
!
Financial Status Neo ”The premium messaging device for successful and demanding professionals”
To be updated for NEO
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
Comment :
Accounts: E981-0085, E982-0089 E984-0414
Planning Status: 28.08.2003
Cost overview until M 3
To be updated for NEO
R&D Spending Neo ”The premium messaging device for successful and demanding professionals”

## Slide 8
Risks and Actions Neo (1) ”The premium messaging device for successful and demanding professionals”
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
Risks and Actions Neo (2) ”The premium messaging device for successful and demanding professionals”
Notes: <number>
<footer>
<header>
<date/time>

## Slide 10: Decision options
A – Continue with Neo Not delayed within the mechanical process due to software Release budget for tooling when necessary (before M1)
B – Stop of the project Neo
A
We take the following decision:
B
Present again on

## Slide 11: Backup

## Slide 12: Time schedule Neo
Software:
Due to SX1 2 Month delay for NEO
S0 for SW unclear (target until End Sept.)
Software core team not fully staffed.
External companies (e.g Atelier) aren’t able to support Neo due to SX1
Contract negotiations with Nokia are focusing on SX1 not on Neo. No Series 60 contract available for Neo.
Hardware:
S0 for HW on 4th of Sept S4 for HW on 27th of July 2004
Display 1.9“ on critical path => Only 30k are available end of July 193K are available end of August

## Slide 13: Neo-BOM: History and status
BOM development:
Start Kempinski-WS 145 EUR (Basis Yazoo)
Result of Landshut-WS (21.07-01.08.03) Neo design V3 is 162,00 EUR
V3 includes: - amber keypad LED's (12er block)
- simple QWETRTY keypad (Foil Keypad) - no QWERTY illumination
Current position (25.08.03)
no stacked EGOLD - 1,30 EUR
QWERTY-keypad SL55 like + 5 EUR
red QWERTY illumination + 1 EUR
white keypad LED's (12er block) + 3 EUR
->Neo BOM today: 169,70 EUR

## Slide 14
Neo concept #3
“Yazoo” Kem-pinski
Neo actual design
“Yazoo” Target
Target setting
Concept #3 cost adder
Fugu Qwerty
White LED
DTC no stacked E-Gold
Qwerty LED
Neo BOM development
145
162
170
143

## Slide 15
EBIT: -33,6
“Yazoo” Commitment Kempinski
Neo actual design
Neo actual design
EBIT: -55,5
EBIT: -71,8
Delay / TTM (SX1 impact)
Design concept phase
EBIT: 0
Neo concept #3
EBIT: -59,5
Feature increase
BOM
Volume in Mio.
Price ASP
Neo EBIT development