## UMTS Cockpit
TTM
Cockpit UMTS NIG | Product | update from date | All |  | Next Milestone | [5 empty] | DS / S4 | [5 empty] | Technical Risk Status
|  |  | Input Status | Status | MS |  | MS date | Input Status | Status | History |  |  | date | Input Status | Status | History | TOP Risks |  | Input Status | Status | History
| Wolf 5 | T. Engelhardt | red |  | S2 | Plan | 2005-03-08 | red |  |  | Status | DS | 2005-09-23 | green |  |  | Software implementation by QCT |  | yellow
|  | 2005-04-15 |  |  |  | Current | 2005-04-22 |  |  |  | Current |  | 2005-09-23 |  |  |  | Timely GCF V3.17 approval
| Wolf 4 | Hans Beckers | yellow |  | S2 | Plan | 2005-05-13 | green |  |  | Plan | DS | 2005-11-04 | green |  |  | MMI flex shielding |  | red
|  | 2005-04-15 |  |  |  | Current | 2005-05-13 |  |  |  | Current |  | 2005-11-04 |  |  |  | dependency on W5 SW implementing
| Robin | Klaus Bräuherr | yellow |  | M0 | Plan | 2005-04-22 | green |  |  | Plan | DS | 2006-03-17 | green |  |  | dependency on W5 SW implementing |  | yellow
|  | 2005-04-15 |  |  |  | Current | 2005-04-29 |  |  |  | Current |  | 2006-03-17 |  |  |  | feature support by QCT (capacity)
| Kestrel | Holger Petersen | yellow |  | S0 | Plan | 2005-04-08 | yellow |  |  | Plan | DS | 2006-02-27 | green |  |  | dependency on W5 SW implementing |  | yellow
|  | 2005-04-15 |  |  |  | Current | 2005-04-20 |  |  |  | Current |  | 2006-02-27 |  |  |  | ultra slim new housing technology
| Product | update from date | Resource Situation | [7 empty] | Project-Budget | [5 empty] | BOM / HK (incl.Challenge)
|  |  | TOP Problems |  |  |  |  | Input Status | Status | History |  | Budget |  | Input Status | Status | History |  | BOM / HK (incl.Challenge) | Input Status | Status | History
| Wolf 5 | T. Engelhardt | [5 empty] | green |  |  | target M1 | 49000000 |  | green |  |  | target M1 | 129 | yellow
|  | 2005-04-15 | [8 empty] | Current | 49000000 |  |  |  |  | Current | 134.57
| Wolf 4 | Hans Beckers | Resource situation stable |  |  |  |  | green |  |  | target | 26600000 |  | green |  |  | target M1 | 125 (117) € | green
|  | 2005-04-15 | [15 empty] | 124
| Robin | Klaus Bräuherr | Replanning is ongoing because DS |  |  |  |  | yellow |  |  | target | 18300000 |  | blank |  |  | target M-alpha | 100 | yellow
|  | 2005-04-15 | pulled in from May to March/06 | [14 empty] | 110
| Kestrel | Holger Petersen | Late release of ressources for working teams, |  |  |  |  | yellow |  |  | target M0 | 20500000 |  | green |  |  | target M0 | 122 ( 111) € | yellow
|  | 2005-04-15 | holiday from 2004, several changes in team | [14 empty] | 128
Hidden infomation. |  | Legend: History | [8 empty] | Icons: |  | Hints on data entry:
ü
List for traffic light: |  | traffic light has improved compared to last status report | [10 empty] | 1 |  | Traffic lights are driven by input in column named "Input Status"
green | [12 empty] | 2 |  | Trend icons have to be copied from Legend (see left side)
yellow |  | no change of traffic compared to last status report | [10 empty] | 3 |  | Please hide columns D, I, O, T, Y, AD, AI by pressing button
red | [14 empty] | butten for level 1 in the very top left corner of this sheet
blank |  | traffic light worser compared to last status report
[13 empty] | x |  | Please see also comments behind cells
Table for use of history symbols:
|  | last |  | actual |  | Symbol
|  | green |  | green
|  | green |  | yellow or red
|  | yellow |  | yellow
|  | yellow |  | green
|  | yellow |  | red
|  | red |  | red
|  | red |  | yellow or green
Note on D4: green: all lights are green yellow: no red, but one or more yellow lights red: 1 or more red lights
Note on I4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on I16: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on K4: here please state the trend of traffic light in the past - examples see below
Note on K16: here please state the trend of traffic light in the past - examples see below
Note on M5: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M7: DS when "Next Milestone" is before DS, S4 when "Next Milestone" is DS or later
Note on M9: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M11: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on O4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on O16: green: less than +/- 3% deviation *) yellow: between +/- 3% and +6% deviation *) red: more than +/- 6% deviation *) *) shall cover both actual status and M3 prognosis
Note on Q4: here please state the trend of traffic light in the past - examples see below
Note on Q16: here please state the trend of traffic light in the past - examples see below
Note on T4: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on T16: green: better or equal yellow: max. +3 Euro red: more than +3 Euro (compared to target)
Note on V4: here please state the trend of traffic light in the past - examples see below
Note on V16: here please state the trend of traffic light in the past - examples see below