## EG V3, EG Lite Cockpit
TTM
Cockpit EG Lite EG V3 | Product | update from date | All |  | Next Milestone | [5 empty] | DS / S4 | [5 empty] | Technical Risk Status
|  |  | Input Status | Status | MS |  | MS date | Input Status | Status | History |  |  | date | Input Status | Status | History | TOP Risks |  | Input Status | Status | History
| Libra | C. Ziegler | yellow |  | Plan | S3HW | not planned | blank |  |  | Plan | DS | 2005-05-06 | yellow |  |  | availability of UC with new display lens (200Nm static load) |  | yellow
|  | 2005-04-15 |  |  | Current |  | 2005-04-15 |  |  |  | Current |  | 2005-05-20 |  |  |  | high NCCPI 32000 due to a lot of SW bugs (DS criteria NCCPI 7000)
| Dorado | C. Ziegler | red |  | Plan | S25 | 2005-02-25 | red |  |  | Plan | DS | 2005-05-20 | yellow |  |  | ENSURE DS 3.6. / drop test failed in 3rd OT |  | red
|  | 2005-04-15 |  |  | Current |  | 2005-04-22 |  |  |  | Current |  | 2005-06-03 |  |  |  | ESD problems caused by instability of conduct rubber at speaker cover
| Pegasus | C. Ziegler | red |  | Plan | S25 | 2005-03-17 | red |  |  | Plan | DS | 2005-05-30 | red |  |  | drop test failed in 3rd OT |  | yellow
|  | 2005-04-15 |  |  | Current |  | 2005-04-23 |  |  |  | Current |  | 2005-06-17 |  |  |  | ESD problems on keypad
| Flamingo | C. Ziegler | yellow |  | Plan | S2 | 2005-05-26 | green |  |  | Plan | DS | 2005-10-24 | green |  |  | delay of modified displays leads to reduction of evaluation time |  | yellow
|  | 2005-04-15 |  |  | Current |  | 2005-05-26 |  |  |  | Current |  | 2005-10-24 |  |  |  | new SIM card reader need 80% rework due to bad coplanarity
| Quail | C. Ziegler | yellow |  | Plan | S0 | 2005-04-21 | green |  |  | Plan | DS | 2006-01-24 | yellow |  |  | bending during poplation due to IO in west |  | yellow
|  | 2005-04-15 |  |  | Current |  | 2005-04-21 |  |  |  | Current |  | 2006-02-01 |  |  |  | implementation of slim line antenna concept
| Finch | C. Ziegler | yellow |  | Plan | S0 | 2005-04-12 | yellow |  |  | Plan | DS | 2006-01-26 | yellow |  |  | leading pojrect of NANO IO |  | green
|  | 2005-04-15 |  |  | Current |  | 2005-04-20 |  |  |  | Current |  | 2006-02-07 |  |  |  | Change to SD2 due to DTC shifts DS 3days after CNY - opt. ongoing
| Pelicane | C. Ziegler | green |  | Plan | M0 | 2005-04-22 | green |  |  | Plan | DS | 2006-03-01 | green |  |  | Currently no risks / M0 workshop 18.-22.04. |  | green
|  | 2005-04-15 |  |  | Current |  | 2005-04-29 |  |  |  | Current |  | 2006-03-01
| Lark | not started yet | blank |  | Plan |  |  | blank |  |  | Plan | DS | 06.06 | blank |  |  |  |  | blank
[5 empty] | Current | [5 empty] | Current
| Product | update from date | Resource Situation | [7 empty] | Project-Budget | [5 empty] | BOM / HK (incl.Challenge)
|  |  | TOP Problems |  |  |  |  | Input Status | Status | History |  | Budget (total direct costs) |  | Input Status | Status | History |  | BoM / HK over Life Cycle in EUR | Input Status | Status | History
| Libra | C. Ziegler | no problems yet |  |  |  |  | green |  |  | target M1 | 4'4 |  | green |  |  | M1 value | 36.72 / - | green
|  | 2005-04-15 | [8 empty] | Actual/FC (03.05) | 2'7 / 3'7 |  |  |  |  | S25 value - 15.04.2005 | 35.25 / 41.79
| Dorado | C. Ziegler | EA equip. critical for R&TTE & FCC aprroval |  |  |  |  | yellow |  |  | target M1 | 3'0 |  | green |  |  | M1 value | 24.44 / - | yellow
|  | 2005-04-15 | [8 empty] | Actual/FC (03.05) | 1'8 / 2'6 |  |  |  |  | S2 value - 20.03.2005 | 25.28 / 29.70
| Pegasus | C. Ziegler | no problems yet |  |  |  |  | green |  |  | target M1 | 4'4 |  | green |  |  | M1 value | 41.67 / - | green
|  | 2005-04-15 | [8 empty] | Actual/FC (03.05) | 2'8 / 3'6 |  |  |  |  | S2 value - 03.02.2005 | 36.15 / -
| Flamingo | C. Ziegler | no problems yet |  |  |  |  | green |  |  | target M1 | 5'6 |  | green |  |  | M1 value | 45.55 / - | green
|  | 2005-04-15 | [8 empty] | Actual/FC (03.05) | 0'6 / 4'6 |  |  |  |  | M1 - 27.01.2005 | 45.55 / -
| Quail | C. Ziegler | no problems yet |  |  |  |  | green |  |  | target M0 | 3'8 |  | green |  |  | M0 value | 43.20 / 50.44 | blank
|  | 2005-04-15 | [8 empty] | Actual/FC (15.04.05) | 0'1 / 3'8 |  |  |  |  | M0 value - 21.03.05 | 43.20 / 50.44
| Finch | C. Ziegler | Due to SD2 DTC need of double PCB qual. ongoing |  |  |  |  | green |  |  | target M0 | 3'8 |  | green |  |  | M0 value | 35.54 / 42.00 | blank
|  | 2005-04-15 | [8 empty] | Actual/FC (15.04.05) | 0'1 / 3'8 |  |  |  |  | M0 value - 21.03.05 | 35.54 / 42.00
| Pelicane | C. Ziegler | PPLs mostly named. Contact persons as standin |  |  |  |  | green |  |  |  | M0 not reached yet |  | blank |  |  | M0 value | MS not reached | blank
|  | 2005-04-15 | [8 empty] | FC M3 (16.03.05) | 3'1
| Lark | not started yet | [5 empty] | blank |  |  |  | M0 not reached yet |  | blank |  |  | M0 value | MS not reached | blank
[11 empty] | FC M3 (16.03.05) | 2'9
Hidden infomation. |  | Legend: History | [8 empty] | Icons: |  | Hints on data entry:
ü
List for traffic light: |  | traffic light has improved compared to last status report | [10 empty] | 1 |  | Traffic lights are driven by input in column named "Input Status"
green | [12 empty] | 2 |  | Trend icons have to be copied from Legend (see left side)
yellow |  | no change of traffic compared to last status report | [10 empty] | 3 |  | Please hide columns D, I, O, T, Y, AD, AI by pressing button
red | [14 empty] | butten for level 1 in the very top left corner of this sheet
blank |  | traffic light worser compared to last status report
[13 empty] | x |  | Please see also comments behind cells
Table for use of history symbols:
|  | last |  | actual |  | Symbol
|  | green |  | green
|  | green |  | yellow or red
|  | yellow |  | yellow
|  | yellow |  | green
|  | yellow |  | red
|  | red |  | red
|  | red |  | yellow or green
Note on D4: green: all lights are green yellow: no red, but one or more yellow lights red: 1 or more red lights
Note on I4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on I24: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on K4: here please state the trend of traffic light in the past - examples see below
Note on K24: here please state the trend of traffic light in the past - examples see below
Note on M5: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M7: DS when "Next Milestone" is before DS, S4 when "Next Milestone" is DS or later
Note on M9: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M11: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M13: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M15: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M17: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M19: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on N7: Claus Ziegler: PV baseline: 20-May-05 PL-T: 19-May-05
Note on N9: Claus Ziegler: wrong date in PV M1 baseline at M1: DS PV plan: 20-Jun-05 DS PLT: 30-May-05
Note on N11: Claus Ziegler: Commited DS is 24-Oct-05. Agressiv Team Challeange to reach DS matching X-mas is 05-Oct-05 (PV plan)
Note on O4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on O24: green: less than +/- 3% deviation *) yellow: between +/- 3% and +6% deviation *) red: more than +/- 6% deviation *) *) shall cover both actual status and M3 prognosis
Note on Q4: here please state the trend of traffic light in the past - examples see below
Note on Q24: here please state the trend of traffic light in the past - examples see below
Note on T4: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on T24: green: better or equal yellow: max. +3 Euro red: more than +3 Euro (compared to target)
Note on V4: here please state the trend of traffic light in the past - examples see below
Note on V24: here please state the trend of traffic light in the past - examples see below